## BTOP
LCR | COUNTY | LOCATION NAME | Build Type | AGENCY | Router Serial Number | BTOP - NT10BIX5570031 Asset Tag Number | Shipping Tracking Number | Router Deployed | Reconciliation with TeleHealth Alliance Grant or Eliminated | Reconciliation with POCs/FTR/GIT | Agency Supported by | Date LCR Received | ENGINEERING REQUIRED | ENGINEERING SUBMITTED | LCR Total Construction Cost | Rejected (Y/N) | Revision Received | LCR Final Approval Notice | ENGINEERING APPROVED | Approved Fiber Footage | Report Column - Fiber feet to be pulled by Frontier | Schedule for Fiber Completion | SCHEDULE FOR FIBER COMPLETION | Fiber Footage Completed | Facilities Build-Out Required | FACILITY BUILD OUT INFO | Facilites Build-Out Scheduled | Facilities Build-Out Completed | Completed to the DMARC | COMPLETED TO DMARC | DMARC COMPLETION DATE | ROUTER DEPLOYMENT INFO | ROUTER DEPLOY DATE | CAI COMPLETE | CAI Notification Date Ready for Service | Comments / Issues | Selected for QA Review | QA Review Completion Date | QA Report Submitted To BTOP/NTIA
BB01A01 | BARBOUR | Barbour County Courthouse | FR | CHOUSE | FTX1441A0PE | 581 | Delivered and Installed by Tech | 2012-06-27 |  | fiber and router needed | WVNET | 2011-05-06 | Y | Y | 11447.2 | N |  | 2011-05-26 | Y | 1420 | 1420 | 2011-10-01 | Complete | 2011-09-09 | N | No Build Required |  |  | 2011-09-20 | Complete | 2011-09-20 | Complete | 2012-06-27 | Ready | 2012-08-10 | **LCR WAS LISTED ON MIKE TORDORVICH'S MEMO TO APPROVE 26 LCRs ON 4/15/2011**
BB01A02 | BARBOUR | BELINGTON ELEMENTARY & MIDDLE SCHOOLS | FR | K12 | FTX1442A1XF | 316 |  | 2011-08-25 |  | fiber and router needed | K-12 | 2011-04-08 | Y | Y | 54308.8 | N |  | 2011-05-26 | Y | 6880 | 6880 | 2012-02-01 | Complete | 2011-04-21 | Y | Complete | 2012-06-21 | 2012-04-30 | 2012-05-16 | Complete | 2012-05-16 | Complete | 2011-08-25 | Ready | 2012-05-18 | **LCR WAS LISTED ON MIKE TORDORVICH'S MEMO TO APPROVE 26 LCRs ON 4/15/2011**
BB01A03 | BARBOUR | PHILIPPI ELEMENTARY & MIDDLE SCHOOLS | FR | K12 | FTX1442A2C6 | 317 |  | 2011-09-09 |  | per FTR; site already has fiber- router only; PER FTR- THIS CAI WAS ADDED BACK TO BUILD LIST ON 1/24/12 PER GIT DECISION | K-12 | 2012-01-27 | Y | Y | 29124 | Y | 2012-02-13 | 2012-04-09 | Y | 4215 | 4215 | 2012-02-01 | Complete | 2012-05-29 | Y | Complete |  | 2012-06-06 | 2012-07-16 | Complete | 2012-07-16 | Complete | 2011-09-09 | Ready
BB01A04 | BARBOUR | JUNIOR ELEMENTARY SCHOOL | FR | K12 | FTX1442A1YQ | 318 |  | 2011-08-29 |  | fiber and router needed | K-12 | 2011-04-15 | Y | Y | 186268.74 | N |  | 2011-09-26 | Y | 24969 | 24969 | 2012-02-01 | Complete | 2012-08-16 | N | No Build Required |  |  | 2012-08-16 | Complete | 2012-08-16 | Complete | 2011-08-29 | Ready | 2012-08-17
BB01A05 | BARBOUR | KASSON ELEMENTARY/MIDDLE SCHOOL | RO | K12 | FTX1442A1T6 | 319 |  | 2012-01-10 |  | Per FTR - This site will be engineered from an outside FTR related Project and will not have fiber built as a part of the BTOP Grant. Router Only | K-12 | 2011-04-15 | Y | Y | 229909.74 | N |  | 2011-09-08 | Y | 30819 | 30819 | 2012-03-01 | Complete | 2012-09-21 | N | No Build Required | N/A | N/A | 2012-09-21 | Complete | 2012-09-21 | Complete | 2012-01-10 | Ready | 2012-04-04
BB01A06 | BARBOUR | MOUNT VERNON ELEMENTARY SCHOOL | FR | K12 | FTX1442A1HU | 320 |  | 2012-01-10 |  | fiber and router needed | K-12 | 2011-04-15 | Y | Y | 161113.62 | N |  | 2011-09-08 | Y | 21597 | 21597 | 2012-02-01 | Complete | 2012-03-20 | Y | Complete | 2012-06-05 | 2012-04-20 | 2012-05-10 | Complete | 2012-05-10 | Complete | 2012-01-10 | Ready | 2012-05-10 | * FBO Notified - Contractor notified WVOT and Frontier that FBO is required at this site. Frontier confirmed the work is required and agreed to move forward with the FBO. 2/2/12* *FBO Update - Backboard Placed for location - $50 charge will be added to final invoice for the placement. Michelle - Gudenkauf - 4/17/12*
BB01A07 | BARBOUR | PHILIP BARBOUR HIGH SCHOOL | FR | K12 | FTX1442A2CY | 321 |  | 2011-04-20 |  | per FTR; site already has fiber- router only; PER FTR- THIS CAI WAS ADDED BACK TO BUILD LIST ON 1/24/12 PER GIT DECISION | K-12 | 2012-01-27 | Y | Y | 31556.75 | N |  | 2012-04-09 | Y | 2150 | 2150 | 2012-02-01 | Complete | 2012-05-21 | N | No Build Required |  |  | 2012-05-21 | Complete | 2012-05-21 | Complete | 2011-04-20 | Ready | 2012-05-25
BB01A08 | BARBOUR | VOLGA CENTURY ELEMENTARY SCHOOL | FR | K12 | FTX1442A1YW | 322 |  | 2012-01-10 |  | fiber and router needed | K-12 | 2011-04-15 | Y | Y | 41124 | N |  | 2011-09-08 | Y | 2926 | 2926 | 2012-01-01 | Complete | 2011-12-09 | N | No Build Required |  |  | 2011-12-09 | Complete | 2011-12-09 | Complete | 2012-01-10 | Ready | 2012-02-17
BB01A09 | BARBOUR | Philippi Public Library | FR | LIB | FTX1439A16L | 679 |  | 2011-10-17 |  | fiber and router needed | WVNET | 2011-05-06 | Y | Y | 7310.8 | N |  | 2011-05-26 | Y | 980 | 980 | 2012-02-01 | Complete | 2011-09-02 | Y | Complete | 2012-06-12 | 2012-04-20 | 2012-05-08 | Complete | 2012-05-08 | Complete | 2011-10-17 | Ready | 2012-05-10 | **LCR WAS LISTED ON MIKE TORDORVICH'S MEMO TO APPROVE 26 LCRs ON 4/15/2011**
BB01A10 | BARBOUR | Barbour County 9-1-1 | FR | PSAP | FTX1436AJTD | 1385 |  | 2012-01-17 |  | fiber and router needed |  | 2011-10-19 | Y | Y | 28133 | N |  | 2011-11-09 | Y | 2149 | 2149 | 2012-01-01 | Complete | 2011-12-23 | N | No Build Required |  |  | 2011-12-23 | Complete | 2011-12-23 | Complete | 2012-01-17 | Ready | 2012-02-02
BB01A11 | BARBOUR | Philippi Barbour - Troop 3 State Police | RO | SP | FTX1439A25W | 1083 |  | 2011-12-29 |  | per FTR; site already has fiber- router only | State Police |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-12-29 | Ready | 2012-01-27
BB01A12 | BARBOUR | Belington Community Medical Services Association, Inc. | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB01A13 | BARBOUR | Brandon Wellness Center | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB02A01 | BERKELEY | Berkeley County Courthouse | FR | CHOUSE | FTX1441AHZE | 582 | Delivered and Installed by Tech | 2012-07-11 |  | fiber and router needed | WVNET | 2011-06-20 | Y | Y | 26611.74 | N |  | 2011-07-05 | Y | 3619 | 3619 | 2012-02-01 | Complete | 2012-01-23 | N | No Build Required |  |  | 2012-01-23 | Complete | 2012-01-23 | Complete | 2012-07-11 | Ready
BB02A02 | BERKELEY | Martinsburg Correctional Center | FR | CORR | FTX1443AK9T | 606 |  | 2012-03-23 |  |  | WVOT | 2011-06-20 | Y | Y | 4907 | N |  | 2011-12-22 | Y | 6650 | 6650 | 2012-03-01 | Complete | 2012-02-27 | N | No Build Required |  |  | 2012-02-27 | Complete | 2012-02-27 | Complete | 2012-03-23 | Ready | 2012-04-05
BB02A03 | BERKELEY | Martinsburg Parole Office | FR | CORR | FTX1444AJ0Z | 607 |  |  |  | fiber and router needed | WVOT | 2011-06-20 | Y | Y | 137119 | Y | 6/27/2011; 8/23/2011 | 2011-10-31 | Y | 11150 | 11150 | 2012-02-01 | Complete | 2012-01-26 | N | No Build Required |  |  | 2012-01-26 | Complete | 2012-01-26 | TBD |  | Waiting on Router
BB02A04 | BERKELEY | STARS Youth Reporting Center | FR | DJS | FTX1444AHK5 | 472 |  |  |  |  | WVOT | 2011-06-20 | Y | Y | 15302 | N |  | 2011-10-31 | Y | 1969 | 1969 | 2012-02-01 | Complete | 2012-02-23 | N | No Build Required |  |  | 2012-02-23 | Complete | 2012-02-23 | TBD |  | Waiting on Router
BB02A05 | BERKELEY | Vicky V Douglas Juv Cnt | FR | DJS | FTX1444AJ0W | 473 |  |  |  |  | WVOT | 2011-06-20 | Y | Y | 67379 | N | 7/11/11 ($162,357.00) | 2011-10-31 | Y | 9032 | 9032 | 2012-02-01 | Complete | 2012-02-23 | N | No Build Required |  |  | 2012-02-23 | Complete | 2012-02-23 | TBD |  | Waiting on Router
BB02A06 | BERKELEY | WVIEP - BOARD OF CHILD CARE | FR | K12 | FTX1442A2D2 | 323 |  | 2011-08-05 |  | fiber and router needed | K-12 | 2011-06-20 | Y | Y | 48182.24 | N |  | 2011-10-31 | Y | 6444 | 6444 | 2012-02-01 | Complete | 2012-01-23 | N | No Build Required |  |  | 2012-01-23 | Complete | 2012-01-23 | Complete | 2011-08-05 | Ready | 2012-02-23 | *Stephens Excavating has gone out to this site to begin the estimate process. They met with the regular contact Dave Kenny and was making progress on the estimation when a maintenance director informed him that there is no digging permitted on this site. We will have to work with the Administration for this location due to their students being on campus all year around and the building not being owned by the state. The contractor informed me that there is no way to go aerial with this job without installing some poles and also they cannot utilize the existing conduit because it is full. I have spoken to Jeff Krystofika about this situation and informed him the on premise job will be at no expense to them. Also I agreed to let them review the path of the newly required work before we go out to this location and begin any form of approval to save them any issues or time. I let him know that if there is and sidewalk/parking lot/ground disturbed we will be replacing it to the best of our ability to be sure that we leave things just as good as they were when we came on site. This site will be going through our approval process which is now: 1. Contractor Submits an estimate with Map, GPS Coordinates, and Pictures of designated path to the WV Office of Technology. 2. Estimate, Map, GPS Coordinates, and Pictures reviewed by the CEO of the Child Care Office for approval for them to plan around the construction for the safety of their students. 3. Environmental Assessment for approval on the path generated with GPS coordinates, Map, and Pictures. 4. WV Office of Technology for Final Approval on job. 5. Approved estimate forwarded to Contractor to begin their construction on site. Jeff Krystofika – (304) 276-3304 - Supervisor – jkrystofika@boardofchildcare.org* *FBO Hold - 8/1/12 - Pending Board of Child Care Administration approval. - Nick Patel - 8/1/12* *FBO Update - Recieved FBR, EST, and EA Mapping today. Will make contact with Board of Child Care Administration to begin the Approval Process. Disclaimer on the FBR states that "All rock will be invoiced as an extra cost @ $6/CU. FT. In areas of rocky soil conditions where stone and dust is required, stone dust will be provided at an extra cost of $18/ TON in place." This can add some cost to the current estimate if this type of work is required. 8/1/12 - Nick Patel* *FBO Hold - WVIEP Schools Demarc Extensions Pending approval by the GIT*
BB02A07 | BERKELEY | North Berkeley Public Library | FR | LIB | FTX1439AJYJ | 815 |  | 2012-07-17 |  | fiber and router needed | WVNET | 2011-06-20 | Y | Y | 83188.2 | N |  | 2011-10-31 | Y | 11070 | 11070 | 2012-02-01 | Complete | 2011-11-24 | Y | Complete | 2012-01-04 | 2012-01-06 | 2012-01-24 | Complete | 2012-01-24 | Complete | 2012-07-17 | Ready
BB02A08 | BERKELEY | Naylor Memorial Public Library | FR | LIB | FTX1439A177 | 814 |  | 2012-07-17 |  | fiber and router needed | WVNET | 2011-06-20 | Y | Y | 22416.76 | Y | 2011-06-24 | 2011-07-05 | Y | 2926 | 2926 | 2011-12-01 | Complete | 2011-08-31 | N | No Build Required |  |  | 2011-11-18 | Complete | 2011-11-18 | Complete | 2012-07-17 | Ready | 2012-08-10
BB02A09 | BERKELEY | Musselman-South Berkeley Community Library | FR | LIB | FTX1439A176 | 825 |  | 2012-07-18 |  | fiber and router needed | WVNET | 2011-06-20 | Y | Y | 24661.4 | N |  | 2011-10-31 | Y | 3690 | 3690 | 2012-02-01 | Complete | 2012-01-26 | N | No Build Required |  |  | 2012-01-26 | Complete | 2012-01-26 | Complete | 2012-07-18 | Ready
BB02A10 | BERKELEY | Martinsburg-Berkeley Co. Public Library | FR | LIB | FTX1439A144 | 826 |  | 2012-07-18 |  | fiber and router needed | WVNET | 2011-06-20 | Y | Y | 16796.22 | N |  | 2011-07-05 | Y | 2147 | 2147 | 2012-02-01 | Complete | 2012-01-30 | N | No Build Required |  |  | 2012-01-30 | Complete | 2012-01-30 | Complete | 2012-07-18 | Ready
BB02A11 | BERKELEY | Region 9–Eastern Panhandle Regional Planning and Development (Berkeley, Jefferson, Morgan) | FR | PDEV | FTX1436A1XV | 1019 | 1ZX560410300469388 | 2011-09-28 |  | fiber and router needed | ? | 2011-06-20 | Y | Y | 3414.6 | N |  | 2011-07-05 | Y | 310 | 310 | 2012-03-01 | Complete | 2012-01-26 | N | No Build Required |  |  | 2012-01-26 | Complete | 2012-01-26 | Complete | 2011-09-28 | Ready | 2012-02-02
BB02A12 | BERKELEY | Central Dispatch | FR | PSAP | FTX1436AJV2 | 1343 |  | 11/15/2011 |  | fiber and router needed |  | 2011-06-20 | Y | Y | 5057 | N |  | 2011-10-31 | Y | 550 | 550 | 2012-02-01 | Complete | 2012-02-23 | N | No Build Required |  |  | 2012-02-23 | Complete | 2012-02-23 | Complete | 11/15/2011 | Ready | 2012-03-02
BB02A13 | BERKELEY | Eastern Regional Jail | FR | RJAIL | FTX1436A1R5 |  |  | 2012-05-15 |  |  | WVOT | 2011-06-20 | Y | Y | 5121 | N |  | 2011-10-31 | Y | 794 | 794 | 2012-02-01 | Complete | 2012-02-23 | N | No Build Required |  |  | 2012-02-23 | Complete | 2012-02-23 | Complete | 2012-05-15 | Ready | 2012-05-18 | *Router Update -Router Was Distributed out of the 100 WVOT Routers Before Regular Distribution. BTOP Tag is Currently Unknown - Nick Patel - 5/15/12*
BB02A14 | BERKELEY | Martinsburg / Berkeley - Troop 2 State Police | FR | SP | FTX1439A23M | 1037 |  | 2011-12-13 |  | fiber and router needed | State Police | 2011-06-20 | Y | Y | 122616.04 | N |  | 2011-10-31 | Y | 16374 | 16374 | 2012-03-01 | Complete | 2012-02-21 | N | No Build Required |  |  | 2012-02-21 | Complete | 2012-02-21 | Complete | 2011-12-13 | Ready | 2012-02-23
BB02A15 | BERKELEY | WVU Robert C Byrd Health Sciences Center Eastern Division | FR | TMED | FTX1436A1QZ | 847 | 1ZX560410300455919 | 2011-11-14 |  | fiber and router needed | ? | 2011-06-20 | Y | Y | 115023.8 | Y | 7/13/2011; 8/23/2011 | 2011-10-31 | Y | 16846 | 16846 | 2012-02-01 | Removed | 2012-04-09 | N | Removed |  |  | 2012-04-11 | Removed | 2012-04-11 | N/A | 2011-11-14 | Removed | 2012-04-13
BB02A16 | BERKELEY | City Hospital | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB03A01 | BOONE | Boone County Courthouse | RO | CHOUSE | FTX1441AHZK |  |  |  |  | per FTR; site already has fiber- router only | WVNET |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | TBD |  | Waiting on Router | N/A
BB03A02 | BOONE | *SHERMAN JUNIOR HIGH & HIGH SCHOOLS | RO | K12 | FTX1437A1NB | 124 |  | 2011-05-27 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-05-27 | Ready | 2012-01-05 | Location is listed as one building, but has 2 different schools. We have 2 routers listed for this location - BTOP TAG - 124 and 137 router serial numbers FTX1437A1NB and FTX1437A1P3
BB03A03 | BOONE | ASHFORD-RUMBLE ELEMENTARY | RO | K12 | FTX1437A1Q2 | 125 |  | 2011-05-02 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-05-02 | Ready | 2012-01-05
BB03A04 | BOONE | BOONE COUNTY ADULT BASIC EDUCATION | FR | K12 | FTX1437A1P8 | 126 |  | 2011-11-10 |  | fiber and router needed | K-12 | 2011-10-03 | Y | Y | 18256.5 | N |  | 2012-05-10 | Y | 2200 | 2200 | 2012-06-01 | Complete | 2012-06-30 | Y | TBD |  |  |  | TBD | N/A | Complete | 2011-11-10 | TBD
BB03A05 | BOONE | BOONE COUNTY CAREER CENTER | RO | K12 | FTX1437AJJ3 | 127 |  | 2011-06-15 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-06-15 | Ready | 2012-01-05
BB03A06 | BOONE | BROOKVIEW ELEMENTARY | RO | K12 | FTX1437AJJB | 128 |  | 2011-06-15 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-06-15 | Ready | 2012-01-05
BB03A07 | BOONE | JEFFREY-SPENCER ELEMENTARY SCHOOL | RO | K12 | FTX1437AJJD | 129 |  | 2011-06-15 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-06-15 | Ready | 2012-01-05
BB03A08 | BOONE | MADISON ANNEX PRE-SCHOOL | RO | K12 | FTX1437A1NU | 130 |  | 2011-05-25 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-05-25 | Ready | 2012-01-05
BB03A09 | BOONE | MADISON ELEMENTARY SCHOOL | RO | K12 | FTX1437A1PX | 131 |  | 2011-06-15 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-06-15 | Ready | 2012-01-05
BB03A10 | BOONE | MADISON MIDDLE SCHOOL | RO | K12 | FTX1437A1QK | 132 |  | 2011-06-15 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-06-15 | Ready | 2012-01-05
BB03A11 | BOONE | NELLIS ELEMENTARY SCHOOL | RO | K12 | FTX1437A1QM | 133 |  | 2011-05-02 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-05-02 | Ready | 2012-01-05
BB03A12 | BOONE | RAMAGE ELEMENTARY SCHOOL | RO | K12 | FTX1442A1TM | 134 |  | 2011-05-25 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-05-25 | Ready | 2012-01-05
BB03A13 | BOONE | SCOTT HIGH SCHOOL | RO | K12 | FTX1437AJJ2 | 135 |  | 2011-06-15 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-06-15 | Ready | 2012-01-05
BB03A14 | BOONE | SHERMAN ELEMENTARY SCHOOL | RO | K12 | FTX1437A1N8 | 136 |  | 2011-05-02 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-05-02 | Ready | 2012-01-05
BB03A15 | BOONE | SHERMAN HIGH SCHOOL | RO | K12 | FTX1437A1P3 | 137 |  | 2011-05-27 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-05-27 | Ready | 2012-01-05 | Location is listed as one building, but has 2 different schools. We have 2 routers listed for this location - BTOP TAG - 124 and 137 router serial numbers FTX1437A1NB and FTX1437A1P3
BB03A16 | BOONE | VAN ELEMENTARY | RO | K12 | FTX1437A1QU | 138 |  | 2011-05-26 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-05-26 | Ready | 2012-01-05
BB03A17 | BOONE | VAN JUNIOR-SENIOR HIGH SCHOOL | RO | K12 | FTX1437AJJ4 | 139 |  | 2011-05-25 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-05-25 | Ready | 2012-01-05
BB03A18 | BOONE | WHARTON ELEMENTARY | RO | K12 | FTX1437A1P6 | 140 |  | 2011-05-25 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-05-25 | Ready | 2012-01-05
BB03A19 | BOONE | WHITESVILLE ELEMENTARY SCHOOL | RO | K12 | FTX1437A1R8 | 141 |  | 2011-05-02 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-05-02 | Ready | 2012-04-16
BB03A20 | BOONE | WVIEP - DONALD KUHN JUVENILE CENTER DJS | FR | K12 | FTX1437AJHP | 142 |  | 2011-06-15 |  | fiber and router needed | K-12 | 2011-12-08 | Y | Y | 35435.48 ($38,468.21) | Y | 2011-12-09 | 2012-05-10 | Y | 5791 | 5791 | 2012-06-01 | Complete | 2012-07-12 | N | No Build Required |  |  | 2012-07-12 | Complete | 2012-07-12 | Complete | 2011-06-15 | Ready
BB03A21 | BOONE | Coal River Public Library | FR | LIB | FTX1439A140 | 780 |  | 2012-05-15 |  | fiber and router needed | WVNET | 2011-11-30 | Y | Y | 15172.47 | Y | 2011-12-07 | 2012-05-10 | Y | 480 | 480 | 2012-06-01 | 2012-06-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2012-05-15 | TBD
BB03A22 | BOONE | Barrett-Wharton Public Library | FR | LIB | FTX1439AK00 | 783 |  | 2012-05-22 |  | fiber and router needed | WVNET | 2011-11-08 | Y | Y | 5641.98 | N |  | 2012-05-10 | Y | 329 | 329 | 2012-06-01 | Complete | 2012-05-25 | Y | Scheduled | 2012-07-09 |  | 2012-08-29 | Complete | 2012-08-29 | Complete | 2012-05-22 | Ready | 2012-08-31
BB03A23 | BOONE | Boone-Madison Public Library | FR | LIB | FTX1439AJVW | 750 |  | 2012-02-28 |  | fiber and router needed | WVNET | 2011-10-03 | Y | Y | 14764.82 | y | 2012-01-27 | 2012-05-10 | Y | 2345 | 2345 | 2012-06-01 | Complete | 2012-08-10 | Y | TBD |  |  |  | TBD |  | Complete | 2012-02-28 | TBD
BB03A24 | BOONE | Whitesville Public Library | FR | LIB | FTX1439A16K | 781 |  | 2012-05-15 |  | fiber and router needed | WVNET | 2011-11-06 | Y | Y | 9038.89 | N |  | 2012-05-10 | Y | 1157 | 1157 | 2012-06-01 | 2012-06-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2012-05-15 | TBD
BB03A25 | BOONE | Boone County Emergency Ops | FR | PSAP | FTX1436AJTZ | 1381 |  | 2012-01-30 |  | fiber and router needed |  | 2011-09-07 | Y | Y | 4795.6 | N |  | 2011-09-14 | Y | 300 | 300 | 2012-01-01 | Complete | 2011-11-02 | Y | Complete |  | 2012-01-17 | 2012-01-17 | Complete | 2012-01-17 | Complete | 2012-01-30 | Ready | 2012-02-10 | *FBO Not Required - The 911 center advised our Construction forces to utilize an existing hole that housed other cables going into the DMARC. It should be noted that this is not per industry standards and may be something Lance sees should he visit this site, but we did what the customer asked us to do. It is complete to the DMARC. - Mark McKenzie - Frontier - 1/23/12*
BB03A26 | BOONE | Madison Boone - Troop 5 State Police | FR | SP | FTX1439A24A | 1054 |  | 2012-01-13 |  | fiber and router needed | State Police | 2011-10-19 | Y | Y | 16843 | Y | 1/27/2012; 3/20/2012; 3/29/2012 | 2012-05-10 | Y | 3502 | 3502 | 2012-06-01 | Complete | 2012-06-22 | N | No Build Required |  |  | 2012-06-22 | Complete | 2012-06-22 | Complete | 2012-01-13 | Ready
BB03A27 | BOONE | Boone County Health Department | FR | TMED | FTX1436A1UK | 848 | 1ZX560410300455900 | 2011-09-22 |  | fiber and router needed | ? | 2011-10-19 | Y | Y | 16843 | N | 3/29/2012: SEE BB03A26 NOTES FOR DETAILS. | 2012-05-10 | Y | SEE BB03A26 | Included | 2012-07-01 | Complete | 2012-06-28 | N | No Build Required |  |  | 2012-06-28 | Complete | 2012-06-28 | Complete | 2011-09-22 | Ready |  | 3/29/2012: PER FTR, "revised LCR to show that one Frontier project is building to both locations for total of 3,502 feet and cost of $16,843.00." SEE BB03A26 for LCR information; this is no longer a separate LCR. Posted to SharePoint for approval on 3/29/2012
BB03A28 | BOONE | Boone Memorial Hospital | FR | TMED | FTX1436A1UT | 860 | 1ZX560410300468110 | 2011-10-25 |  | fiber and router needed | ? | 2011-11-08 | Y | Y | 4780.32 | N |  | 2012-05-10 | Y | 433 | 433 | 2012-07-01 | Complete | 2012-05-22 | Y | TBD |  |  | 2012-05-30 | Complete | 2012-05-30 | Complete | 2011-10-25 | Ready | 2012-06-08
BB03A29 | BOONE | FamilyCare Madison | RO | TMED | FTX1436A1UQ | 849 | 1ZX560410300456203 | 2011-09-20 |  | per FTR; site already has fiber- router only | ? |  | N | N/A |  |  |  |  | N/A |  | 0 |  | Complete |  |  | No Build Required |  |  |  | Complete | N/A | Complete | 2011-09-20 | Ready
BB03A30 | BOONE | Sherman Elementary Wellness Center (Hygeia Facilities Foundation, Inc.) | RO | TMED | FTX1436A1UM | 851 | 1ZX560410300456196 | 2011-07-25 |  | per FTR; site already has fiber- router only | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-07-25 | Ready | 2012-01-05
BB03A31 | BOONE | Sherman Junior/Senior High School Wellness Center (Hygeia Facilities Foundation, Inc.) | RO | TMED | FTX1436A1WB | 852 | 1ZX560410300456230 | 2011-07-25 |  | per FTR; site already has fiber- router only | ? |  | N | N/A |  |  |  |  | N/A |  | 0 |  | Complete |  |  | No Build Required |  |  |  | Complete | N/A | Complete | 2011-07-25 | Ready
BB03A32 | BOONE | Wharton Medical Center (Hygeia Facilities Foundation, Inc.) | FR | TMED | FTX1436A1R1 | 850 | 1ZX560410300456212 | 2011-07-25 |  | fiber and router needed | ? | 2011-11-08 | Y | Y | 11150.39 | N |  | 2012-05-10 | Y | 1201 | 1201 | 2012-07-01 | 2012-07-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2011-07-25 | TBD
BB03A33 | BOONE | Raleigh-Boone Medical Center (Hygeia Facilities Foundation, Inc.) | FR | TMED | FTX1436A1V4 | 853 | 1ZX560410300456221 | 2011-07-25 |  | fiber and router needed | ? | 2011-11-08 | Y | Y | 22363.68 | N |  | 2012-05-10 | Y | 2040 | 2040 | 2012-07-01 | Complete | 2012-05-30 | N | No Build Required |  |  | 2012-05-30 | Complete | 2012-05-30 | Complete | 2011-07-25 | Ready | 2012-06-08
BB04A01 | BRAXTON | Braxton County Courthouse | RO | CHOUSE | FTX1441AHZF | 591 | Delivered and Installed by Tech | 2012-08-29 |  | per FTR; site already has fiber- router only | WVNET |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-08-29 | Ready | 2012-09-14
BB04A02 | BRAXTON | Burnsville Public Library | FR | LIB | FTX1439AJY9 | 711 |  | 2011-12-16 |  | fiber and router needed | WVNET | 2011-09-07 | Y | Y | 16017.47 | N |  | 2011-09-14 | Y | 1660 | 1660 | 2012-04-01 | Complete | 2011-10-28 | N | No Build Required |  |  | 2011-11-17 | Complete | 2011-11-17 | Complete | 2011-12-16 | Ready | 2012-01-05
BB04A03 | BRAXTON | Gassaway Public Library | FR | LIB | FTX1439A14H | 799 |  | 2012-06-21 |  | fiber and router needed | WVNET | 2011-09-13 | Y | Y | 11020.8 | N |  | 2011-09-16 | Y | 876 | 876 | 2011-10-25 | Complete | 2011-10-24 | N | No Build Required |  |  | 2011-10-25 | Complete | 2011-10-25 | Complete | 2012-06-21 | Ready | 2012-08-10
BB04A04 | BRAXTON | Sutton Public Library | FR | LIB | FTX1439AJW2 | 712 |  | 2011-12-19 |  | fiber and router needed | WVNET | 2011-09-07 | Y | Y | 13401.96 | N |  | 2011-09-14 | Y | 1660 | 1660 | 2011-10-19 | Complete | 2011-10-18 | N | No Build Required |  |  | 2011-10-19 | Complete | 2011-10-19 | Complete | 2011-12-19 | Ready | 2012-01-05
BB04A05 | BRAXTON | WVOT | RO | WVOT | FTX1436A1QY | 1178 |  |  |  | per FTR; site already has fiber- router only | WVOT |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | TBD |  | Waiting on Router | N/A
BB04A06 | BRAXTON | Braxton County 9-1-1 | FR | PSAP | FTX1436AJUI | 1384 |  | 2012-01-31 |  | fiber and router needed |  | 2011-09-20 | Y | Y | 17472.06 | N |  | 2011-09-26 | Y | 1640 | 1640 | 2012-01-01 | Complete | 2011-10-28 | Y | Complete |  | 2011-12-13 | 2011-12-13 | Complete | 2011-12-13 | Complete | 2012-01-31 | Ready | 2012-02-17 | *FBO - Not required due to location completing FBO on own - 01/05/12*
BB04A07 | BRAXTON | Central Regional Jail | FR | RJAIL | FTX1436A1QX | 657 |  | 2012-03-30 |  | fiber and router needed | WVOT | 2011-09-20 | Y | Y | 10374 | N |  | 2011-09-26 | Y | 303 | 303 | 2011-10-31 | Complete | 2011-10-31 | N | No Build Required |  |  | 2011-10-31 | Complete | 2011-10-31 | Complete | 2012-03-30 | Ready | 2012-04-05
BB04A08 | BRAXTON | Sutton Braxton - Troop 3 State Police | FR | SP | FTX1439A247 | 1051 |  | 2012-01-19 |  | fiber and router needed | State Police | 2011-09-20 | Y | Y | 19696.31 | N |  | 2011-11-07 | Y | 985 | 985 | 2012-04-01 | Complete | 2012-03-02 | Y | Scheduled | 2012-04-05 |  | 2012-05-01 | Complete | 2012-05-01 | Complete | 2012-01-19 | Ready | 2012-05-04
BB04A09 | BRAXTON | Braxton County Memorial Hospital | RO | TMED | FTX1436A1ZK | 861 | 1ZX560410300468129 | 2011-12-08 |  | per FTR; site already has fiber- router only | ? |  | N | N/A |  |  |  |  | N/A |  | 0 | N/A | Complete | N/A | N | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-12-08 | Ready | 2012-04-19
BB04A10 | BRAXTON | Braxton Health Associates | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB05A01 | BROOKE | Brooke County Courthouse | FR | CHOUSE | FTX1441AHZJ | 598 | Delivered and Installed by Tech | 2012-09-06 |  | fiber and router needed | WVNET | 2011-09-30 | Y | Y | 25042.11 | Y | 2011-10-04 | 2011-12-08 | Y | 2352 | 2352 | 2012-02-01 | Complete | 2012-01-31 | N | No Build Required |  |  | 2012-01-31 | Complete | 2012-01-31 | Complete | 2012-09-06 | Ready | 2012-09-14
BB05A02 | BROOKE | BEECH BOTTOM PRIMARY | FR | K12 | FTX1442A2CM | 291 |  | 2011-10-25 |  | fiber and router needed | K-12 | 2011-09-30 | Y | Y | 22276.41 | Y | 2011-10-04 | 2011-12-08 | Y | 2696 | 2696 | 2012-02-01 | Complete | 2012-02-15 | Y | Complete | 2012-07-12 | 2012-05-17 |  | TBD |  | Complete | 2011-10-25 | TBD |  | *FBO Update - Backboard is on hold until customer does asbestos test on walls. - Rick Singer - 4/25/12*
BB05A03 | BROOKE | BROOKE HIGH SCHOOL | FR | K12 | FTX1443AK5A | 292 |  | 2011-08-12 |  | fiber and router needed | K-12 | 2011-09-30 | Y | Y | 31954 | Y | 2011-10-04 | 2011-12-08 | Y | 4560 | 4560 | 2012-02-01 | Complete | 2012-03-22 | Y | Complete | 2012-07-04 | 2012-04-30 | 2012-04-20 | Complete | 2012-04-20 | Complete | 2011-08-12 | Ready | 2012-04-27 | *FBO Update - Made an attempt to rod and replace curren conduit. That was unsuccessful therefore the crew had to complete this work by digging up the current conduit and replacing. Any further questions please refer to the Final Invoice. - 4/30/12 - Nick Patel*
BB05A04 | BROOKE | COLLIER PRIMARY SCHOOL | FR | K12 | FTX1443AK5V | 293 |  | 2011-10-27 |  | fiber and router needed | K-12 | 2011-09-30 | Y | Y | 149562.67 | Y | 2011-10-04 | 2011-12-08 | Y | 20712 | 20712 | 2012-02-01 | Complete | 2012-01-31 | Y | Complete | 2012-04-19 | 2012-03-23 | 2012-04-24 | Complete | 2012-04-24 | Complete | 2011-10-27 | Ready | 2012-04-27 | *FBO Approval - Approved by Mike Todorovich and John Dunlap - 3/5/12*
BB05A05 | BROOKE | FOLLANSBEE MIDDLE SCHOOL | FR | K12 | FTX1443AK5G | 294 |  | 2011-10-26 |  | fiber and router needed | K-12 | 2011-09-30 | Y | Y | 8155.67 | Y | 2011-10-04 | 2011-12-08 | Y | 484 | 484 | 2011-12-01 | Complete | 2011-11-14 | Y | Complete | 2012-01-27 | 2012-03-02 | 2012-03-13 | Complete | 2012-03-13 | Complete | 2011-10-26 | Ready | 2012-03-16 | *FBO Update - Revised Date of Completion to 02/29/12 - BMP Process held up completion of this job. Will receive Final invoice by 03/05/12 - 3/1/12*
BB05A06 | BROOKE | FRANKLIN PRIMARY SCHOOL | FR | K12 | FTX1443AK5F | 295 |  | 2011-10-26 |  | fiber and router needed | K-12 | 2011-09-30 | Y | Y | 33188.79 | Y | 2011-10-04 | 2011-12-08 | Y | 1112 | 1112 | 2012-02-01 | Complete | 2012-01-11 | Y | Complete | 2012-03-12 | 2012-03-02 | 2012-03-02 | Complete | 2012-03-02 | Complete | 2011-10-26 | Ready | 2012-03-21
BB05A07 | BROOKE | HOOVERSON HEIGHTS PRIMARY SCHOOL | FR | K12 | FTX1443AK6S | 296 |  | 2011-10-26 |  | fiber and router needed | K-12 | 2011-09-30 | Y | Y | 11917.8 | Y | 2011-10-04 | 2011-12-08 | Y | 938 | 938 | 2011-12-01 | Complete | 2011-11-15 | N | No Build Required |  |  | 2011-11-28 | Complete | 2011-11-28 | Complete | 2011-10-26 | Ready | 2012-01-05
BB05A08 | BROOKE | JEFFERSON PRIMARY SCHOOL | FR | K12 | FTX1442A2D8 | 297 |  | 2011-10-25 |  | fiber and router needed | K-12 | 2011-09-30 | Y | Y | 20821.23 | Y | 2011-10-04 | 2011-12-08 | Y | 2427 | 2427 | 2012-02-01 | Complete | 2012-01-19 | Y | Complete | 2012-03-19 | 2012-03-02 | 2012-03-02 | Complete | 2012-03-02 | Complete | 2011-10-25 | Ready | 2012-03-21 | *FBO Update - Revised completion date from sontractors of 2/27/2012 - 2/22/12*
BB05A09 | BROOKE | MILLSOP PRIMARY SCHOOL | FR | K12 | FTX1442AKES | 298 |  | 2011-10-27 |  | fiber and router needed | K-12 | 2011-09-30 | Y | Y | 49698.15 | Y | 10/4/2011; 11/1/2011 | 2011-12-08 | Y | 5793 | 5793 | 2012-03-01 | Complete | 2012-04-10 | Y | Complete | 2012-07-30 | 2012-08-14 | 2012-08-31 | Complete | 2012-08-31 | Complete | 2011-10-27 | Ready | 2012-09-07 | *FBO Update - The Demarc will only be able to go through the ceiling, but the other option will be through the wall and through the drop ceiling. It will shorten the span if they go to this demarc - reccommendenation is to move demarc. Will discuss with John Miller and Frontier. - Rick Singer - 4/25/12* *FBO Hold - Run fiber 1 more pole span farther and bury the fiber to get to the established Demarc. This will require 1000' of Fiber and also a re-assasment of the Environmental Impact. Gudenkauf will be going out on 5/1/12 to generate a map we can submit to the E.A Representative. Will bring up the situation to the Tiger Team on 5/1/12 - Nick Patel - 4/26/12* *FBO Hold - Pending EA Approval - Nick Patel - 7/26/12*
BB05A10 | BROOKE | WELLSBURG MIDDLE SCHOOL | FR | K12 | FTX1443AK47 | 299 |  | 2011-08-12 |  | fiber and router needed | K-12 | 2011-09-30 | Y | Y | 9970.12 | Y | 2011-10-04 | 2011-12-08 | Y | 502 | 502 | 2012-02-01 | Complete | 2012-04-10 | Y | Complete | 2012-07-16 | 2012-05-11 | 2012-05-22 | Complete | 2012-05-22 | Complete | 2011-08-12 | Ready | 2012-05-25
BB05A11 | BROOKE | WELLSBURG PRIMARY SCHOOL | FR | K12 | FTX1443A23M | 300 |  | 2011-08-12 |  | fiber and router needed | K-12 | 2011-09-30 | Y | Y | 30057.59 | Y | 2011-10-04 | 2011-12-08 | Y | 3241 | 3241 | 2012-02-01 | Complete | 2011-11-30 | Y | Complete | 2012-04-10 | 2012-03-23 | 2012-04-16 | Complete | 2012-04-16 | Complete | 2011-08-12 | Ready | 2012-04-19
BB05A12 | BROOKE | Follansbee Public Library | FR | LIB | FTX1439AJZF | 721 |  | 2012-01-20 |  | fiber and router needed | WVNET | 2011-09-30 | Y | Y | 8516.15 | Y | 2011-10-04 | 2011-12-08 | Y | 684 | 684 | 2011-12-01 | Complete | 2011-11-14 | Y | Complete | 2012-02-15 | 2012-02-02 | 2012-02-28 | Complete | 2012-02-28 | Complete | 2012-01-20 | Ready | 2012-03-02 | *FBO Revised - Revised Date of Completion to 2/2/12*
BB05A13 | BROOKE | Brooke County Public Library | FR | LIB | FTX1439AJZX | 719 |  | 2012-01-18 |  | fiber and router needed | WVNET | 2011-09-30 | Y | Y | 7832.01 | Y | 2011-10-04 | 2011-12-08 | Y | 388 | 388 | 2012-01-01 | Complete | 2011-12-01 | Y | Complete | 2012-02-13 | 2012-02-10 | 2012-02-17 | Complete | 2012-02-17 | Complete | 2012-01-18 | Ready | 2012-02-23 | *FBO Revised - Revised Date of Completion to 2/6/12*
BB05A14 | BROOKE | Mary H. Weir Public Library Brooke pt | REM | LIB |  |  |  |  | E | DUPLICATE SITE: SEE BB15A15 | WVNET |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB05A15 | BROOKE | Region 11–Brooke-Hancock Regional Planning and Development Council (Brooke, Hancock) | REM | PDEV |  |  |  |  | E | SITE REMOVED FROM BUILD/ROUTER LIST ON 12/20/2011. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | Router has be retrieved on 12/22/2011 by Donnie Patterson WVOT Tech. Shipped Router Back to WVOT via Fex Ex Tracking Number -319594315000022 - FTX1436A1QU
BB05A16 | BROOKE | Brooke County Sheriff's Department | FR | PSAP | FTX1436AJU2 | 1369 |  | 2012-01-18 |  | fiber and router needed |  | 2011-09-30 | Y | Y | 18144.59 | Y | 2011-10-04 | 2011-12-08 | Y | 2115 | 2115 | 2012-02-01 | Complete | 2012-01-31 | N | No Build Required |  |  | 2012-01-31 | Complete | 2012-01-31 | Complete | 2012-01-18 | Ready | 2012-02-02
BB05A17 | BROOKE | Wellsburg Brooke - Troop 1 State Police | FR | SP | FTX1439A26E | 1089 |  | 2011-12-19 |  | fiber and router needed | State Police | 2011-09-30 | Y | Y | 41326.67 | Y | 2011-10-04 | 2011-12-08 | Y | 5657 | 5657 | 2012-02-01 | Complete | 2012-03-13 | Y | Complete | 2012-09-28 | 2012-09-06 | 2012-09-18 | Complete | 2012-09-18 | Complete | 2011-12-19 | Ready | 2012-09-21
BB06A01 | CABELL | Cabell County Courthouse | FR | CHOUSE | FTX1441A0PL | 597 | Delivered and Installed by Tech | 2012-07-24 |  | fiber and router needed | WVNET | 2011-09-19 | Y | Y | 19092.48 | Y | 2011-09-21 | 2011-10-06 | Y | 375 | 375 | 2012-06-01 | Complete | 2011-10-23 | N | No Build Required |  |  | 2011-11-15 | Complete | 2011-11-15 | Complete | 2012-07-24 | Ready | 2012-08-10
BB06A02 | CABELL | Huntington Work Release Center | FR | CORR | FTX1443AK9R | 608 | Courier Delivery | 2012-06-26 |  | fiber and router needed | WVOT | 2011-09-19 | Y | Y | $40,763.72 ($26,666.97) | Y | 9/21/2011; 5/4/2012 | 2/24/2012; 6/8/12 | Y | 925 | 925 | 2012-05-01 | 2012-05-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2012-06-26 | TBD
BB06A03 | CABELL | Huntington Parole Office | RO | CORR | FTX1443AK98 | 609 |  | 2012-04-17 |  | per FTR; site already has fiber- router only | WVOT |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-04-17 | Ready | 2012-07-13
BB06A04 | CABELL | Robert L Shell Juv Cnt | FR | DJS | FTX1444AJ1C | 474 |  | 2012-04-25 |  | fiber and router needed | WVOT | 2011-12-07 | Y | Y | 11496.58 | N |  | 2011-12-13 | Y | 525 | 525 | 2012-06-01 | Complete | 2012-01-09 | N | No Build Required |  |  | 2012-01-09 | Complete | 2012-01-09 | Complete | 2012-04-25 | Ready | 2012-05-04
BB06A05 | CABELL | Cabell County Youth Reporting | FR | DJS | FTX1444AHKG | 475 |  |  |  | fiber and router needed | WVOT | 2011-12-07 | Y | Y | 14160.98 | N |  | 2011-12-13 | Y | 300 | 300 | 2012-06-01 | Complete | 2012-01-09 | N | No Build Required |  |  | 2012-01-09 | Complete | 2012-01-09 | TBD |  | Waiting on Router
BB06A06 | CABELL | Salt Rock Elementary School | FR | K12 | FTX1437AJJ1 | 122 |  | 2011-08-18 |  | fiber and router needed | K-12 | 2011-11-08 | Y | Y | $ 695,662.42 ($163,146.13) | Y | 2012-02-13 | 2012-05-02 | Y | 74356 | 74356 | 2012-06-01 | 2012-06-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2011-08-18 | TBD
BB06A07 | CABELL | WVIEP - BARBOURSVILLE SCHOOL | FR | K12 | FTX1437A1QY | 123 |  | 2011-08-18 |  | fiber and router needed | K-12 | 2011-10-19 | Y | Y | 63927.36 | N |  | 2012-04-09 | Y | 10045 | 10045 | 2012-06-01 | Complete | 2012-05-30 | Y | TBD |  |  |  | TBD |  | Complete | 2011-08-18 | TBD |  | FBO Hold - Pending Lance Approval*
BB06A08 | CABELL | Barboursville Public Library | FR | LIB | FTX1439AJWG | 735 |  | 2012-02-24 |  | fiber and router needed | WVNET | 2011-11-16 | Y | Y | 25243.05 | N |  | 2012-02-24 | Y | 1265 | 1265 | 2012-06-01 | Complete | 2012-03-26 | N | No Build Required |  |  | 2012-03-26 | Complete | 2012-03-26 | Complete | 2012-02-24 | Ready | 2012-03-29
BB06A09 | CABELL | Cox Landing Public Library | FR | LIB | FTX1439A16U | 733 |  | 2012-02-24 |  | fiber and router needed | WVNET | 2011-10-17 | Y | Y | 42351.74 | N |  | 2012-04-09 | Y | 2090 | 2090 | 2012-06-01 | Complete | 2012-05-11 | Y | Complete |  | 2012-06-20 |  | TBD |  | Complete | 2012-02-24 | TBD |  | *FBO Cancelled - Building will be demolished. New site will be temporarly be across the street. Barbara England - LIB Comm. - 6/19/12* *FBO Update - Building is owned by Cabell County Board of Ed. It is to be demolished to make way for a new bus garage. A temporary library will be set across the street in a trailer. Once the bus garage is completed, a new library building will be constructed next to the bus garage. I have no idea of the time line, other than they are saying "soon". Again, if you wish to leave the fiber coiled on the pole, that should be fine for now. - Cris Spradling - 7/16/12*
BB06A10 | CABELL | Salt Rock Public Library | FR | LIB | FTX1439A142 | 760 |  | 2012-03-28 |  | fiber and router needed | WVNET | 2011-09-16 | Y | Y | 19249.69 | N |  | 2011-09-26 | Y | 260 | 260 | 2012-06-01 | 2012-06-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2012-03-28 | TBD
BB06A11 | CABELL | Cabell County Public Library | FR | LIB | FTX1439A188 | 669 |  | 2012-01-12 |  | fiber and router needed | WVNET | 2011-09-19 | Y | Y | $43,120.15 ($45,760.94) | Y | 2012-05-07 | 2/24/2012; 5/10/2012; 5/24/12 | Y | 250 | 250 | 2012-06-01 | Complete | 2012-06-19 | N | No Build Required |  |  | 2012-06-19 | Complete | 2012-06-19 | Complete | 2012-01-12 | Ready | 2012-06-22
BB06A12 | CABELL | Gallaher Village Public Library | FR | LIB | FTX1439A18H | 741 |  | 2012-03-02 |  | fiber and router needed | WVNET | 2011-09-22 | Y | Y | 19377.82 | N |  | 2012-02-24 | Y | 365 | 365 | 2012-06-01 | Complete | 2012-03-30 | N | No Build Required |  |  | 2012-03-30 | Complete | 2012-03-30 | Complete | 2012-03-02 | Ready | 2012-04-05
BB06A13 | CABELL | Guyandotte Public Library | FR | LIB | FTX1439AJYH | 739 |  | 2012-09-04 |  | fiber and router needed | WVNET | 2011-07-14 | Y | Y | 33952.38 | Y | 2011-09-14 | 2012-04-09 | Y | 902 | 902 | 2012-06-01 | Complete | 2012-04-25 | N | No Build Required |  |  | 2012-04-25 | Complete | 2012-04-25 | Complete | 2012-09-04 | Ready | 2012-04-27
BB06A14 | CABELL | West Huntington Public Library | FR | LIB | FTX1439AJVP | 767 |  | 2012-03-28 |  | fiber and router needed | WVNET | 2011-11-08 | Y | Y | $ 62,154.84 ($ 44,113.50) | Y | 5/15/2012; 5/21/12 | 2012-04-09 | Y | 1185 | 1185 | 2012-06-01 | Complete | 2012-09-05 | N | No Build Required |  |  | 2012-09-05 | Complete | 2012-09-05 | Complete | 2012-03-28 | Ready | 2012-09-07
BB06A15 | CABELL | Milton Public Library | FR | LIB | FTX1439A16G | 751 |  | 2012-03-02 |  | fiber and router needed | WVNET | 2011-09-16 | Y | Y | 24982.44 | N |  | 2011-09-26 | Y | 374 | 374 | 2012-01-01 | Complete | 2011-11-30 | N | No Build Required |  |  | 2011-12-01 | Complete | 2011-12-01 | Complete | 2012-03-02 | Ready | 2012-03-08
BB06A16 | CABELL | Region 2–Planning and Development Council (Cabell, Lincoln, Logan,Mason, Mingo, Wayne) | FR | PDEV | FTX1436A1T7 | 1023 | 1ZX560410300476656 | 2011-12-14 |  | fiber and router needed | ? | 2011-09-30 | Y | Y | 14844.62 | N |  | 2011-10-06 | Y | 425 | 425 | 2011-10-31 | Complete | 2011-10-29 | N | No Build Required |  |  | 2011-10-31 | Complete | 2011-10-31 | Complete | 2011-12-14 | Ready | 2012-01-26
BB06A17 | CABELL | CCERC 9-1-1 | FR | PSAP | FTX1436AJU4 | 1379 |  | 2012-01-30 |  | fiber and router needed |  | 2011-09-16 | Y | Y | 28372.06 | N |  | 2012-04-09 | Y | 1040 | 1040 | 2012-06-01 | Complete | 2012-04-24 | N | No Build Required |  |  | 2012-04-24 | Complete | 2012-04-24 | Complete | 2012-01-30 | Ready | 2012-04-27
BB06A18 | CABELL | Western Regional Jail | FR | RJAIL | FTX1436A1TE | 655 |  | 2012-03-30 |  | fiber and router needed | WVOT | 2011-10-25 | Y | Y | 30896.77 | N |  | 2011-10-31 | Y | 1500 | 1500 | 2012-01-01 | Complete | 2011-11-30 | N | No Build Required |  |  | 2011-12-02 | Complete | 2011-12-02 | Complete | 2012-03-30 | Ready | 2012-04-05
BB06A19 | CABELL | Huntington / Cabell - Troop 5 State Police | FR | SP | FTX1439A23Z | 1045 |  | 2012-01-20 |  | fiber and router needed | State Police | 2012-01-03 | Y | Y | 159606.86 | Y | 2/1/2012; 2/16/2012 | 2012-03-15 | Y | 16864 | 16864 | 2012-07-01 | Complete | 2012-06-30 | Y | Scheduled | 2012-08-21 |  |  | TBD |  | Complete | 2012-01-20 | TBD
BB06A20 | CABELL | Cabell Huntington Hospital | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB06A21 | CABELL | Valley Health - Huntington High | FR | TMED | FTX1443A29A | 907 | 1ZX560410300485977 | 2012-02-16 |  | fiber and router needed | ? | 2011-12-07 | Y | Y | 31542.92 | N |  | 2012-02-24 | Y | 1500 | 1500 | 2012-07-01 | Complete | 2012-03-30 | N | No Build Required |  |  | 2012-03-30 | Complete | 2012-03-30 | Complete | 2012-02-16 | Ready | 2012-04-05
BB06A22 | CABELL | Valley Health - Spring Valley at Spring Valley High School | FR | TMED | FTX1436A2BF | 895 | 1ZX560410300484521 | 2012-02-16 |  | fiber and router needed | ? | 2011-11-15 | Y | Y | 21529.01 ($18,484.91) | Y | 2011-11-28 | 2011-12-08 | Y | 0 | 0 | 2012-07-01 | Complete | 2012-01-06 | N | No Build Required |  |  | 2012-01-06 | Complete | 2012-01-06 | Complete | 2012-02-16 | Ready | 2012-02-17
BB06A23 | CABELL | Valley Health Diagnostics | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB06A24 | CABELL | Valley Health - A Woman's Place | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB06A25 | CABELL | Valley Health Systems, Inc. | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB06A26 | CABELL | Valley Health - Highlawn | RO | TMED | FTX1436A1Y3 | 914 | 1ZX560410300499855 | 2012-02-29 |  | PER GIT DECISION: CAI HAS FIBER AT LOCATION; ROUTER ONLY. | ? | TBD | Y | N |  |  |  |  | N |  | TBD | 2012-07-01 | 2012-07-01 |  | N | No Build Required |  |  |  | TBD | N/A | Complete | 2012-02-29 | TBD
BB06A27 | CABELL | Valley Health - Westmoreland | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB06A28 | CABELL | Valley Health - Carl Johnson Medical Center | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB06A29 | CABELL | Valley Health - Pharmacy | FR | TMED | FTX1436A1YB | 915 | 1ZX560410300499864 | 2012-02-29 |  | fiber and router needed | ? | 2012-02-01 | Y | Y | 26776.04 | N |  | 2012-04-09 | Y | 1600 | 1600 | 2012-07-01 | 2012-07-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2012-02-29 | TBD
BB06A30 | CABELL | Valley Health - Westmoreland Apartments Senior Center | FO | TMED | [5 empty] | fiber and router needed Per POC; Denied Router - Fiber only | ? | 2011-12-13 | Y | Y | 53493.4 | N |  | 2012-04-09 | Y | 5067 | 5067 | 2012-07-01 | Complete | 2012-08-31 | Y | No Build Required |  |  |  | N/ | N/A | N/A | N/A | Ready |  | * Josh Hammonds - This location does not need a router. Please use this router for a different location that may need it wheter it is Valley Health or not. - 2/16/12* "*FBO Notified - Frontier Notified Location - 8/29/12* *FBO Update - Tom Orr went out to locatin. Did not make contact with POC prior to going on site. Expected to make contact without notification of arrival. Could not get answer back from POC - Location not estimated this trip due to Nichols Lack of communication. Nick PAtel will contact POC and inform them of the contractors coming on site and give them a number for contacting them. - Nick Patel - 9/5/12*"
BB06A31 | CABELL | Valley Health - Harmony House | FR | TMED | FTX1436A2BG | 896 | 1ZX560410300484512 | 2012-02-16 |  | fiber and router needed | ? | 2011-12-01 | Y | Y | $33,028.72 ($12,535.56) | Y | 3/1/2012; 5/4/2012 | 1/5/2012; 6/8/12 | Y | 1620 | 1620 | 2012-07-01 | Complete | 2012-08-27 | N | No Build Required |  |  | 2012-08-27 | Complete | 2012-08-27 | Complete | 2012-02-16 | Ready | 2012-08-31 | 4/3/2012: AN LCR FINAL APPROVAL NOTICE WAS SENT TO FTR (MARK) & AGENCIES ON 1/5/2012; COST AND FIBER FOOTAGE WERE NOT CHANGED, THEREFORE AN ADDITIONAL APPROVAL NOTICE WILL NOT BE SUBMITTED.
BB06A32 | CABELL | Valley Health - Youth and Pediatrics | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB06A33 | CABELL | Valley Health - Grant | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB06A34 | CABELL | Valley Health - Cabell-Midland at Cabell-Midland High School | FR | TMED | FTX1436A1Y9 | 916 | 1ZX560410300499873 | 2012-02-29 |  | fiber and router needed | ? | 2011-12-13 | Y | Y | 13389.28 | N |  | 2011-12-22 | Y | 0 | 0 | 2012-07-01 | Complete | 2012-01-06 | N | No Build Required |  |  | 2012-01-06 | Complete | 2012-01-06 | Complete | 2012-02-29 | Ready | 2012-03-02
BB07A01 | CALHOUN | Calhoun County Courthouse | FR | CHOUSE | FTX1441A0PF |  |  |  |  | fiber and router needed | WVNET | 2011-06-07 | Y | Y | 10418.68 | N |  | 2011-06-29 | Y | 1077 | 1077 | 2012-03-01 | Complete | 2012-02-24 | Y | Complete | 2012-05-16 | 2012-04-02 | 2012-04-04 | Complete | 2012-04-04 | TBD |  | Waiting on Router
BB07A02 | CALHOUN | *CALHOUN COUNTY MS/HS | FR | K12 | FTX1442AKED | 234 |  | 2011-08-05 |  | fiber and router needed | K-12 | 2011-06-07 | Y | Y | 11773.26 | Y | 2011-08-03 | 2011-09-26 | Y | 1045 | 1045 | 2012-03-01 | Complete | 2012-01-31 | N | No Build Required |  |  | 2012-02-07 | Complete | 2012-02-07 | Complete | 2011-08-05 | Ready | 2012-02-10
BB07A03 | CALHOUN | ARNOLDSBURG SCHOOL | FR | K12 | FTX1442A1TQ | 235 |  | 2011-08-05 |  | fiber and router needed | K-12 | 2011-06-07 | Y | Y | 18643 | N |  | 2011-09-26 | Y | 1783 | 1783 | 2012-03-01 | Complete | 2012-02-24 | Y | TBD |  | 2012-03-15 | 2012-04-05 | Complete | 2012-04-05 | Complete | 2011-08-05 | Ready | 2012-04-13 | *FBO Not Required - Location had fiber terminated to the Demarc when arrived on site - Gudenkauf - Trip charge will be generated. - 3/15/12 *
BB07A04 | CALHOUN | CALHOUN GILMER CAREER CTR | FR | K12 | FTX1442A1TB | 236 |  | 2011-08-05 |  | fiber and router needed | K-12 | 2011-06-07 | Y | Y | 151289.8 | N |  | 2011-09-26 | Y | 29737 | 29737 | 2012-03-01 | Complete | 2012-03-14 | N | No Build Required |  |  | 2012-03-16 | Complete | 2012-03-16 | Complete | 2011-08-05 | Ready | 2012-03-23
BB07A05 | CALHOUN | PLEASANT HILL SCHOOL | FR | K12 | FTX1442A1T4 | 237 |  | 2011-08-05 |  | fiber and router needed | K-12 | 2011-06-07 | Y | Y | 23724.6 | N |  | 2011-09-26 | Y | 1306 | 1306 | 2012-03-01 | 2012-03-01 |  | N | No Build Required |  |  | 2012-05-14 | Complete | 2012-05-14 | Complete | 2011-08-05 | Ready | 2012-05-18
BB07A06 | CALHOUN | Calhoun County Public Library | FR | LIB | FTX1439A184 | 676 |  | 2011-10-06 |  | fiber and router needed | WVNET | 2011-06-07 | Y | Y | 8387.18 | N |  | 2011-09-26 | Y | 972 | 972 | 2012-03-01 | Complete | 2012-02-24 | Y | Complete | 2012-05-11 | 2012-03-28 | 2012-04-04 | Complete | 2012-04-04 | Complete | 2011-10-06 | Ready | 2012-04-13
BB07A07 | CALHOUN | Calhoun County 9-1-1 | FR | PSAP | FTX1436AJU5 | 1377 |  | 2012-01-30 |  | fiber and router needed |  | 2011-06-07 | Y | Y | 29868.43 | N | 2011-07-14 | 2011-09-26 | Y | 2940 | 2940 | 2012-03-01 | Complete | 2012-01-31 | N | No Build Required |  |  | 2012-02-07 | Complete | 2012-02-07 | Complete | 2012-01-30 | Ready | 2012-02-10
BB07A08 | CALHOUN | Grantsville Calhoun - Troop 4 State Police | FR | SP | FTX1439A24C | 1056 |  | 2012-01-25 |  | fiber and router needed | State Police | 2011-06-07 | Y | Y | 6791.25 | N |  | 2011-07-05 | Y | 1717 | 1717 | 2011-12-01 | Complete | 2011-11-15 | Y | Complete | 2012-05-22 | 2012-03-28 | 2012-05-14 | Complete | 2012-05-14 | Complete | 2012-01-25 | Ready | 2012-05-18
BB08A01 | CLAY | Clay County Courthouse | FR | CHOUSE | FTX1441AHZH | 561 | Delivered and Installed by Tech | 2012-08-29 |  | fiber and router needed | WVNET | 2011-10-28 | Y | Y | 10849.34 | N |  | 2011-12-08 | Y | 681 | 681 | 2012-05-01 | 2012-05-01 | 51/14/12 | Y | Complete |  | 2012-07-03 |  | TBD |  | Complete | 2012-08-29 | TBD
BB08A02 | CLAY | BIG OTTER ELEMENTARY | RO | K12 | FTX1437A1PM | 143 |  | 2011-05-11 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-05-11 | Ready | 2012-01-05
BB08A03 | CLAY | CLAY COUNTY HIGH SCHOOL | RO | K12 | FTX1437A1NT | 144 |  | 2011-05-11 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-05-11 | Ready | 2012-01-05
BB08A04 | CLAY | CLAY ELEMENTARY SCHOOL | RO | K12 | FTX1437A1Q3 | 145 |  | 2011-05-11 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-05-11 | Ready | 2012-01-05
BB08A05 | CLAY | CLAY MIDDLE SCHOOL | RO | K12 | FTX1437AJHT | 146 |  | 2011-05-11 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-05-11 | Ready | 2012-01-05
BB08A06 | CLAY | H E WHITE ELEMENTARY SCHOOL | FR | K12 | FTX1437A1PW | 147 |  | 2011-05-11 |  | fiber and router needed | K-12 | 2011-04-25 | Y | Y | 9693.47 | N |  | 2012-05-10 | Y | 436 | 436 | N/A | Complete | 2012-06-28 | Y | Complete | 2012-07-25 | 2012-07-25 |  | TBD |  | Complete | 2011-05-11 | TBD
BB08A07 | CLAY | LIZEMORE ELEMENTARY SCHOOL | FR | K12 | FTX1437A1PL | 148 |  | 2011-05-11 |  | fiber and router needed | K-12 | 2011-10-28 | Y | Y | 21670.39 | N |  | 2011-12-08 | Y | 3174 | 3174 | 2012-05-01 | Complete | 2012-05-14 | Y | TBD |  |  |  | TBD |  | Complete | 2011-05-11 | TBD |  | *FBO Update - The IT Director of this site said he would care for the FBO Work - Tom Orr - 8/8/12*
BB08A08 | CLAY | Clay County Public Library | FR | LIB | FTX1439A18B | 748 |  | 2012-02-15 |  | fiber and router needed | WVNET | 2011-10-28 | Y | Y | 4797.44 | N |  | 2011-12-08 | Y | 800 | 800 | 2012-05-01 | Complete | 2012-05-14 | Y | Complete | 2012-07-11 | 2012-07-25 |  | TBD |  | Complete | 2012-02-15 | TBD
BB08A09 | CLAY | Clay County 9-1-1 | FR | PSAP | FTX1436AJU3 | 1376 |  | 2012-01-31 |  | fiber and router needed |  | 2011-10-24 | Y | Y | 5033.04 | N |  | 2011-10-31 | Y | 800 | 800 | 2012-05-01 | Complete | 2012-02-15 | Y | Complete |  | 2012-03-22 |  | TBD |  | Complete | 2012-01-31 | TBD |  | *FBO No Longer required - Aaron Morrison - The Aerial Crew Placing fiber for Frontier to this location was able to free up the blockage and place fiber in the building. No FBO is needed for this location.- 3/22/12*
BB08A10 | CLAY | Clay - Troop 4 State Police | FR | SP | FTX1439A244 | 1049 |  | 2012-01-19 |  | fiber and router needed | State Police | 2011-10-28 | Y | Y | 179902.76 | Y | 2011-11-04 | 2011-12-08 | Y | 25770 | 25770 | 2012-05-01 | Complete | 2012-09-10 | N | No Build Required |  |  | 2012-09-10 | Complete | 2012-09-10 | Complete | 2012-01-19 | Ready | 2012-09-14
BB08A11 | CLAY | Primary Care Systems, Inc. | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB08A12 | CLAY | Clay County Elementary School Wellness Center | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB08A13 | CLAY | Clay County Middle School Wellness Center | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB08A14 | CLAY | Clay County High School Wellness Center | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB08A15 | CLAY | Big Otter Clinic | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB09A01 | DODDRIDGE | Doddridge County Courthouse | FR | CHOUSE | FTX1441A0PH | 587 | Delivered and Installed by Tech | 2012-06-22 |  | fiber and router needed | WVNET | 2011-04-15 | Y | Y | 27229 | N |  | 2011-09-08 | Y | 3650 | 3650 | 2011-09-26 | Complete | 2011-09-23 | N | No Build Required |  |  | 2011-09-26 | Complete | 2011-09-26 | Complete | 2012-06-22 | Ready | 2012-08-10
BB09A02 | DODDRIDGE | DODDRIDGE COUNTY ELEMENTARY SCHOOL | RO | K12 | FTX1442A1XQ | 324 |  |  |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | TBD |  | Waiting on Router | N/A
BB09A03 | DODDRIDGE | DODDRIDGE COUNTY HIGH SCHOOL | RO | K12 | FTX1442A2CL | 325 |  | 2011-04-19 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-04-19 | Ready | 2012-01-05
BB09A04 | DODDRIDGE | DODDRIDGE COUNTY MIDDLE SCHOOL | RO | K12 | FTX1442A2SB | 326 |  | 2011-05-19 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-05-19 | Ready | 2012-01-05
BB09A05 | DODDRIDGE | WVIEP - WV INDUSTRIAL HOME FOR YOUTH (IHY) DJS | FR | K12 | FTX1442A2D1 | 327 |  | 2012-01-19 |  | fiber and router needed | K-12 | 2011-04-15 | Y | Y | 25364 | N |  | 2011-09-08 | Y | 3400 | 3400 | 2011-12-01 | Complete | 2011-11-10 | N | No Build Required |  |  | 2011-11-10 | Complete | 2011-11-10 | Complete | 2012-01-19 | Ready | 2012-02-17 | *FBO Update - 8/1/12 - Discussed issues and resolutions with Frontier and Contractors. We developed a vague stick drawing (Given to John D.) on the situation. Frontier provided me information on a Mon Power contact to begin a possible resolution on how we will be able to obtain access to the poles and be permitted to utilize them for Lashing to the Demarc.We also need to figuer out how the demarc extensions will be paid for. If these locations have already been billed we need a secondary solution of payment. - Nick Patel* *FBO Hold - WVIEP Schools Demarc Extensions Pending approval by the GIT*
BB09A06 | DODDRIDGE | Center Point Public Library | FR | LIB | FTX1439A15T |  |  |  |  | fiber and router needed | WVNET | 2011-04-15 | Y | Y | 1730.72 | N |  | 2011-05-26 | Y | 232 | 232 | 2012-02-01 | Complete | 2011-08-06 | Y | Complete | 2012-05-17 | 2012-03-28 | 2012-04-19 | Complete | 2012-04-19 | TBD |  | Waiting on Router
BB09A07 | DODDRIDGE | Doddridge County Public Library | FR | LIB | FTX1439A14G | 707 |  | 2011-12-09 |  | fiber and router needed | WVNET | 2011-04-15 | Y | Y | 2238 | N |  | 2011-05-26 | Y | 300 | 300 | 2012-02-01 | Complete | 2011-08-02 | Y | Complete | 2012-05-14 | 2012-04-02 | 2012-04-17 | Complete | 2012-04-17 | Complete | 2011-12-09 | Ready | 2012-04-19
BB09A08 | DODDRIDGE | North Central Regional Jail | FR | RJAIL | FTX1444AHKU | 647 |  |  |  | fiber and router needed | WVOT | 2011-04-15 | Y | Y | 310873.12 | N |  | 2011-09-08 | Y | 41672 | 41672 | 2012-01-01 | Complete | 2011-12-19 | N | No Build Required |  |  | 2011-12-19 | Complete | 2011-12-19 | TBD |  | Waiting on Router
BB09A09 | DODDRIDGE | West Union / Doddridge - Troop 1 State Police | FR | SP | FTX1439A25U | 1081 |  | 2011-12-27 |  | fiber and router needed | State Police | 2011-04-15 | Y | Y | 7586.82 | N |  | 2011-05-26 | Y | 1017 | 1017 | 2012-01-01 | Complete | 2011-12-19 | N | No Build Required |  |  | 2011-12-19 | Complete | 2011-12-19 | Complete | 2011-12-27 | Ready | 2012-01-26
BB10A01 | FAYETTE | Fayette County Courthouse | FR | CHOUSE | FTX1441AHZM |  |  |  |  | fiber and router needed | WVNET | 2011-10-20 | Y | Y | 11592 | N |  | 2011-10-31 | Y | 697 | 697 | 2012-01-01 | Complete | 2011-11-30 | Y | Complete | 2012-02-29 | 2012-04-30 | 2012-03-07 | Complete | 2012-03-07 | TBD |  | Waiting on Router |  | *FBO Not Required - Fayette County Courthouse employed an electrical contractor (outside of BTOP program) to perform electrical work. The pictures included in this email represent the work they performed. Apparently, they did not follow the State BMP regarding historical buildings. Nichols Construction was also handed a BTOP related FBO job at this location. Upon them conducting a site survey, they documented that the proper industry standards were not followed via the attached photographs. Please note for your files that neither Frontier Communications or Nichols Construction is responsible for this work. Thank You, Mark McKenzie. 1/26/12* * FBO is Required - the work done by the Electrician was not completed to the Dmarc and not going to be used for Fiber Pulling. FBO will Contintue 2/14/12*
BB10A02 | FAYETTE | Mt. Olive Correctional Complex | RO | CORR | FTX1443AK9Q | 610 | 1ZX560410300504142 | 2012-03-09 |  | per FTR; site already has fiber- router only | WVOT |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-03-09 | Ready | 2012-03-15
BB10A03 | FAYETTE | FAYETTE PLATEAU VOCATIONAL CENTER | FR | K12 | FTX1442A1Y7 | 214 |  | 2012-01-20 |  | fiber and router needed | K-12 | 2011-12-01 | Y | Y | 8905.68 | N |  | 2011-12-13 | Y | 450 | 450 | 2012-08-01 | Complete | 2012-02-01 | Y | TBD |  |  |  | TBD |  | Complete | 2012-01-20 | TBD |  | *FBO On Hold - Until Perry Verifies - 2/10/12* *FBO Update - Perry verified FBO is required - 2/17/12* *FBO Hold - Pending EA Review - 8/13/12*
BB10A04 | FAYETTE | MEADOW BRIDGE ELEMENTARY SCHOOL | RO | K12 | FTX1442A1TK | 215 |  | 2012-03-14 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-03-14 | Ready | 2012-04-16
BB10A05 | FAYETTE | OAK HILL ELEMENTARY SCHOOL (Closed - New School is New River ES) | RO | K12 | FTX1442AKEN | 217 |  | 2012-01-20 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-01-20 | Ready | 2012-04-16
BB10A06 | FAYETTE | OAK HILL HIGH SCHOOL | RO | K12 | FTX1442AKEL | 218 |  | 2012-01-20 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-01-20 | Ready | 2012-04-16
BB10A07 | FAYETTE | VALLEY ELEMENTARY SCHOOL | FR | K12 | FTX1442A1HT | 220 |  | 2012-03-14 |  | fiber and router needed | K-12 | 2011-10-17 | Y | Y | 26450.38 | N |  | 2012-03-29 | Y | 3059 | 3059 | 2012-08-01 | Complete | 2012-05-29 | Y | TBD |  |  |  | TBD |  | Complete | 2012-03-14 | TBD
BB10A08 | FAYETTE | WVIEP - GENE SPADARO JUVENILE CENTER DJS | FR | K12 | FTX1439AH03 | 221 |  | 2012-01-25 |  | fiber and router needed | K-12 | 2011-11-30 | Y | Y | 15565.75 | N |  | 2012-06-08 | Y | 1030 | 1030 | 2012-08-01 | 2012-08-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2012-01-25 | TBD
BB10A09 | FAYETTE | Ansted Public Library | FR | LIB | FTX1439AJVS | 683 |  | 2011-10-25 |  | fiber and router needed | WVNET | 2011-10-28 | Y | Y | 27646.28 | N |  | 2012-06-08 | Y | 2337 | 2337 | 2012-08-01 | 2012-08-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2011-10-25 | TBD
BB10A10 | FAYETTE | Fayetteville Public Library | FR | LIB | FTX1439A189 | 770 |  | 2012-04-04 |  | fiber and router needed | WVNET | 2011-10-20 | Y | Y | 11141.74 | N |  | 2011-10-31 | Y | 558 | 558 | 2012-08-01 | Complete | 2011-12-20 | N | No Build Required |  |  | 2011-12-20 | Complete | 2011-12-20 | Complete | 2012-04-04 | Ready | 2012-04-27
BB10A11 | FAYETTE | Gauley Bridge Public Library | RO | LIB | FTX1439A18G | 682 |  | 2011-10-25 |  | per FTR; site already has fiber- router only | WVNET |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-10-25 | Ready | 2012-01-05
BB10A12 | FAYETTE | Meadow Bridge Public Library | FR | LIB | FTX1439AJZK | 768 |  | 2012-04-16 |  | fiber and router needed | WVNET | 2011-10-31 | Y | Y | 22400.72 | N |  | 2012-06-08 | Y | 2121 | 2121 | 2012-08-01 | 2012-08-01 | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-04-16 | Ready | 2012-04-27
BB10A13 | FAYETTE | Montgomery Public Library | FR | LIB | FTX1439A14P | 681 |  | 2011-10-20 |  | fiber and router needed | WVNET | 2011-11-09 | Y | Y | 46268.99 | N |  | 2012-06-08 | Y | 2259 | 2259 | 2012-08-01 | 2012-08-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2011-10-20 | TBD
BB10A14 | FAYETTE | Mt. Hope Public Library | FR | LIB | FTX1439A146 | 769 |  | 2012-04-02 |  | fiber and router needed | WVNET | 2011-12-01 | Y | Y | 12693.42 | N |  | 2012-06-08 | Y | 1247 | 1247 | 2012-08-01 | 2012-08-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2012-04-02 | TBD
BB10A15 | FAYETTE | Fayette County Public Library | FR | LIB | FTX1439AJVY |  |  |  |  | fiber and router needed | WVNET | 2011-11-01 | Y | Y | 13821.77 | N |  |  | N |  | TBD | 2012-08-01 | 2012-08-01 |  | N | No Build Required |  |  |  | TBD |  | TBD |  | TBD
BB10A16 | FAYETTE | Oak Hill Public Library | FR | LIB | FTX1439A17A | 692 |  | 2011-11-18 |  | fiber and router needed | WVNET | 2011-10-31 | Y | Y | 24903.85 | N |  | 2012-06-08 | Y | 335 | 335 | 2012-08-01 | 2012-08-01 |  | N | No Build Required | 2012-05-25 |  |  | TBD |  | Complete | 2011-11-18 | TBD
BB10A17 | FAYETTE | Glen Jean Armory NG/State Side | FR | NGWV | FTX1436A1T8 | 1172 |  |  |  | fiber and router needed |  | 2011-10-17 | Y | Y | 57724.16 | N |  | 2012-06-08 | Y | 9464 | 9464 | 2012-08-01 | 2012-08-01 |  | N | No Build Required |  |  |  | TBD |  | TBD |  | TBD
BB10A18 | FAYETTE | Fayette County E-911 | FR | PSAP | FTX1436AJU6 | 1356 |  | 2012-01-31 |  | fiber and router needed |  | 2011-12-01 | Y | Y | 44652.2 | N |  | 2012-06-08 | Y | 6270 | 6270 | 2012-08-01 | 2012-08-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2012-01-31 | TBD
BB10A19 | FAYETTE | Gauley Bridge Fayette - Troop 6 State Police | FR | SP | FTX1439A24M | 1062 |  | 2012-01-04 |  | fiber and router needed | State Police | 2011-12-01 | Y | Y | 42913.48 | N |  | 2012-06-08 | Y | 2167 | 2167 | 2012-08-01 | 2012-08-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2012-01-04 | TBD
BB10A20 | FAYETTE | Oak Hill Fayette - Troop 6 State Police | FR | SP | FTX1439A24F | 1057 |  | 2011-12-15 |  | fiber and router needed | State Police | 2011-10-28 | Y | Y | 12134.7 | N |  | 2012-03-29 | Y | 1006 | 1006 | 2012-08-01 | Complete | 2012-04-30 | Y | Scheduled | 2012-05-25 |  | 2012-09-26 | Complete | 2012-09-26 | Complete | 2011-12-15 | Ready | 2012-09-28
BB10A21 | FAYETTE | Ansted Medical Clinic | FR | TMED | FTX1436A1TL | 854 | 1ZX560410300456436 | 2011-12-02 |  | fiber and router needed | ? | 2011-10-28 | Y | Y | 11724.37 | N |  | 2011-11-07 | Y | 670 | 670 | 2012-08-01 | Complete | 2012-08-07 | Y | TBD |  |  |  | TBD |  | Complete | 2011-12-02 | TBD
BB10A22 | FAYETTE | Montgomery General Hospital | RO | TMED | FTX1436A1UY | 877 | 1ZX560410300476683 | 2011-10-26 |  | per FTR; site already has fiber- router only | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-10-26 | Ready | 2012-01-05
BB10A23 | FAYETTE | NRHA Fayetteville Location | FR | TMED | FTX1436A2B9 | 898 | 1ZX560410300484496 | 2012-01-18 |  | fiber and router needed | ? | 2011-11-28 | Y | Y | 16948.75 | N |  | 2012-06-08 | Y | 1121 | 1121 | 2012-08-01 | 2012-08-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2012-01-18 | TBD
BB10A24 | FAYETTE | NRHA MHHS Wellness Center | RO | TMED | FTX1436A1UV | 926 | Courier Delivery | 2012-06-25 |  | per FTR; site already has fiber- router only | ? | TBD | Y | N |  |  |  |  | N |  | TBD |  | TBD |  |  | No Build Required |  |  |  | TBD | N/A | Complete | 2012-06-25 | TBD | 2012-07-13
BB10A25 | FAYETTE | NRHA MHE Wellness Center | FR | TMED | FTX1436AKQN | 899 | 1ZX560410300484503 | 2012-01-18 |  | fiber and router needed | ? | 2011-12-01 | Y | Y | $3358.50 ($12,688.49) | Y |  | 2012-06-08 | Y | 357 | 357 | 2012-08-01 | 2012-08-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2012-01-18 | TBD
BB10A26 | FAYETTE | NRHA OHHS Wellness Center | FR | TMED | FTX1436A2FC | 900 | 1ZX560410300484487 | 2012-01-18 |  | fiber and router needed | ? | 2011-11-30 | Y | Y | 31716.6 | N |  | 2012-06-08 | Y | 2897 | 2897 | 2012-08-01 | 2012-08-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2012-01-18 | TBD
BB10A27 | FAYETTE | NRHA CMS Wellness Center | FR | TMED | FTX1436A2BK | 901 | 1ZX560410300484478 | 2012-01-18 |  | fiber and router needed | ? | 2011-11-21 | Y | Y | 16965.5 | N |  | 2011-12-08 | Y | 347 | 347 | 2012-08-01 | Complete | 2012-04-16 | Y | TBD |  |  |  | TBD |  | Complete | 2012-01-18 | TBD
BB10A28 | FAYETTE | NRHA OES Wellness Center | RO | TMED | FTX1444AJ16 | 927 | Courier Delivery | 2012-06-25 |  | per FTR; site already has fiber- router only | ? | TBD | Y | N |  |  |  |  | N |  | TBD |  | TBD |  |  | No Build Required |  |  |  | TBD | N/A | Complete | 2012-06-25 | TBD | 2012-07-13
BB10A29 | FAYETTE | NRHA Scarbro Location | FR | TMED | FTX1436A1YA | 906 | 1ZX560410300485940 | 2012-01-18 |  | fiber and router needed | ? | 2011-12-09 | Y | Y | 89299.76 | N |  | 2012-06-08 | Y | 10562 | 10562 | 2012-08-01 | 2012-08-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2012-01-18 | TBD
BB10A30 | FAYETTE | NRHA Whipple Location | FR | TMED | FTX1436A1Y6 | 902 | 1ZX560410300484450 | 2012-01-18 |  | fiber and router needed | ? | 2011-12-02 | Y | Y | 71597.12 | N |  | 2012-06-08 | Y | 8312 | 8312 | 2012-08-01 | 2012-08-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2012-01-18 | TBD
BB11A01 | GILMER | Gilmer County Courthouse | FR | CHOUSE | FTX1441A0PM |  |  |  |  | fiber and router needed | WVNET | 2011-08-29 | Y | Y | 16726.98 | N |  | 2011-12-22 | Y | 975 | 975 | 2012-05-01 | Complete | 2012-02-16 | N | No Build Required |  |  | 2012-02-16 | Complete | 2012-02-16 | TBD |  | Waiting on Router
BB11A02 | GILMER | Morris Criminal Justice Training Center | RO | CORR | FTX1443AK9N | 611 | Courier Delivery | 2012-06-27 |  | per FTR; site already has fiber- router only | WVOT |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-06-27 | Ready | 2012-07-13
BB11A03 | GILMER | GILMER COUNTY HIGH SCHOOL | RO | K12 | FTX1442A1YS | 328 |  | 2011-06-22 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-06-22 | Ready | 2012-01-05
BB11A04 | GILMER | GLENVILLE ELEMENTARY SCHOOL | RO | K12 | FTX1442A1YX | 329 |  | 2011-11-18 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-11-18 | Ready | 2012-01-05
BB11A05 | GILMER | NORMANTOWN ELEMENTARY SCHOOL | FR | K12 | FTX1442A2C5 | 330 |  | 2011-12-01 |  | fiber and router needed | K-12 | 2011-08-29 | Y | Y | 39467.47 | N |  | 2011-12-22 | Y | 7397 | 7397 | 2012-05-01 | Complete | 2012-04-09 | N | No Build Required |  |  | 2012-04-09 | Complete | 2012-04-09 | Complete | 2011-12-01 | Ready | 2012-04-13
BB11A06 | GILMER | SAND FORK ELEMENTARY SCHOOL | FR | K12 | FTX1442A1ZG | 331 |  | 2011-11-28 |  | fiber and router needed | K-12 | 2011-08-23 | Y | Y | 17713.03 | N |  | 2011-12-22 | Y | 1401 | 1401 | 2012-05-01 | Complete | 2012-01-24 | Y | Complete |  | 2012-01-24 | 2012-01-24 | Complete | 2012-01-24 | Complete | 2011-11-28 | Ready | 2012-02-02 | *FBO Cancelled - Completed to Demarc on 01/24/12 - Mark McKenzie - 3/6/12*
BB11A07 | GILMER | TROY ELEMENTARY SCHOOL | FR | K12 | FTX1442A1XL | 332 |  | 2011-11-18 |  | fiber and router needed | K-12 | 2011-09-07 | Y | Y | 147640.28 | Y | 2011-11-07 | 2011-12-22 | Y | 19272 | 19272 | 2012-05-01 | Complete | 2012-04-26 | N | No Build Required |  |  | 2012-04-26 | Complete | 2012-04-26 | Complete | 2011-11-18 | Ready | 2012-05-04
BB11A08 | GILMER | Gilmer Public Library | FR | LIB | FTX1439A14N | 801 |  | 2012-06-27 |  | fiber and router needed | WVNET | 2011-08-23 | Y | Y | 34902 | Y | 2011-11-07 | 2011-12-22 | Y | 2384 | 2384 | 2012-05-01 | Complete | 2012-02-08 | Y | Complete | 2011-06-11 | 2012-04-20 | 2012-04-13 | Complete | 2012-04-13 | Complete | 2012-06-27 | Ready
BB11A09 | GILMER | Glenville Gilmer - Troop 3 State Police | FR | SP | FTX1439A23T | 1041 |  | 2011-12-29 |  | fiber and router needed | State Police | 2011-08-23 | Y | Y | 27781.28 | N |  | 2011-12-22 | Y | 4677 | 4677 | 2012-05-01 | Complete | 2012-02-03 | Y | Complete | 2012-06-03 | 2012-04-20 |  | TBD |  | Complete | 2011-12-29 | TBD
BB12A01 | GRANT | Grant County Courthouse | FR | CHOUSE | FTX1441A0PG |  |  |  |  | fiber and router needed | WVNET | 2011-09-29 | Y | Y | 8027 | N |  | 2011-10-06 | Y | 388 | 388 | 2012-06-01 | Complete | 2012-02-13 | N | No Build Required |  |  | 2012-02-13 | Complete | 2012-02-13 | TBD |  | Waiting on Router
BB12A02 | GRANT | DORCAS ELEMENTARY SCHOOL | FR | K12 | FTX1442AKEW | 423 |  | 2011-07-07 |  | fiber and router needed | K-12 | 2011-10-10 | Y | Y | 128445 | Y | 2011-10-17 | 2012-03-07 | Y | 21750 | 21750 | 2012-08-01 | Complete | 2012-06-13 | Y | TBD |  |  |  | TBD |  | Complete | 2011-07-07 | TBD |  | *FBO Hold - Pending EA Information from Contractors - 9/4/12*
BB12A03 | GRANT | MAYSVILLE ELEMENTARY SCHOOL | RO | K12 | FTX1443AK4G | 424 |  | 2011-07-06 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-07-06 | Ready | 2012-01-05
BB12A04 | GRANT | PETERSBURG ELEMENTARY SCHOOL | RO | K12 | FTX1443AK3V | 425 |  | 2011-07-07 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-07-07 | Ready | 2012-01-05
BB12A05 | GRANT | PETERSBURG HIGH SCHOOL | RO | K12 | FTX1443AK45 | 426 |  | 2011-07-07 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-07-07 | Ready | 2012-01-05
BB12A06 | GRANT | SOUTH BRANCH VOCATIONAL CENTER | RO | K12 | FTX1443AK4Z | 427 |  | 2011-07-07 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-07-07 | Ready | 2012-01-05
BB12A07 | GRANT | UNION EDUCATIONAL COMPLEX | FR | K12 | FTX1443AK44 | 428 |  | 2011-07-06 |  | fiber and router needed | K-12 | 2011-09-13 | Y | Y | 4273 | N |  | 2011-09-16 | Y | 465 | 465 | 2012-01-05 | Complete | 2012-01-05 | N | No Build Required |  |  | 2012-01-05 | Complete | 2012-01-05 | Complete | 2011-07-06 | Ready | 2012-01-13
BB12A08 | GRANT | Allegheny Mt. Top Public Library | FR | LIB | FTX1439AJYC | 810 |  | 2012-07-10 |  | fiber and router needed | WVNET | 2011-09-13 | Y | Y | 67512 | N |  | 2012-03-07 | Y | 8923 | 8923 | 2012-08-01 | Complete | 2012-07-23 | N | No Build Required |  |  | 2012-07-23 | Complete | 2012-07-23 | Complete | 2012-07-10 | Ready
BB12A09 | GRANT | Grant County Public Library | FR | LIB | FTX1439A15E | 823 |  | 2012-07-23 |  | fiber and router needed | WVNET | 2011-10-03 | Y | Y | 10877 | N |  | 2012-01-26 | Y | 1095 | 1095 | 2012-08-01 | Complete | 2012-02-24 | N | No Build Required |  |  | 2012-02-24 | Complete | 2012-02-24 | Complete | 2012-07-23 | Ready
BB12A10 | GRANT | Region 8–Planning and Development Council (Grant, Hampshire Hardy, Mineral, Pendleton) | FR | PDEV | FTX1436A1SG | 1022 | 1ZX560410300476674 | 2011-10-25 |  | fiber and router needed | ? | 2011-09-30 | Y | Y | 133004.65 | N |  | 2011-10-06 | Y | 15060 | 15060 | 2012-06-01 | Complete | 2012-04-27 | N | No Build Required |  |  | 2012-04-27 | Complete | 2012-04-27 | Complete | 2011-10-25 | Ready | 2012-05-04
BB12A11 | GRANT | County EOC | FR | PSAP | FTX1436AJTR | 1361 |  | 2012-02-29 |  | fiber and router needed |  | 2011-09-30 | Y | Y | 46516 | N |  | 2011-10-06 | Y | 3046 | 3046 | 2012-06-01 | Complete | 2012-02-10 | Y | Complete |  | 2012-03-09 | 2012-03-08 | Complete | 2012-03-08 | Complete | 2012-02-29 | Ready | 2012-03-21 | *FBO Not Required - Not sure who cared for the FBO work, but Frontier Construction was able to terminate this fiber to the DMARC. If Gudenkauf has not performed the work, then the customer may have, but I would stop any further action on this site. - Mark McKenzie - 3/9/12*
BB12A12 | GRANT | BCI Petersburg - Grant County State Police | FR | SP | FTX1439A26D | 1088 |  | 2011-12-15 |  | fiber and router needed | State Police | 2011-10-19 | Y | Y | 59661 | N |  | 2011-10-31 | Y | 12405 | 12405 | 2012-06-01 | Complete | 2012-06-13 | Y | TBD |  |  |  | TBD |  | Complete | 2011-12-15 | TBD |  | *FBO Hold - Pending EA Information from Contractors - 9/4/12*
BB12A13 | GRANT | Grant Memorial Hospital | FR | TMED | FTX1436A2B5 | 880 | 1ZX560410300476978 | 2011-11-30 |  | fiber and router needed | ? | 2011-10-17 | Y | Y | 38186 | Y | 2011-10-24 | 2012-03-07 | Y | 7219 | 7219 | 2012-08-01 | 2012-08-01 |  | N | No Build Required |  |  | 2012-04-19 | Complete | 2012-04-19 | Complete | 2011-11-30 | Ready
BB13A01 | GREENBRIER | Greenbrier County Courthouse | FR | CHOUSE | FTX1441AHZP |  |  |  |  | fiber and router needed | WVNET | 2011-10-28 | Y | Y | 16106.24 | N |  | 2011-11-07 | Y | 1431 | 1431 | 2012-09-01 | Complete | 2012-02-14 | Y | Complete | 2012-04-07 | 2012-06-29 | 2012-08-20 | Complete | 2012-08-20 | TBD |  | Waiting on Router
BB13A02 | GREENBRIER | Anthony Correctional Center | FR | CORR | FTX1443AKAP | 612 |  | 2012-03-21 |  | fiber and router needed | WVOT | 2011-12-01 | Y | Y | $19,067.50 ($19,542.50) | Y |  | 2011-12-08 | Y | 2565 | 2565 | 2012-09-01 | Complete | 2012-02-15 | N | No Build Required |  |  | 2012-02-13 | Complete | 2012-02-13 | Complete | 2012-03-21 | Ready | 2012-03-23
BB13A03 | GREENBRIER | Lewisburg Parole Office | FR | CORR | FTX1444AHHT | 613 | Delivered by Courier | 2012-07-25 |  | fiber and router needed | WVOT | 2011-10-28 | Y | Y | 3873.95 | N |  | 2011-11-07 | Y | 503 | 503 | 2012-09-01 | Complete | 2012-02-15 | Y | Complete |  | 2012-03-14 |  | TBD |  | Complete | 2012-07-25 | TBD |  | *FBO Not Required - Not sure who cared for the FBO work, but Frontier Construction was able to terminate this fiber to the DMARC. If Gudenkauf has not performed the work, then the customer may have, but I would stop any further action on this site. - Mark McKenzie - 3/6/12*
BB13A04 | GREENBRIER | WVIEP - ANTHONY CENTER | FR | K12 | FTX1442A1Y8 | 222 |  | 2012-01-09 |  | fiber and router needed | K-12 | 2011-12-01 | Y | Y | SEE BB13A02 | N |  | 2011-12-08 | Y | BB13A02 | Included | 2012-09-01 | Complete | 2012-02-15 | N | No Build Required |  |  | 2012-02-13 | Complete | 2012-02-13 | Complete | 2012-01-09 | Ready | 2012-04-12 | *Router Update - Router Installed - 7/13/12*
BB13A05 | GREENBRIER | WVIEP - DAVIS-STUART SCHOOL | FR | K12 | FTX1439AH0N | 223 |  | 2012-01-09 |  | fiber and router needed | K-12 | 2011-10-28 | Y | Y | 63220.25 | N |  | 2012-03-26 | Y | 14804 | 14804 | 2012-09-01 | Complete | 2012-08-10 | Y | TBD |  |  |  | TBD |  | Complete | 2012-01-09 | TBD |  | *FBO Hold - WVIEP Schools DEmarc Extensions Pending approval by the GIT*
BB13A06 | GREENBRIER | Greenbrier County Public Library | FR | LIB | FTX1439AK0L | 691 |  | 2011-11-15 |  | fiber and router needed | WVNET | 2011-10-31 | Y | Y | 106130.21 | N |  | 2012-03-26 | Y | 11128 | 11128 | 2012-09-01 | Complete | 2012-03-31 | N | No Build Required |  |  | 2012-03-31 | Complete | 2012-03-31 | Complete | 2011-11-15 | Ready | 2012-04-05
BB13A07 | GREENBRIER | Ronceverte Public Library | FR | LIB | FTX1439AJVC | 694 |  | 2011-12-05 |  | fiber and router needed | WVNET | 2011-10-17 | Y | Y | 10324.35 | N |  | 2012-03-23 | Y | 1793 | 1793 | 2012-09-01 | Complete | 2012-05-17 | Y | Complete | 2012-07-09 | 2012-07-25 | 2012-08-20 | Complete | 2012-08-20 | Complete | 2011-12-05 | Ready | 2012-08-24
BB13A08 | GREENBRIER | Quinwood Public Library closed 2003 | REM | LIB |  |  |  |  | E | SITE CLOSED IN 2003: REMOVE FROM BUILD/ROUTER LIST | WVNET |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB13A09 | GREENBRIER | Rainelle Public Library | FR | LIB | FTX1439AJVM | 778 |  | 2012-05-01 |  | fiber and router needed | WVNET | 2011-10-28 | Y | Y | 13781.79 | N |  | 2012-03-23 | Y | 2628 | 2628 | 2012-09-01 | 2012-09-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2012-05-01 | TBD
BB13A10 | GREENBRIER | White Sulphur Springs Public Library | FR | LIB | FTX1439A15Q | 695 |  | 2011-12-08 |  | fiber and router needed | WVNET | 2011-11-10 | Y | Y | 34831.39 | N |  | 2011-11-16 | Y | 4101 | 4101 | 2012-09-01 | Complete | 2012-02-25 | N | No Build Required |  |  | 2012-02-25 | Complete | 2012-02-25 | Complete | 2011-12-08 | Ready | 2012-03-02
BB13A11 | GREENBRIER | Alderson Public Library | FR | LIB | FTX1439A18A | 693 |  | 2011-12-05 |  | fiber and router needed | WVNET | 2011-10-28 | Y | Y | 14012.7 | N |  | 2012-03-23 | Y | 1364 | 1364 | 2012-09-01 | Complete | 2012-05-10 | N | No Build Required |  |  | 2012-05-10 | Complete | 2012-05-10 | Complete | 2011-12-05 | Ready | 2012-05-10
BB13A12 | GREENBRIER | Rupert Public Library | FR | LIB | FTX1439AJZJ | 777 |  | 2012-05-01 |  | fiber and router needed | WVNET | 2011-11-30 | Y | Y | 6379.9 | N |  | 2012-03-23 | Y | 815 | 815 | 2012-09-01 | 2012-09-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2012-05-01 | TBD
BB13A13 | GREENBRIER | Greenbrier County 9-1-1 | RO | PSAP | FTX1436AJU8 | 1354 |  | 2012-02-22 |  | per FTR; site already has fiber- router only |  |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-02-22 | Ready | 2012-03-08
BB13A14 | GREENBRIER | BCI - Lewisburg - Greenbrier State Police | RO | SP | FTX1439A23X |  |  |  |  | per FTR; site already has fiber- router only | State Police |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | TBD |  | Waiting on Router | N/A
BB13A15 | GREENBRIER | Lewisburg Greenbrier - Troop 6 State Police | FR | SP | FTX1439A24Y | 1067 |  | 2012-01-24 |  | fiber and router needed | State Police | 2011-10-26 | Y | Y | 20126.42 | N |  | 2012-03-23 | Y | 2271 | 2271 | 2012-09-01 | 2012-09-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2012-01-24 | TBD
BB13A16 | GREENBRIER | Rainelle Greenbrier - Troop 6 State Police | FR | SP | FTX1439A24Z | 1068 |  | 2012-01-06 |  | fiber and router needed | State Police | 2011-11-10 | Y | Y | 37652.45 | N |  | 2012-03-23 | Y | 3158 | 3158 | 2012-09-01 | Complete | 2012-09-22 | N | No Build Required |  | 2012-09-22 |  | TBD |  | Complete | 2012-01-06 | TBD
BB13A17 | GREENBRIER | Greenbrier Valley Medical Center | FR | TMED | FTX1436A2BJ | 855 | 1ZX560410300456418 | 2011-07-26 |  | fiber and router needed | ? | 2011-10-28 | Y | Y | 9847.93 | N |  | 2011-11-07 | Y | 1484 | 1484 | 2012-09-01 | Complete | 2012-02-14 | N | No Build Required |  |  | 2012-02-13 | Complete | 2012-02-13 | Complete | 2011-07-26 | Ready | 2012-02-17
BB13A18 | GREENBRIER | Osteopathic Medical School | RO | TMED | FTX1436A1XZ | 913 | 1ZX560410300497697 | 2012-02-10 |  | per FTR; site already has fiber- router only | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-02-10 | Ready | N/A
BB14A01 | HAMPSHIRE | Hampshire County Courthouse | FR | CHOUSE | FTX1441AHZQ | 588 | Delivered and Installed by Tech | 2012-07-20 |  | fiber and router needed | WVNET | 2011-05-16 | Y | Y | 8401.7 | Y | 2011-06-15 | 5/20/2011; 7/5/2011 | Y | 1045 | 1045 | 2011-11-04 | Complete | 2011-09-22 | N | No Build Required |  |  | 2011-11-04 | Complete | 2011-11-04 | Complete | 2012-07-20 | Ready | 2012-08-10
BB14A02 | HAMPSHIRE | AUGUSTA ELEMENTARY SCHOOL | FR | K12 | FTX1443A23Q | 429 |  | 2011-07-13 |  | fiber and router needed | K-12 | 2011-09-13 | Y | Y | 13302.57 | Y | 2011-09-14 | 2011-12-08 | Y | 1863 | 1863 | 2012-08-01 | Complete | 2012-02-15 | Y | Complete |  | 2012-03-26 | 2012-04-03 | Complete | 2012-04-03 | Complete | 2011-07-13 | Ready | 2012-04-05 | *FBO No Longer Required - I’ve spoken with our Engineering Department and we agree that this is something our Construction crew can handle. I will reach out to that group today and will take this off the FBO list. - Mark McKenzie - Frontier - 3/26/12
BB14A03 | HAMPSHIRE | CAPON BRIDGE ELEMENTARY SCHOOL | RO | K12 | FTX1443A23J | 430 |  | 2011-07-13 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-07-13 | Ready | 2012-01-05
BB14A04 | HAMPSHIRE | CAPON BRIDGE MIDDLE SCHOOL | RO | K12 | FTX1443A23C | 431 |  | 2011-07-13 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-07-13 | Ready | 2012-01-05
BB14A05 | HAMPSHIRE | HAMPSHIRE SENIOR HIGH SCHOOL | RO | K12 | FTX1443AK4K | 432 |  | 2011-07-12 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-07-12 | Ready | 2012-01-05
BB14A06 | HAMPSHIRE | JOHN J. CORNWELL ELEMENTARY SCHOOL | RO | K12 | FTX1443AK5Y | 433 |  | 2011-07-12 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-07-12 | Ready | 2012-01-05
BB14A07 | HAMPSHIRE | ROMNEY ELEMENTARY SCHOOL | RO | K12 | FTX1443AK5C | 434 |  | 2011-07-21 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-07-21 | Ready | 2012-01-05
BB14A08 | HAMPSHIRE | ROMNEY MIDDLE SCHOOL | RO | K12 | FTX1443AK42 | 435 |  | 2011-07-21 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-07-21 | Ready | 2012-01-05
BB14A09 | HAMPSHIRE | SLANESVILLE ELEMENTARY SCHOOL | FR | K12 | FTX1443AK3Z | 436 |  | 2011-07-21 |  | fiber and router needed | K-12 | 2011-09-13 | Y | Y | 142453.5 | Y | 2011-09-14 | 2011-12-08 | Y | 13983 | 13983 | 2012-08-01 | Complete | 2012-02-29 | N | No Build Required |  |  | 2012-02-29 | Complete | 2012-02-29 | Complete | 2011-07-21 | Ready | 2012-03-02
BB14A10 | HAMPSHIRE | SPRINGFIELD-GREEN SPRING ELEMENTARY SCH | RO | K12 | FTX1443A23X | 437 |  | 2011-07-21 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-07-21 | Ready | 2012-01-05
BB14A11 | HAMPSHIRE | WVIEP - CHICK BUCKBEE JUVENILE CENTER DJS | FR | K12 | FTX1443AK4M | 438 |  | 2011-08-18 |  | fiber and router needed | K-12 | 2011-09-15 | Y | Y | 16037.56 | N |  | 2011-09-26 | Y | 911 | 911 | 2012-06-01 | Complete | 2012-02-20 | Y | Complete | 2012-06-06 | 2012-07-02 | 2012-08-02 | Complete | 2012-08-02 | Complete | 2011-08-18 | Ready | 2012-08-10 | *FBO Hold - Pending GIT Decision - John Dunlap - 04/24/12* * FBO Update - Location Approved and contractors will move forward - Nick Patel - 6/1/12*
BB14A12 | HAMPSHIRE | WVIEP - POTOMAC CENTER | FR | K12 | FTX1443A23Y | 439 |  | 2011-07-26 |  |  | K-12 | 2011-05-16 | Y | Y | 14159 | Y | 2011-06-15 | 5/20/2011; 7/5/2011 | Y | 1820 | 1820 | 2011-11-04 | Complete | 2011-10-27 | N | No Build Required |  |  | 2011-11-04 | Complete | 2011-11-04 | Complete | 2011-07-26 | Ready | 2012-01-05
BB14A13 | HAMPSHIRE | WV SCHOOLS FOR DEAF & BLIND | FR | K12 | FTX1443AK41 | 440 |  | 2011-07-12 |  | fiber and router needed | K-12 | 2011-09-23 | Y | Y | 30409 | N |  | 2011-10-06 | Y | 1850 | 1850 | 2012-06-01 | Complete | 2012-03-28 | N | No Build Required |  |  | 2012-03-28 | Complete | 2012-03-28 | Complete | 2011-07-12 | Ready | 2012-03-29
BB14A14 | HAMPSHIRE | Capon Bridge Public Library | FR | LIB | FTX1439AJYK | 824 |  | 2012-07-18 |  | fiber and router needed | WVNET | 2011-05-16 | Y | Y | 15876.18 | Y | 2011-06-15 | 5/20/2011 (12/8/11-SEE NOTES) | Y | 2248 | 2248 | 2012-02-01 | Complete | 2012-01-19 | N | No Build Required |  |  | 2012-01-19 | Complete | 2012-01-19 | Complete | 2012-07-18 | Ready |  | **BB14A14 WAS PREVIOUSLY APPROVED ON 5/20/11; THERE WILL NOT BE AN ADDITIONAL APPROVAL NOTICE SENT AT THIS TIME.
BB14A15 | HAMPSHIRE | Hampshire County Public Library | FR | LIB | FTX1439A18J | 745 |  | 2012-02-15 |  | fiber and router needed | WVNET | 2011-09-23 | Y | Y | 17317 | N |  | 2011-10-06 | Y | 14860 | 14860 | 2012-01-01 | Complete | 2011-12-07 | N | No Build Required |  |  | 2011-12-07 | Complete | 2011-12-07 | Complete | 2012-02-15 | Ready | 2012-04-27
BB14A16 | HAMPSHIRE | Hampshire County 911 | FR | PSAP | FTX1436AJUR | 1342 |  | 2011-11-15 |  | fiber and router needed |  | 2011-09-26 | Y | Y | 71212 | N |  | 2011-10-06 | Y | 8700 | 8700 | 2012-06-01 | Complete | 2012-03-28 | N | No Build Required |  |  | 2012-03-28 | Complete | 2012-03-28 | Complete | 2011-11-15 | Ready | 2012-03-29
BB14A17 | HAMPSHIRE | Potomac Highlands Regional Jail | FR | RJAIL | FTX1436A1T6 | 656 |  |  |  | fiber and router needed | WVOT | 2011-09-23 | Y | Y | 75537 | N |  | 2011-10-06 | Y | 4840 | 4840 | 2012-02-01 | Complete | 2012-02-22 | N | No Build Required |  |  | 2012-02-22 | Complete | 2012-02-22 | TBD |  | Waiting on Router
BB14A18 | HAMPSHIRE | Romney Hampshire - Troop 2 State Police | FR | SP | FTX1439A23Y | 1044 |  | 2011-12-14 |  | fiber and router needed | State Police | 2011-05-16 | Y | Y | 32216.4 | Y | 2011-06-15 | 5/20/2011; 7/5/2011 | Y | 4840 | 4840 | 2011-11-04 | Complete | 2011-10-27 | N | No Build Required |  |  | 2011-11-04 | Complete | 2011-11-04 | Complete | 2011-12-14 | Ready | 2012-01-05
BB15A01 | HANCOCK | Hancock County Courthouse | FR | CHOUSE | FTX1441AHZR | 564 | Delivered and Installed by Tech | 2012-09-06 |  | fiber and router needed | WVNET | 2011-09-30 | Y | Y | $23507.29 ($14,425.00) | Y | 2011-10-04 | 11/22/2011; 1/5/2012 | Y | 1974 | 1974 | 2012-01-01 | Complete | 2011-12-06 | Y | Complete | 2012-04-13 | 2012-03-19 | 2012-03-22 | Complete | 2012-03-22 | Complete | 2012-09-06 | Ready | 2012-09-14 | **ON 1/4/12, WVOT RECEIVED A REVISED LCR REMOVING BB15A14 FROM ORIGINAL LCR; A SEPARATE LCR WILL BE SUBMITTED FOR THIS SITE. THE FIBER FOOTAGE REMAINED THE SAME, BUT COST WAS REVISED TO $14,425.00. THIS REVISION WAS POSTED TO SHAREPOINT ON 1/4/12. *FBO Update - Hancock County Courthouse(BB15A01) and Hancock County 911(BB15A16) are in the same location. 2 different server rooms, but for the location to get fiber it requires some on premise work. - 2/2/12*
BB15A02 | HANCOCK | Brooke/Hancock Youth Reporting Center | FR | DJS | FTX1444AHKA | 476 |  |  |  | fiber and router needed | WVOT | 2011-09-30 | Y | Y | 12317.72 | Y | 2011-10-04 | 2011-10-18 | Y | 1860 | 1860 | 2012-02-01 | Complete | 2011-10-31 | Y | Complete | 2012-01-18 | 2012-02-06 | 2012-02-27 | Complete | 2012-02-27 | TBD |  | Waiting on Router |  | *FBO Revised - Revised Date of Completion to 2/1/12*
BB15A03 | HANCOCK | ALLISON ELEMENTARY SCHOOL | FR | K12 | FTX1443A23W | 258 |  | 2011-07-25 |  | fiber and router needed | K-12 | 2011-09-30 | Y | Y | 15119.61 | Y | 2011-10-04 | 2011-11-22 | Y | 1547 | 1547 | 2012-01-01 | Complete | 2011-12-16 | Y | Complete | 2012-04-23 | 2012-03-02 | 2012-03-13 | Complete | 2012-03-13 | Complete | 2011-07-25 | Ready | 2012-03-16 | *FBO Update - Revised completion date from sontractors of 2/29/2012 - 2/22/12*
BB15A04 | HANCOCK | BROADVIEW ELEMENTARY SCHOOL | FR | K12 | FTX1442AKEK | 259 |  | 2011-07-26 |  | fiber and router needed | K-12 | 2011-09-30 | Y | Y | 30841.51 | Y | 2011-10-04 | 2011-11-22 | Y | 3595 | 3595 | 2012-02-01 | Complete | 2011-12-16 | Y | Complete | 2012-02-29 | 2012-02-21 | 2012-03-05 | Complete | 2012-03-05 | Complete | 2011-07-26 | Ready | 2012-03-21
BB15A05 | HANCOCK | JOHN D. ROCKEFELLER VOC-TECH CENTER | FR | K12 | FTX1442AKF0 | 260 |  | 2011-07-26 |  | fiber and router needed | K-12 | 2011-09-30 | Y | Y | 15716.84 | Y | 2011-10-04 | 2011-10-18 | Y | 1000 | 1000 | 2011-12-01 | Complete | 2011-11-13 | Y | Complete | 2012-01-03 | 2012-01-05 | 2012-02-09 | Complete | 2012-02-09 | Complete | 2011-07-26 | Ready | 2012-02-24
BB15A06 | HANCOCK | LIBERTY ELEMENTARY SCHOOL | FR | K12 | FTX1442A2D5 | 261 |  | 2011-07-25 |  | fiber and router needed | K-12 | 2011-09-30 | Y | Y | 28568.07 | Y | 2011-10-04 | 2011-11-22 | Y | 3330 | 3330 | 2012-02-01 | Complete | 2012-01-06 | Y | Complete | 2012-03-05 | 2012-02-09 | 2012-02-28 | Complete | 2012-02-28 | Complete | 2011-07-25 | Ready | 2012-03-02
BB15A07 | HANCOCK | NEW MANCHESTER ELEMENTARY SCHOOL | FR | K12 | FTX1442AKEX | 262 |  | 2011-07-25 |  | fiber and router needed | K-12 | 2011-09-30 | Y | Y | 18648.74 | Y | 2011-10-04 | 2011-11-22 | Y | 2857 | 2857 | 2012-02-01 | Complete | 2012-01-21 | Y | Complete | 2012-04-06 | 2012-05-17 | 2012-05-22 | Complete | 2012-05-22 | Complete | 2011-07-25 | Ready | 2012-05-25 | *FBO Hold - New Manchester Elementary School (Hancock County / BB15A07) has a unique problem. The original demarc may be on the outside of the building (Mark please confirm if this is true). So the school was told that the fiber would be terminated on the wall just inside that point. The problem is that this is a classroom. The school does not want a fiber box mounted in a classroom. Neither do I. - John Miller - 3/9/12 *FBO Hold - Update - Limited Fiber at this site to move Demarc. Will verify how much is available to work with to move into a safer location than in a classroom. Rick Singer(Gudenkauf) will update un on 3/20/12 - Nick Patel - 3/14/12* *FBO Hold Update - Rick Singer will be stopping by today. - 3/20/12* *FBO Update - Location No Longer on Hold - Rick Singer has gone out to check how much excess Fiber there was. They are able to do a Fiber pull in a custodian closet. Principal and Custodian has approved. Rick will inform John Miller of the change. Expect a larger charge on the final Invoice then what is on the estimate due to a farther distance to the Demarc and more conduit required. - Nick Patel - 3/21/12* *FBO Update - Lance Host will be going out to this location to assess the situation and report back a recommended plan of action on this site to complete the Facility Build Out. - Nick Patel - 3/27/12.* *FBO Update - Lance Host supplied us with the information required for us to complete the FBO on this site. Mark McKenzie will have to send and engineer out to extend the entrance fiber to get this job completed to the new existing Demarc. Nick Patel - 4/3/12* *Fbo Update - extra $800.00 due to extra trips required to completed job. - Nick Patel - 5/17/12*
BB15A08 | HANCOCK | OAK GLEN HIGH SCHOOL | FR | K12 | FTX1442A2C3 | 263 |  | 2011-07-25 |  | fiber and router needed | K-12 | 2011-09-30 | Y | Y | 11661.96 | Y | 10/4/2011; 10/26/2011 | 2011-11-22 | Y | 1360 | 1360 | 2012-03-01 | Complete | 2012-02-17 | Y | Complete | 2012-05-23 | 2012-03-23 | 2012-03-27 | Complete | 2012-03-27 | Complete | 2011-07-25 | Ready | 2012-03-29
BB15A09 | HANCOCK | OAK GLEN MIDDLE SCHOOL | FR | K12 | FTX1443AK57 | 264 |  | 2011-07-26 |  | fiber and router needed | K-12 | 2011-09-30 | Y | Y | 10630.04 | Y | 2011-10-04 | 10/6/11 (10/18/11-SEE NOTES) | Y | 1514 | 1514 | 2011-12-01 | Complete | 2011-11-14 | Y | Complete | 2012-01-03 | 2012-01-03 | 2012-02-07 | Complete | 2012-02-07 | Complete | 2011-07-26 | Ready | 2012-02-10 | A LCR FINAL APPROVAL NOTICE WAS SENT TO POC ON 10/6/2011; THE SAME LCR WAS APPROVED ON 10/18/2011 BY ALL PARTIES WITH NO CHANGE TO LCR. WVOT WILL NOT SEND OUT DUPLICATE FINAL APPROVAL NOTICE.
BB15A10 | HANCOCK | WEIR HIGH SCHOOL | FR | K12 | FTX1443AK6R | 265 |  | 2011-07-26 |  | fiber and router needed | K-12 | 2011-10-04 | Y | Y | 22678.07 | N |  | 2011-11-22 | Y | 3860 | 3860 | 2012-02-01 | Complete | 2012-03-16 | Y | Complete | 2012-05-10 | 2012-05-17 | 2012-05-23 | Complete | 2012-05-23 | Complete | 2011-07-26 | Ready | 2012-05-25 | *FBO On Hold - Location has only 1 LCR. 2 different Dmarcs and addresses. Will bring up issues at Tiger Team Meeting on 3/27/12. - Nick Patel - 3/24/12* *FBO Update - Per Tiger Team continue with the Current LCR no new LCR is required. - 3/27/12* *FBO Update - Final Invoice is over by $50.00 due to backboard being installed by contractor. - Nick Patel - 5/17/12*
BB15A11 | HANCOCK | WEIR MIDDLE SCHOOL | FR | K12 | FTX1442AKFG | 266 |  | 2011-07-26 |  | fiber and router needed | K-12 | 2011-10-04 | Y | Y | SEE BB15A10 | N |  | 2011-11-22 | Y | SEE BB15A10 | Included | 2012-02-01 | Complete | 2012-03-16 | Y | Complete | 2012-08-27 | 2012-09-06 | 2012-09-13 | Complete | 2012-09-13 | Complete | 2011-07-26 | Ready | 2012-05-25 | *FBO Reschedule - This site will be done separatly from the High school due to the middle school not having an existing demarc. We are pending estimate and GPS Mapping for EA Approval and Photos for visual verification. - Nick Patel - 6/2/12* *FBO Update - K12 needs this build completed due to their TCR already being submitted. They are pending our build to complete their circut and establish their new demarc. - Nick Patel - 7/16/12* *FBO EA Approved - 8/7/12* *FBO Hold - John D Requested Lance Review - 8/9/12* *FBO Update - Pending Contractor Justification of work - 8/13/12* *FBO Update - Lance Approved work - 8/23/12* *FBO Approved - 8/27/12*
BB15A12 | HANCOCK | WEIRTON HEIGHTS ELEMENTARY SCHOOL | FR | K12 | FTX1442A2CV | 267 |  | 2011-07-26 |  | fiber and router needed | K-12 | 2011-10-04 | Y | Y | 22931.67 | N |  | 2011-11-22 | Y | 2673 | 2673 | 2012-02-01 | Complete | 2012-01-19 | Y | Complete | 2012-04-16 | 2012-03-23 | 2012-06-19 | Complete | 2012-06-19 | Complete | 2011-07-26 | Ready | 2012-06-22
BB15A13 | HANCOCK | Lynn Murray Memorial Library | FR | LIB | FTX1439A171 | 720 |  | 2012-01-20 |  | fiber and router needed | WVNET | 2011-10-04 | Y | Y | 8311.09 | N |  | 2011-11-22 | Y | 1272 | 1272 | 2012-01-01 | Complete | 2011-12-07 | Y | Complete | 2012-03-07 | 2012-02-15 | 2012-02-27 | Complete | 2012-02-27 | Complete | 2012-01-20 | Ready | 2012-03-02
BB15A14 | HANCOCK | Swaney Memorial Library | FR | LIB | FTX1439AJVU | 722 |  | 2012-01-20 |  | fiber and router needed | WVNET | 2011-12-28 | Y | Y | 9083 | N | 2011-10-04 | 11/22/2011; 1/5/2012; 4/3/2012 | Y | 1352 | 1352 | 2012-01-01 | Complete | 2011-12-06 | Y | Complete | 2012-04-20 | 2012-07-25 | 2012-06-07 | Complete | 2012-06-07 | Complete | 2012-01-20 | Ready | 2012-06-08 | **ON 1/4/12, WVOT RECEIVED A REVISED LCR FOR THIS LOCATION ONLY; THIS CAI WAS ORIGINALLY ON A COMBINED LCR WITH BB15A01 & BB15A16. THIS REVISION WAS POSTED TO SHAREPOINT ON 1/4/12. ON 1/9/12, THIS LCR WAS APPROVED THROUGH GIT PROCESS AGAIN. I WILL NOTIFY MARK MCKENZIE; WVOT WILL NOT BE GENERATING ANOTHER LCR FINAL APPROVAL NOTICE.** "*FBO On HOLD - Dave Robinson(Gudenkauf), Mark, Teresa, and I have found that the Swaney Memorial Library location will require an environmental re-assessment. Per Teresa Schuller, Gudenkauf will provide a map with details of work required and gps coordinates of the build to WVOT. This will be attached to an estimate that will be forwarded to Teresa Schuller for the re-assessment to begin. After the E.A. Process is completed we will continue with the FBO business as usual.* * FBO Update - FBR and Estimate Received from Contractor and drawing of what work will be completed. Information has been forwarded to the E.A. Rep. for further analysis. - 2/16/12* *FBO Hold - Update - E.A. Re-assessment is in mapping now. - Teresa Schuller - 3/14/12* *FBO Hold - Update - Sending Gudenkauf out to location to make sure fiber is sufficient to complete the FBO work and also termination and testing. - Nick Patel - 4/3/12* FBO Hold - Update - Revised LCR was submitted today from the E.A. Office and the desk of Mike T.Final Approval from John Dunlap. - Nick Patel - 4/3/12* *FBO Update - Frontier will be going out to extend the fiber to the Dictated length on the LCR. Dave - Gudenkauf - 4/4/12* *FBO Approved - Approved by Mike T. and John Dunlap - 4/5/12* *FBO Update - Gudenkauf will now utilize a new route. The Fiber can follow the current Power line and be dropped into the basement to get to the newly established demarc. - Gudenkauf - 4/28/12*"
BB15A15 | HANCOCK | Mary H. Weir Public Library | FR | LIB | FTX1439A145 | 674 |  | 2011-09-22 |  | same as BB15A14 | WVNET | 2011-10-04 | Y | Y | 15084.34 | Y | 2011-10-31 | 2011-11-07 | Y | 1612 | 1612 | 2011-12-01 | Complete | 2011-11-12 | Y | Complete | 2012-01-26 | 2012-02-06 | 2012-02-09 | Complete | 2012-02-09 | Complete | 2011-09-22 | Ready | 2012-02-24 | *FBO Revised - Revised Date of Completion to 1/31/12*
BB15A16 | HANCOCK | Hancock County 9-1-1 | FR | PSAP | FTX1436AJUC | 1368 |  | 2012-01-18 |  | same as BB15A01 |  | 2011-09-30 | Y | Y | SEE BB15A01 | Y | 2011-10-04 | 11/22/2011; 1/5/2012 | Y | SEE BB15A01 | Included | 2012-02-01 | Complete | 2011-12-06 | Y | TBD | SEE BB15A01 | SEE BB15A01 | SEE BB15A01 |  | SEE BB15A01 | Complete | 2012-01-18 | TBD | 2012-03-22 | SEE BB15A01
BB15A17 | HANCOCK | New Cumberland / Hancock - Troop 1 State Police | FR | SP | FTX1439A26K | 1091 |  | 2011-12-19 |  | fiber and router needed | State Police | 2011-05-06 | Y | Y | 6311.16 | Y | 2011-10-04 | 2011-05-19 | Y | 846 | 846 | 2011-11-23 | Complete | 2011-09-26 | N | No Build Required |  |  | 2011-11-23 | Complete | 2011-11-23 | Complete | 2011-12-19 | Ready | 2012-01-26 | **LCR WAS LISTED ON MIKE TORDORVICH'S MEMO TO APPROVE 26 LCRs ON 4/15/2011**
BB16A01 | HARDY | Hardy County Courthouse | RO | CHOUSE | FTX1441AHZL |  |  |  |  | Hardy County Grant Overlap | WVNET |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | TBD |  | Waiting on Router | N/A
BB16A02 | HARDY | *EAST HARDY EARLY/MIDDLE & HIGH SCHOOL | RO | K12 | FTX1443A23K | 441 |  | 2011-09-02 |  | Hardy County Grant Overlap | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-09-02 | Ready | 2012-01-05 | Hardy County Grant Overlap - Router Permitted
BB16A03 | HARDY | *MOOREFIELD MIDDLE SCHOOL (Shared with board office--cannot determine actual counts) | RO | K12 | FTX1443AK4F | 442 |  | 2011-09-02 |  | Hardy County Grant Overlap | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-09-02 | Ready | 2012-01-05 | Hardy County Grant Overlap - Router Permitted
BB16A04 | HARDY | MOOREFIELD ELEMENTARY | RO | K12 | FTX1443AK5D | 443 |  | 2011-09-02 |  | Hardy County Grant Overlap | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-09-02 | Ready | 2012-01-05 | Hardy County Grant Overlap - Router Permitted
BB16A05 | HARDY | MOOREFIELD HIGH SCHOOL | RO | K12 | FTX1443A25Q | 444 |  | 2011-09-02 |  | Hardy County Grant Overlap | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-09-02 | Ready | 2012-01-05 | Hardy County Grant Overlap - Router Permitted
BB16A06 | HARDY | MOOREFIELD INTERMEDIATE | RO | K12 | FTX1443AK49 | 445 |  | 2011-09-02 |  | Hardy County Grant Overlap | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-09-02 | Ready | 2012-01-05 | Hardy County Grant Overlap - Router Permitted
BB16A07 | HARDY | Hardy County Public Library | RO | LIB | FTX1439A18N | 821 |  | 2012-07-24 |  | Hardy County Grant Overlap | WVNET |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-07-24 | Ready | 2012-08-31
BB16A08 | HARDY | East Hardy Public Library | RO | LIB | FTX1439A16V | 818 |  | 2012-07-24 |  | Hardy County Grant Overlap | WVNET |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-07-24 | Ready | 2012-08-31
BB16A09 | HARDY | Hardy County 9-1-1 | RO | PSAP | FTX1436AJTQ | 1360 |  | 2012-02-29 |  | Hardy County Grant Overlap |  |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-02-29 | Ready | 2012-03-08
BB16A10 | HARDY | Moorefield Hardy - Troop 2 State Police | RO | SP | FTX1439A26Q | 1096 |  | 2011-12-14 |  | Hardy County Grant Overlap | State Police |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-12-14 | Ready | 2012-01-05
BB16A11 | HARDY | E. A. Hawse Health Center | RO | TMED | FTX1436A2BA | 882 | 1ZX560410300479457 | 2011-12-05 |  | Hardy County Grant Overlap | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-12-05 | Ready | 2012-01-05
BB16A12 | HARDY | E. A. Hawse Health Center of Mathias | RO | TMED | FTX1436A1QQ | 883 | 1ZX560410300479484 | 2011-12-05 |  | Hardy County Grant Overlap | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-12-05 | Ready | 2012-01-05
BB16A13 | HARDY | Moorefield Middle School Health Center | RO | TMED | FTX1436A1R2 | 884 | 1ZX560410300479475 | 2011-12-05 |  | Hardy County Grant Overlap | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-12-05 | Ready | 2012-01-05
BB16A14 | HARDY | Moorefield Elementary/High School Health Center | RO | TMED | FTX1436A1TA | 885 | 1ZX560410300479466 | 2011-12-05 |  | Hardy County Grant Overlap | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-12-05 | Ready | 2012-01-05
BB16A15 | HARDY | WVU East/Michael Medical/Moorefield Renal Clinic | RO | TMED | FTX1436A1V1 | 878 | 1ZX560410300476969 | 2011-11-30 |  | Hardy County Grant Overlap | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-11-30 | Ready | 2012-01-05
BB17A01 | HARRISON | Harrison County Courthouse | FR | CHOUSE | FTX1441AHZS | 568 | Delivered and Installed by Tech | 2012-06-06 |  | fiber and router needed | WVNET | 2011-05-06 | Y | Y | 3976.18 | N |  | 2011-05-26 | Y | 533 | 533 | 2011-10-06 | Complete | 2011-10-04 | N | No Build Required |  |  | 2011-10-06 | Complete | 2011-10-06 | Complete | 2012-06-06 | Ready | 2012-08-10 | **LCR WAS LISTED ON MIKE TORDORVICH'S MEMO TO APPROVE 26 LCRs ON 4/15/2011**
BB17A02 | HARRISON | Clarksburg Parole Office | FR | CORR | FTX1444AHJN | 614 | Courier Delivery | 2012-07-10 |  | fiber and router needed | WVOT | 5/6/2011; 9/15/2011 | Y | Y | $6117.20; $11,020.80 | N |  | 2011-12-08 | Y | 800 | 800 | 2011-09-30 | Complete | 2011-09-30 | N | No Build Required |  |  | 2011-09-30 | Complete | 2011-09-30 | Complete | 2012-07-10 | Ready | 2012-08-10 | **LCR WAS LISTED ON MIKE TORDORVICH'S MEMO TO APPROVE 26 LCRs ON 4/15/2011**/**PER EMAIL FROM FTR (9/15/11), FTR WILL USE AERIAL FEED ON THIS LOCATION INSTEAD OF BURIED FIBER; COST HAS CHANGED**
BB17A03 | HARRISON | PRESSLEY RIDGE | FR | K12 | FTX1442A1TS | 333 |  | 2012-07-30 |  | fiber and router needed | K-12 | 2011-04-15 | Y | Y | 104619.04 | N |  | 2011-09-14 | Y | 14024 | 14024 | 2011-12-01 | Complete | 2011-11-10 | Y | Complete | 2012-05-10 | 2012-03-14 | 2012-04-12 | Complete | 2012-04-12 | Complete | 2012-07-30 | Ready | 2012-08-10 | *FBO Update - Revised completion date from sontractors of 3/27/2012 - 2/22/12*
BB17A04 | HARRISON | Bridgeport Public Library | FR | LIB | FTX1439AJWF | 665 |  | 2011-05-17 |  | fiber and router needed | WVNET | 2011-05-06 | Y | Y | 7452.54 | N |  | 2011-05-26 | Y | 999 | 999 | 2011-04-27 | Complete | 2011-04-27 | N | No Build Required |  |  | 2011-04-27 | Complete | 2011-04-27 | Complete | 2011-05-17 | Ready | 2012-01-05 | **LCR WAS LISTED ON MIKE TORDORVICH'S MEMO TO APPROVE 26 LCRs ON 4/15/2011**
BB17A05 | HARRISON | Clarksburg-Harrison Co. Public Library | FR | LIB | FTX1439A13V | 677 |  | 2011-10-26 |  | fiber and router needed | WVNET | 2011-05-06 | Y | Y | 9407.06 | N |  | 2011-05-26 | Y | 1261 | 1261 | 2011-10-03 | Complete | 2011-09-30 | N | No Build Required |  |  | 2011-10-03 | Complete | 2011-10-03 | Complete | 2011-10-26 | Ready | 2012-01-05 | **LCR WAS LISTED ON MIKE TORDORVICH'S MEMO TO APPROVE 26 LCRs ON 4/15/2011**
BB17A06 | HARRISON | Nutter Fort Public Library | FR | LIB | FTX1439A17F | 802 |  | 2012-06-27 |  | fiber and router needed | WVNET | 2011-05-06 | Y | Y | 10294.8 | N |  | 2011-05-26 | Y | 1380 | 1380 | 2012-02-01 | Complete | 2011-04-29 | Y | Complete | 2012-04-24 | 2012-03-02 | 2012-03-27 | Complete | 2012-03-27 | Complete | 2012-06-27 | Ready |  | **LCR WAS LISTED ON MIKE TORDORVICH'S MEMO TO APPROVE 26 LCRs ON 4/15/2011** *FBO Update - Revised completion date from sontractors of 3/6/2012 - 2/22/12*
BB17A07 | HARRISON | Lowe Public Library | FR | LIB | FTX1439A179 | 800 |  | 2012-06-27 |  | fiber and router needed | WVNET | 2011-05-06 | Y | Y | 11749.5 | N |  | 5/26/2011; 9/14/2011 | Y | 1575 | 1575 | 2012-02-01 | Complete | 2011-05-03 | Y | Complete | 2012-05-04 | 2012-03-14 | 2012-04-19 | Complete | 2012-04-19 | Complete | 2012-06-27 | Ready |  | **LCR WAS LISTED ON MIKE TORDORVICH'S MEMO TO APPROVE 26 LCRs ON 4/15/2011** *FBO Update - Revised completion date from sontractors of 3/8/2012 - 2/22/12*
BB17A08 | HARRISON | Southern Area Public Library | FR | LIB | FTX1439AJVE | 666 |  | 2011-06-08 |  | fiber and router needed | WVNET | 2011-05-06 | Y | Y | 7668.88 | N |  | 2011-05-26 | Y | 1028 | 1028 | 2011-04-28 | Complete | 2011-04-27 | N | No Build Required |  |  | 2011-04-28 | Complete | 2011-04-28 | Complete | 2011-06-08 | Ready | 2012-01-05 | **LCR WAS LISTED ON MIKE TORDORVICH'S MEMO TO APPROVE 26 LCRs ON 4/15/2011**
BB17A09 | HARRISON | Harrison/Taylor 9-1-1 | FR | PSAP | FTX1436AJTB | 1386 |  | 2012-01-30 |  | fiber and router needed |  | 2011-05-06 | Y | Y | 11839.02 | N |  | 2011-05-26 | Y | 1587 | 1587 | 2011-06-09 | Complete | 2011-05-13 | N | No Build Required |  |  | 2011-06-09 | Complete | 2011-06-09 | Complete | 2012-01-30 | Ready | 2012-02-17 | **LCR WAS LISTED ON MIKE TORDORVICH'S MEMO TO APPROVE 26 LCRs ON 4/15/2011**
BB17A10 | HARRISON | Bridgeport Harrison - Troop 1 State Police | FR | SP | FTX1439A26F | 1090 |  | 2011-12-14 |  | fiber and router needed | State Police | 2011-04-15 | Y | Y | 7646.5 | N |  | 2011-09-14 | Y | 1025 | 1025 | 2012-02-01 | Complete | 2011-12-30 | Y | Complete | 2012-05-14 | 2012-03-14 | 2012-04-12 | Complete | 2012-04-12 | Complete | 2011-12-14 | Ready | 2012-04-13
BB17A11 | HARRISON | Shinnston Harrison Troop 1 State Police | FR | SP | FTX1439A26P | 1095 |  | 2011-12-14 |  | fiber and router needed | State Police | 2011-04-15 | Y | Y | 2126.1 | N |  | 2011-09-14 | Y | 285 | 285 | 2012-03-01 | Complete | 2012-02-29 | Y | Complete | 2012-05-10 | 2012-04-30 | 2012-05-29 | Complete | 2012-05-29 | Complete | 2011-12-14 | Ready | 2012-06-08 | * FBO Notified - Contractor notified WVOT and Frontier that FBO is required at this site. Frontier confirmed the work is required and agreed to move forward with the FBO. 2/28/12*
BB17A12 | HARRISON | West Milford Health Center | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB17A13 | HARRISON | UHC (United Hospital Center) | RO | TMED | FTX1436A1TT | 876 | 1ZX560410300476665 | 2011-11-21 |  | per FTR; site already has fiber- router only | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-11-21 | Ready | 2012-01-05 | United Hospital Center 327 Medical Park Drive Bridgeport, WV 26330 (681) 342-1000
BB17A14 | HARRISON | West Virginia State Auditor's Office | FR | WVSAO | FTX1441A0N6 | 1184 |  |  |  | fiber and router needed |  | 2011-05-06 | Y | Y | 7288.42 | N |  | 2011-05-26 | Y | 977 | 977 | 2011-09-23 | Complete | 2011-09-20 | N | No Build Required |  |  | 2011-09-23 | Complete | 2011-09-23 | TBD |  | Waiting on Router |  | **LCR WAS LISTED ON MIKE TORDORVICH'S MEMO TO APPROVE 26 LCRs ON 4/15/2011**
BB18A01 | JACKSON | Jackson County Courthouse | FR | CHOUSE | FTX1441A0PP |  |  |  |  | fiber and router needed | WVNET | 2011-06-11 | Y | Y | 9926.17 | N |  | 6/29/2011; 9/14/2011 | Y | 1233 | 1233 | 2012-03-01 | Complete | 2012-02-10 | Y | Complete | 2012-06-26 | 2012-05-25 | 2012-06-19 | Complete | 2012-06-19 | TBD |  | Waiting on Router
BB18A02 | JACKSON | Ripley Parole Office | FR | CORR | FTX1444AHHK | 615 | Courier Delivery | 2012-06-26 |  | fiber and router needed | WVOT | 2011-06-07 | Y | Y | 5464.92 | N |  | 2011-06-29 | Y | 685 | 685 | 2012-02-01 | Complete | 2011-09-06 | Y | Complete | 2012-06-07 | 2012-04-16 | 2012-05-09 | Complete | 2012-05-09 | Complete | 2012-06-26 | Ready
BB18A03 | JACKSON | Ravenswood Public Library | FR | LIB | FTX1439AJV8 | 749 |  | 2012-02-27 |  | fiber and router needed | WVNET | 2011-06-09 | Y | Y | 5498.01 | N |  | 2011-06-29 | Y | 894 | 894 | 2012-02-01 | 2012-02-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2012-02-27 | TBD
BB18A04 | JACKSON | Jackson County Public Library | FR | LIB | FTX1439A168 | 671 |  | 2011-08-16 |  | fiber and router needed | WVNET | 2011-06-07 | Y | Y | 6206.38 | N |  | 2011-06-29 | Y | 914 | 914 | 2011-08-16 | Complete | 2011-08-16 | N | No Build Required |  |  | 2011-08-16 | Complete | 2011-08-16 | Complete | 2011-08-16 | Ready | 2012-01-05
BB18A05 | JACKSON | Jackson County 9-1-1 | FR | PSAP | FTX1436AJTC | 1375 |  | 1/23/2012 |  | fiber and router needed |  | 2011-06-07 | Y | Y | 5724.93 | N |  | 2011-06-29 | Y | 960 | 960 | 2012-02-01 | Complete | 2012-02-14 | Y | Complete | 2012-07-31 | 2012-06-05 | 2012-06-19 | Complete | 2012-06-19 | Complete | 1/23/2012 | Ready | 2012-06-22
BB18A06 | JACKSON | Ripley Jackson - Troop 4 State Police | FR | SP | FTX1439A24B | 1055 |  | 2012-01-24 |  | fiber and router needed | State Police | 2011-06-07 | Y | Y | 5017.47 | N |  | 2011-09-14 | Y | 526 | 526 | 2012-02-01 | Complete | 2011-10-21 | Y | Complete | 2012-06-14 | 2012-04-20 | 2012-05-07 | Complete | 2012-05-07 | Complete | 2012-01-24 | Ready | 2012-05-10
BB18A07 | JACKSON | Jackson General Hospital | RO | TMED | FTX1436A1V2 | 879 | 1ZX560410300476718 | 2011-10-26 |  | per FTR; site already has fiber- router only | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-10-26 | Ready | 2012-01-05
BB19A01 | JEFFERSON | Jefferson County Courthouse | FR | CHOUSE | FTX1441AHZT | 547 | Delivered and Installed by Tech | 2012-07-11 |  | fiber and router needed | WVNET | 2011-06-24 | Y | Y | 11190 | N |  | 2011-07-05 | Y | 1500 | 1500 | 2011-12-01 | Complete | 2011-11-18 | N | No Build Required |  |  | 2011-11-18 | Complete | 2011-11-18 | Complete | 2012-07-11 | Ready | 2012-08-10
BB19A02 | JEFFERSON | South Jefferson Public Library | FR | LIB | FTX1439A141 | 817 |  | 2012-07-18 |  | fiber and router needed | WVNET | 2011-06-24 | Y | Y | 293178 | N |  | 2011-07-05 | Y | 39300 | 39300 | 2012-03-01 | Complete | 2012-02-08 | N | No Build Required |  |  | 2012-02-08 | Complete | 2012-02-08 | Complete | 2012-07-18 | Ready
BB19A03 | JEFFERSON | Bolivar-Harpers Ferry Public Library | FR | LIB | FTX1439AK02 | 811 |  | 2012-07-18 |  | fiber and router needed | WVNET | 2011-06-24 | Y | Y | 53712 | N |  | 2011-07-05 | Y | 7200 | 7200 | 2011-11-01 | Complete | 2011-10-08 | N | No Build Required |  |  | 2011-11-01 | Complete | 2011-11-01 | Complete | 2012-07-18 | Ready | 2012-08-10
BB19A04 | JEFFERSON | Shepherdstown Public Library | FR | LIB | FTX1439A16W | 816 |  | 2012-07-18 |  | fiber and router needed | WVNET | 2011-06-24 | Y | Y | 22380 | N |  | 2011-07-05 | Y | 3000 | 3000 | 2011-10-28 | Complete | 2011-10-10 | N | No Build Required |  |  | 2011-10-28 | Complete | 2011-10-28 | Complete | 2012-07-18 | Ready | 2012-08-10
BB19A05 | JEFFERSON | Jefferson County 911 | FR | PSAP | FTX1436AJV3 | 1345 |  | 2011-11-15 |  | fiber and router needed |  | 2011-06-24 | Y | Y | 279227.8 | N |  | 2011-07-05 | Y | 37430 | 37430 | 2011-12-01 | Complete | 2011-11-18 | N | No Build Required |  |  | 2011-11-18 | Complete | 2011-11-18 | Complete | 2011-11-15 | Ready | 2012-02-02
BB19A06 | JEFFERSON | Charles Town / Jefferson - Troop 2 Command HDQ State Police | FR | SP | FTX1439A245 | 1050 |  | 2011-12-13 |  | fiber and router needed | State Police | 2011-06-24 | Y | Y | 25634 | N |  | 2011-07-05 | Y | 3400 | 3400 | 2011-12-01 | Complete | 2011-11-18 | N | No Build Required |  |  | 2011-11-18 | Complete | 2011-11-18 | Complete | 2011-12-13 | Ready | 2012-01-05
BB19A07 | JEFFERSON | WVU / UHA Clinic | FR | TMED | FTX1436A1V0 | 873 | 1ZX560410300469342 | 2011-11-14 |  | fiber and router needed | ? | 2011-06-24 | Y | Y | 11190 | N |  | 2011-07-05 | Y | 1500 | 1500 | 2011-10-24 | Complete | 2011-10-24 | N | No Build Required |  |  | 2011-10-24 | Complete | 2011-10-24 | Complete | 2011-11-14 | Ready | 2012-01-05
BB19A08 | JEFFERSON | A member of WVU Hospital System | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB19A09 | JEFFERSON | Jefferson | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB19A10 | JEFFERSON | Harpers Ferry | REM | TMED |  |  |  |  | E | DUPLICATE SITE: SEE BB19A07 | ? |  | N | N/A |  |  |  |  | N/A |  | 0 |  | Removed |  |  | Removed |  |  |  | Removed | N/A | N/A | N/A | Removed
BB20A01 | KANAWHA | Kanawha County Courthouse | RO | CHOUSE | FTX1441AHZU | 590 | Delivered and Installed by Tech | 2012-08-29 |  | per FTR; site already has fiber- router only | WVNET |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-08-29 | Ready | 2012-09-14
BB20A02 | KANAWHA | Div of Corrections Central Office | RO | CORR | FTX1443AKAQ | 616 |  | 2012-04-10 |  | per FTR; site already has fiber- router only | WVOT |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-04-10 | Ready | 2012-06-08
BB20A03 | KANAWHA | WV Correctional Industries | FR | CORR | FTX1444AHJQ | 617 |  | 2012-04-19 |  | fiber and router needed | WVOT | 2011-11-09 | Y | Y | 22532.17 | N |  | 2011-11-16 | Y | 1773 | 1773 | 2012-06-01 | Complete | 2012-05-19 | Y | Complete |  | 2012-06-25 | 2012-06-27 | Complete | 2012-06-27 | Complete | 2012-04-19 | Ready
BB20A04 | KANAWHA | Charleston Correctional Center (new location) | RO | CORR | FTX1444AHK2 | 618 | Courier Delivery | 2012-06-26 |  | per FTR; site already has fiber- router only | WVOT |  | N | N/A |  |  |  |  | N/A | 0 | 0 | 2012-06-01 | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-06-26 | Ready | 2012-07-13
BB20A05 | KANAWHA | Charleston Parole Office | FR | CORR | FTX1444AHJS | 619 | Courier Delivery | 2012-06-26 |  | fiber and router needed | WVOT | 2011-10-24 | Y | Y | 15783.49 | N |  | 2011-10-31 | Y | 680 | 680 | 2012-06-01 | Complete | 2011-11-15 | N | No Build Required |  |  | 2011-11-17 | Complete | 2011-11-17 | Complete | 2012-06-26 | Ready | 2012-08-10 | *Router Update/Delivery - Nick Patel - 6/26/12 - Router Deployed to new address - 1339 Plaza East, Charleston, WV 25301.*
BB20A06 | KANAWHA | Kanawha County Youth Reporting | FR | DJS | FTX1444AHK6 | 477 |  |  |  | fiber and router needed | WVOT | 2011-11-19 | Y | Y | 17620.07 | N |  | 2011-12-08 | Y | 1362 | 1362 | 2012-06-01 | Complete | 2012-05-19 | Y | Scheduled | 2012-07-25 |  |  | TBD |  | TBD |  | TBD
BB20A07 | KANAWHA | ALBAN ELEMENTARY SCHOOL | RO | K12 | FTX1437AJJJ | 149 |  | 2012-07-26 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-07-26 | Ready | 2012-08-10
BB20A08 | KANAWHA | ALUM CREEK ELEMENTARY SCHOOL | RO | K12 | FTX1437A1NA | 150 |  | 2012-01-27 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-01-27 | Ready | N/A
BB20A09 | KANAWHA | ANDREW HEIGHTS ELEMENTARY SCHOOL | RO | K12 | FTX1437A1N9 | 151 |  | 2011-10-11 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-10-11 | Ready | N/A
BB20A10 | KANAWHA | ANDREW JACKSON MIDDLE SCHOOL | RO | K12 | FTX1437A1Q7 | 152 |  | 2012-02-15 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-02-15 | Ready | 2012-05-18
BB20A100 | KANAWHA | (Cabin Creek Health Systems) CCHS Administration | FR | TMED | FTX1436A1V6 | 912 | 1ZX560410300485959 | 2011-12-19 |  | fiber and router needed | ? | 2011-11-27 | Y | Y | 10854.24 | N |  | 2012-06-21 | Y | 400 | 400 | 2012-07-01 | 2012-07-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2011-12-19 | TBD |  | *FBO Notified - Frontier Notified Location - 8/17/12*
BB20A101 | KANAWHA | Sissonville Health Center | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB20A102 | KANAWHA | CAMC Health Systems, Inc. | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB20A103 | KANAWHA | CAMC Women and Children's Hospital | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB20A104 | KANAWHA | FamilyCare Patrick Street | FR | TMED | FTX1436A1UP | 894 | 1ZX560410300484110 | 2011-12-12 |  | fiber and router needed | ? | 2011-11-30 | Y | Y | 7156.68 | N |  | 2012-05-10 | Y | 840 | 840 | 2012-07-01 | Complete | 2012-05-24 | Y | TBD |  |  |  | TBD |  | Complete | 2011-12-12 | TBD
BB20A105 | KANAWHA | FamilyCare HealthCenter @ Schoenbaum Family Enrichment Center | FR | TMED | FTX1443A28F | 921 |  | 2012-03-23 |  | fiber and router needed | ? | 2011-12-01 | Y | Y | 18983.4 | N |  | 2011-12-13 | Y | 1475 | 1475 | 2012-07-01 | Complete | 2012-01-27 | N | No Build Required |  |  | 2012-02-01 | Complete | 2012-02-01 | Complete | 2012-03-23 | Ready | 2012-03-23 | Primary Care will be replacing FamilyCare. If Grants are made available
BB20A106 | KANAWHA | FamilyCare Health Center | FR | TMED | FTX1436A1UR | 892 | 1ZX560410300484156 | 2011-12-12 |  | fiber and router needed | ? | 2011-11-30 | Y | Y | 15112.47 | N |  | 2011-12-19 | Y | 675 | 675 | 2012-07-01 | Complete | 2012-01-06 | Y | Complete | 2012-03-22 | 2012-07-02 | 2012-07-23 | Complete | 2012-07-23 | Complete | 2011-12-12 | Ready
BB20A107 | KANAWHA | Family Care Pennsylvania Avenue | FR | TMED | FTX1436A1TD | 893 | 1ZX560410300484129 | 2011-12-12 |  | fiber and router needed | ? | 2011-11-28 | Y | Y | 18429.39 | N |  | 2011-12-08 | Y | 1380 | 1380 | 2012-07-01 | Complete | 2012-06-06 | N | No Build Required |  |  | 2012-06-06 | Complete | 2012-06-06 | Complete | 2011-12-12 | Ready | 2012-06-08
BB20A108 | KANAWHA | HBHS dba Process Strategies, Inc. | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB20A109 | KANAWHA | HBHS dba Process Strategies, Inc. - Prestera Center | FR | TMED | FTX1443A28S | 910 | 1ZX560410300485995 | 2012-01-17 |  | fiber and router needed | ? | 2011-12-07 | Y | Y | 5307.84 | N |  | 2011-12-13 | Y | 0 | 0 | 2012-01-09 | Complete | 2012-01-09 | N | No Build Required |  |  | 2012-01-09 | Complete | 2012-01-09 | Complete | 2012-01-17 | Ready | 2012-01-20
BB20A11 | KANAWHA | ANNE BAILEY ELEMENTARY SCHOOL | RO | K12 | FTX1437AJJP | 153 |  | 2012-02-15 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-02-15 | Ready | 2012-04-16
BB20A110 | KANAWHA | Highland Hospital | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB20A111 | KANAWHA | Highland Partial Program | FR | TMED | FTX1443A28P | 920 | 1ZX560410300507989 | 2012-03-21 |  | fiber and router needed | ? | 2011-12-07 | Y | Y | 20028 | N |  | 5/10/2012; 7/13/12 | Y | 2210 | 2210 | 2012-08-29 | 2012-08-29 |  | N | No Build Required |  |  | 2012-08-30 | Complete | 2012-08-30 | Complete | 2012-03-21 | Ready | 2012-08-31 | Damon Karradine - 300 56th Street, Charleston, WV 25304
BB20A112 | KANAWHA | Women's Health Center of West Virginia | FR | TMED | FTX1436A1SC | 891 | 1ZX560410300484147 | 2011-12-22 |  | fiber and router needed | ? | 2011-11-30 | Y | Y | 12061.69 | N |  | 2012-06-21 | Y | 603 | 603 | 2012-07-01 | Complete | 2012-08-16 | Y | TBD |  |  |  | TBD |  | Complete | 2011-12-22 | TBD |  | *FBO Notified - Frontier Notified Location - 8/17/12*
BB20A113 | KANAWHA | Community Health Network of WV - Colocation Facility | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB20A114 | KANAWHA | Valley Health - Upper Kanawha | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB20A115 | KANAWHA | Valley Health - Kanawha WIC | FR | TMED | [5 empty] | fiber and router needed | ? | 2012-03-20 | Y | Y | 89448.85 | N |  |  | N |  | TBD | 2012-07-01 | 2012-07-01 |  | N | No Build Required |  |  |  | TBD |  | TBD |  | TBD
BB20A12 | KANAWHA | BELLE ELEMENTARY | RO | K12 | FTX1437AJHQ | 154 |  | 2012-02-13 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-02-13 | Ready | 2012-04-16
BB20A13 | KANAWHA | BEN FRANKLIN CAREER CENTER | RO | K12 | FTX1437A1NV | 155 |  | 2012-02-13 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-02-13 | Ready | 2012-04-16
BB20A14 | KANAWHA | BONHAM ELEMENTARY SCHOOL | REM | K12 | FTX1437AJJM | 156 |  |  | E | SITE CLOSED: REMOVE FROM BUILD/ROUTER LIST | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB20A15 | KANAWHA | BRIDGE ELEMENTARY SCHOOL | RO | K12 | FTX1437A1R2 | 157 |  | 2012-05-02 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-05-02 | Ready | 2012-05-18
BB20A16 | KANAWHA | BRIDGEVIEW ELEMENTARY SCHOOL | RO | K12 | FTX1443AK60 | 158 |  | 2012-03-22 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-03-22 | Ready | 2012-04-16
BB20A17 | KANAWHA | CARVER CAREER-TECHNICAL ED CTR | RO | K12 | FTX1443AK4A | 159 |  | 2012-07-25 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-07-25 | Ready | 2012-08-10
BB20A18 | KANAWHA | CEDAR GROVE COMMUNITY SCHOOL | RO | K12 | FTX1443A23U | 160 |  | 2012-03-27 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-03-27 | Ready | 2012-04-16
BB20A19 | KANAWHA | CENTRAL ELEMENTARY SCHOOL | RO | K12 | FTX1442A2CZ | 161 |  | 2011-12-16 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-12-16 | Ready | N/A
BB20A20 | KANAWHA | CHAMBERLAIN ELEMENTARY SCHOOL | RO | K12 | FTX1437A1PC | 162 |  | 2011-07-15 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-07-15 | Ready | 2012-04-16
BB20A21 | KANAWHA | CHANDLER ELEMENTARY SCHOOL | REM | K12 | FTX1443AK5H | 163 |  |  | E | SITE CLOSED: REMOVE FROM BUILD/ROUTER LIST | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB20A22 | KANAWHA | CHESAPEAKE ELEMENTARY SCHOOL | RO | K12 | FTX1443A23D | 164 |  | 2012-02-06 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-02-06 | Ready | N/A
BB20A23 | KANAWHA | CLENDENIN ELEMENTARY SCHOOL | RO | K12 | FTX1443AK5N | 165 |  | 2012-02-06 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-02-06 | Ready | N/A
BB20A24 | KANAWHA | CROSS LANES ELEMENTARY SCHOOL | RO | K12 | FTX1442A2DU | 166 |  | 2011-09-29 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-09-29 | Ready | N/A
BB20A25 | KANAWHA | DUNBAR INTERMEDIATE SCHOOL | RO | K12 | FTX1437A1PP | 167 |  | 2011-07-26 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-07-26 | Ready | 2012-04-16
BB20A26 | KANAWHA | DUNBAR MIDDLE SCHOOL | RO | K12 | FTX1437A1Q1 | 168 |  | 2011-07-26 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-07-26 | Ready | 2012-04-16
BB20A27 | KANAWHA | DUNBAR PRIMARY SCHOOL | RO | K12 | FTX1437AJJL | 169 |  | 2012-02-23 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-02-23 | Ready | 2012-04-16
BB20A28 | KANAWHA | DUPONT MIDDLE SCHOOL | RO | K12 | FTX1443AK4B | 170 |  | 2012-02-05 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-02-05 | Ready | N/A
BB20A29 | KANAWHA | EAST BANK MIDDLE SCHOOL | RO | K12 | FTX1443AK4Y | 171 |  | 2011-07-18 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-07-18 | Ready | 2012-04-16
BB20A30 | KANAWHA | ELK CENTER ELEMENTARY SCHOOL | RO | K12 | FTX1443AK54 | 172 |  | 2011-07-18 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-07-18 | Ready | 2012-04-16
BB20A31 | KANAWHA | ELKVIEW MIDDLE SCHOOL | RO | K12 | FTX1437A1PH | 173 |  | 2011-07-18 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-07-18 | Ready | 2012-04-16
BB20A32 | KANAWHA | FLINN ELEMENTARY | RO | K12 | FTX1437A1P4 | 174 |  | 2011-07-12 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-07-12 | Ready | 2012-01-05
BB20A33 | KANAWHA | GARNET CAREER CENTER | RO | K12 | FTX1437A1P0 | 175 |  | 2012-03-17 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-03-17 | Ready | 2012-04-16
BB20A34 | KANAWHA | GLENWOOD ELEMENTARY SCHOOL | REM | K12 | FTX1437AJHS | 176 |  |  | E | SITE CLOSED: REMOVE FROM BUILD/ROUTER LIST | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB20A35 | KANAWHA | GRANDVIEW ELEMENTRY SCHOOL | RO | K12 | FTX1437A1Q8 | 177 |  | 2011-07-15 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-07-15 | Ready | 2012-04-16
BB20A36 | KANAWHA | Hayes Middle School | RO | K12 | FTX1437A1QD | 178 |  | 2012-04-18 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-04-18 | Ready | 2012-05-18
BB20A37 | KANAWHA | HOLZ ELEMENTARY SCHOOL | RO | K12 | FTX1437A1QX | 179 |  | 2012-07-25 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-07-25 | Ready | 2012-08-10
BB20A38 | KANAWHA | Horace Mann Middle School | RO | K12 | FTX1437AJHM | 180 |  | 2011-07-15 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-07-15 | Ready | 2012-04-16
BB20A39 | KANAWHA | JOHN ADAMS MIDDLE SCHOOL | RO | K12 | FTX1438AH0V | 181 |  | 2012-02-03 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-02-03 | Ready | N/A
BB20A40 | KANAWHA | KANAWHA CITY ELEMENTARY SCHOOL | RO | K12 | FTX1437AJJ0 | 182 |  | 2011-07-15 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-07-15 | Ready | 2012-04-16
BB20A41 | KANAWHA | KANAWHA COUNTY SCHOOLS ACADEMY | RO | K12 | FTX1437A1PJ | 183 |  |  |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | TBD |  | Waiting on Router | N/A
BB20A42 | KANAWHA | KENNA ELEMENTARY SCHOOL | RO | K12 | FTX1437AJHX | 184 |  | 2011-12-09 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-12-09 | Ready | 2012-04-16
BB20A43 | KANAWHA | LAKEWOOD ELEMENTARY SCHOOL | RO | K12 | FTX1443A243 | 185 |  | 2012-02-03 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-02-03 | Ready | N/A
BB20A44 | KANAWHA | MALDEN ELEMENTARY SCHOOL | RO | K12 | FTX1437AJHZ | 186 |  | 2012-02-06 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-02-06 | Ready | N/A
BB20A45 | KANAWHA | MARMET ELEMENTARY SCHOOL | RO | K12 | FTX1437A1NQ | 187 |  | 2012-05-02 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-05-02 | Ready | 2012-05-18
BB20A46 | KANAWHA | MARY INGLES ELEMENTARY SCHOOL | RO | K12 | FTX1437AJJN | 188 |  | 2011-12-16 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-12-16 | Ready | N/A
BB20A47 | KANAWHA | Mckinley Middle School | RO | K12 | FTX1443AK58 | 189 |  | 2012-01-30 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-01-30 | Ready | N/A
BB20A48 | KANAWHA | MIDLAND TRAIL ELEMENTARY SCHOOL | RO | K12 | FTX1437A1QE | 190 |  | 2012-02-06 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-02-06 | Ready | N/A
BB20A49 | KANAWHA | MONTROSE ELEMENTARY SCHOOL | RO | K12 | FTX1437A1QT | 191 |  | 2011-07-15 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-07-15 | Ready | 2012-04-16
BB20A50 | KANAWHA | NEW SISSONVILLE MIDDLE SCHOOL | RO | K12 | FTX1437A1QL | 192 |  | 2011-07-12 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-07-12 | Ready | 2012-01-05
BB20A51 | KANAWHA | NITRO ELEMENTARY SCHOOL | RO | K12 | FTX1443AK5L | 193 |  | 2011-07-13 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-07-13 | Ready | 2012-01-05
BB20A52 | KANAWHA | OVERBROOK ELEMENTARY | RO | K12 | FTX1443AK4J | 194 |  |  |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | TBD |  | Waiting on Router | N/A
BB20A53 | KANAWHA | PIEDMONT ELEMENTARY SCHOOL (YRE) | RO | K12 | FTX1437A1N5 | 195 |  | 2012-02-06 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-02-06 | Ready | N/A
BB20A54 | KANAWHA | PINCH ELEMENTARY SCHOOL | RO | K12 | FTX1437A1R3 | 196 |  | 2012-07-25 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-07-25 | Ready | 2012-08-10
BB20A55 | KANAWHA | POINT HARMONY ELEMENTARY SCHOOL | RO | K12 | FTX1437A1PV | 197 |  | 2011-07-13 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-07-13 | Ready | 2012-01-05
BB20A56 | KANAWHA | PRATT ELEMENTARY SCHOOL | RO | K12 | FTX1443A23L | 198 |  |  |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | TBD |  | Waiting on Router | N/A
BB20A57 | KANAWHA | RICHMOND ELEMENTARY SCHOOL | RO | K12 | FTX1437A1QV | 199 |  | 2012-07-25 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-07-25 | Ready | 2012-08-10
BB20A58 | KANAWHA | J. E. Robins Elementary School | RO | K12 | FTX1437A1N7 | 200 |  | 2012-02-03 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-02-03 | Ready | N/A
BB20A59 | KANAWHA | RUFFNER ELEMENTARY SCHOOL | RO | K12 | FTX1437AJJR | 201 |  | 2012-05-02 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-05-02 | Ready | 2012-05-18
BB20A60 | KANAWHA | RUTHLAWN ELEMENTARY SCHOOL | RO | K12 | FTX1437AJHV | 202 |  | 2012-02-13 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-02-13 | Ready | 2012-04-16
BB20A61 | KANAWHA | SHARON DAWES ELEMENTARY SCHOOL | RO | K12 | FTX1443A242 | 203 |  |  |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | TBD |  | Waiting on Router | N/A
BB20A62 | KANAWHA | SHAWNEE COMMUNITY CENTER | RO | K12 | FTX1443AK3U | 204 |  |  |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | TBD |  | Waiting on Router | N/A
BB20A63 | KANAWHA | SHOALS ELEMENTARY SCHOOL | RO | K12 | FTX1443A23B | 205 |  | 2012-07-25 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-07-25 | Ready | 2012-08-10
BB20A64 | KANAWHA | SISSONVILLE ELEMENTARY SCHOOL | RO | K12 | FTX1437A1QZ | 206 |  | 2012-08-01 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-08-01 | Ready | 2012-08-10
BB20A65 | KANAWHA | South Charleston Middle School | RO | K12 | FTX1437A1NG | 207 |  |  |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | TBD |  | Waiting on Router | N/A
BB20A66 | KANAWHA | Stonewall Jackson Middle School | RO | K12 | FTX1437AJJC | 208 |  | 2012-02-07 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-02-07 | Ready | N/A
BB20A67 | KANAWHA | TYLER ALTERNATIVE MIDDLE SCHOOL | RO | K12 | FTX1437A1NZ | 209 |  | 2012-05-02 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-05-02 | Ready | 2012-05-18
BB20A68 | KANAWHA | WATTS ELEMENTARY SCHOOL | RO | K12 | FTX1437A1NL | 210 |  | 2011-07-18 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-07-18 | Ready | 2012-04-16
BB20A69 | KANAWHA | WEBERWOOD ELEMENTARY SCHOOL | RO | K12 | FTX1437A1R0 | 211 |  | 2012-03-26 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-03-26 | Ready | 2012-04-16
BB20A70 | KANAWHA | WEIMER ELEMENTARY SCHOOL | RO | K12 | FTX1437A1PY | 212 |  | 2011-12-12 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-12-12 | Ready | N/A
BB20A71 | KANAWHA | WVIEP - TIGER MORTON JUVENILE CENTER DJS | FR | K12 | FTX1437A1NM | 213 |  | 2011-06-29 |  | fiber and router needed | K-12 | 2011-10-24 | Y | Y | 10934.05 | N |  | 2011-10-31 | Y | 375 | 375 | 2011-12-01 | Complete | 2011-11-15 | N | No Build Required |  |  | 2011-11-21 | Complete | 2011-11-21 | Complete | 2011-06-29 | Ready | 2012-01-05
BB20A72 | KANAWHA | South Charleston Public Library | FR | LIB | FTX1439A181 | 831 |  | 2012-08-02 |  | fiber and router needed | WVNET | 2011-10-17 | Y | Y | 15152.34 | N |  | 2011-10-31 | Y | 1555 | 1555 | 2011-12-01 | Complete | 2011-11-18 | N | No Build Required |  |  | 2011-11-18 | Complete | 2011-11-18 | Complete | 2012-08-02 | Ready | 2012-08-10
BB20A73 | KANAWHA | Clendenin Public Library | RO | LIB | FTX1439A14E | 697 |  | 2011-12-16 |  | per FTR; site already has fiber- router only | WVNET |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-12-16 | Ready | 2012-01-05
BB20A74 | KANAWHA | Cross Lanes Public Library | RO | LIB | FTX1439AJWE | 704 |  | 2011-12-16 |  | per FTR; site already has fiber- router only | WVNET |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-12-16 | Ready | 2012-01-05
BB20A75 | KANAWHA | Dunbar Public Library | RO | LIB | FTX1439A143 | 698 |  | 2011-12-16 |  | per FTR; site already has fiber- router only | WVNET |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-12-16 | Ready | 2012-01-05
BB20A76 | KANAWHA | Elk Valley Public Library | RO | LIB | FTX1439AJY7 | 699 |  | 2011-12-16 |  | per FTR; site already has fiber- router only | WVNET |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-12-16 | Ready | 2012-01-05
BB20A77 | KANAWHA | Glasgow Public Library | RO | LIB | FTX1439AK08 | 700 |  | 2011-12-16 |  | per FTR; site already has fiber- router only | WVNET |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-12-16 | Ready | 2012-01-05
BB20A78 | KANAWHA | Kanawha County Public Library | RO | LIB | FTX1439A16Z | 696 |  | 2011-12-16 |  | per FTR; site already has fiber- router only | WVNET |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-12-16 | Ready | 2012-01-05
BB20A79 | KANAWHA | Marmet Public Library | RO | LIB | FTX1439AJWK | 701 |  | 2011-12-16 |  | per FTR; site already has fiber- router only | WVNET |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-12-16 | Ready | 2012-01-05
BB20A80 | KANAWHA | Nitro Public Library | RO | LIB | FTX1439A17G | 702 |  | 2011-12-16 |  | per FTR; site already has fiber- router only | WVNET |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-12-16 | Ready | 2012-01-05
BB20A81 | KANAWHA | Riverside Library | RO | LIB | FTX1439AJVX | 703 |  | 2011-12-16 |  | per FTR; site already has fiber- router only | WVNET |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-12-16 | Ready | 2012-01-05
BB20A82 | KANAWHA | Sissonville Public Library | RO | LIB | FTX1439A165 | 705 |  | 2011-12-16 |  | per FTR; site already has fiber- router only | WVNET |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-12-16 | Ready | 2012-01-05
BB20A83 | KANAWHA | St. Albans Public Library | RO | LIB | FTX1439AJVT | 706 |  | 2011-12-16 |  | per FTR; site already has fiber- router only | WVNET |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-12-16 | Ready | 2012-01-05
BB20A84 | KANAWHA | Alum Creek Public Library | RO | LIB | FTX1439AJWC | 737 |  | 2012-02-28 |  | per FTR; site already has fiber- router only | WVNET |  | N | N/A |  |  |  |  | N/A |  | 0 |  | Complete |  |  | No Build Required |  |  |  | Complete | N/A | Complete | 2012-02-28 | Ready
BB20A85 | KANAWHA | WV National Guard Operations Center / State | FR | NGWV | FTX1436A1SA | 1171 |  |  |  | fiber and router needed |  | 2012-04-27 | Y | Y | 553646.3 | N | 2012-05-01 |  | N |  | TBD | 2012-07-01 | 2012-07-01 |  |  | TBD |  |  |  | TBD |  | TBD |  | TBD
BB20A86 | KANAWHA | Region 3 -Regional Intergovernmental Council (Boone, Clay, Kanawha Putnam) | FR | PDEV | FTX1436A1UJ | 1028 | 1ZX560410300484138 | 2011-12-21 |  | fiber and router needed | ? | 2011-11-27 | Y | Y | 25902.42 | N |  | 2011-12-08 | Y | 2022 | 2022 | 2012-07-01 | Complete | 2012-01-30 |  | TBD |  |  | 2012-02-01 | Complete | 2012-02-01 | Complete | 2011-12-21 | Ready | 2012-02-10
BB20A87 | KANAWHA | Metro Communications | RO | PSAP | FTX1436AJU7 | 1364 |  | 1/10/2012 |  | per FTR; site already has fiber- router only |  | TBD | Y | N |  |  |  |  | N |  | TBD |  | TBD |  |  | No Build Required |  |  |  | Complete | N/A | Complete | 1/10/2012 | Ready
BB20A88 | KANAWHA | Regional Jails Central Office (WVRJA) | FR | RJAIL | FTX1444AHKD | 648 |  |  |  | fiber and router needed | WVOT | 2011-09-30 | Y | Y | 33439.9 | N |  | 10/6/2011; 5/16/12 | Y | 4012 | 4012 | 2012-06-01 | 2012-06-01 |  |  | TBD |  |  | 2012-06-13 | Complete | 2012-06-13 | TBD |  | Waiting on Router
BB20A89 | KANAWHA | Regional Jails Training Facility/Academy | REM | RJAIL | FTX1444AHKJ | 649 |  |  | E | per FTR; site already has fiber- router only; PER Tiger Team Meeting- this is a duplicate CAI (See BB11A02 Gilmer Criminal Justice Training Center) and is listed under incorrect County/Address. | WVOT |  | N | N/A |  |  |  |  | N/A |  | 0 |  | Removed |  |  | Removed |  |  |  | Removed | N/A | N/A | N/A | Removed
BB20A90 | KANAWHA | South Central Regional Jail | FR | RJAIL | FTX1436A1UX | 651 | Courier Delivery | 2012-04-06 |  | fiber and router needed | WVOT | 2011-10-17 | Y | Y | 19788.78 | N |  | 2011-10-31 | Y | 3333 | 3333 | 2012-01-01 | Complete | 2011-12-08 | N | No Build Required |  |  | 2011-12-08 | Complete | 2011-12-08 | Complete | 2012-04-06 | Ready | 2012-05-18
BB20A91 | KANAWHA | Dept Headquarters Kanawha - Troop 0 State Police | RO | SP | FTX1439A23P | 1110 |  | 2012-01-17 |  | per FTR; site already has fiber- router only | State Police |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-01-17 | Ready | 2012-01-27
BB20A92 | KANAWHA | South Charleston Kanawha - Troop 4 State Police | RO | SP | FTX1439A24Q | 1065 |  | 2012-01-19 |  | per FTR; site already has fiber- router only | State Police |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-01-19 | Ready | 2012-01-27
BB20A93 | KANAWHA | Troop 7 - Turnpike Kanawha State Police | RO | SP | FTX1439A251 | 1111 |  | 2012-01-19 |  | per FTR; site already has fiber- router only | State Police |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-01-19 | Ready | 2012-01-27
BB20A94 | KANAWHA | Academy Kanawha - Troop 0 State Police | RO | SP | FTX1439A24J | 1109 |  | 2012-01-18 |  | per FTR; site already has fiber- router only | State Police |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-01-18 | Ready | 2012-01-27
BB20A95 | KANAWHA | BCI Charleston Kanawha - Troop 8 State Police | FR | SP | FTX1439A249 | 1053 |  | 2012-01-18 |  | fiber and router needed | State Police | 2011-11-29 | Y | Y | 17083.63 | N |  | 2012-06-21 | Y | 1364 | 1364 | 2012-08-01 | Complete | 2012-09-26 | N | No Build Required |  |  | 2012-09-26 | Complete | 2012-09-26 | Complete | 2012-01-18 | Ready | 2012-09-28
BB20A96 | KANAWHA | Quincy Kanawha - Troop 4 State Police | FR | SP | FTX1439A24H | 1059 |  | 2012-01-19 |  | fiber and router needed | State Police | 2011-10-24 | Y | Y | 7785.18 | N |  | 2011-10-31 | Y | 826 | 826 | 2011-12-01 | Complete | 2011-11-17 | N | No Build Required |  |  | 2011-11-17 | Complete | 2011-11-17 | Complete | 2012-01-19 | Ready | 2012-01-26
BB20A97 | KANAWHA | Riverside High School (CCHC off site) | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB20A98 | KANAWHA | Clendenin (CCHC off site) | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB20A99 | KANAWHA | Cabin Creek Health Center | FR | TMED | FTX1443A28H | 911 | 1ZX560410300485986 | 2011-12-19 |  | fiber and router needed | ? | 2011-11-27 | Y | Y | 11698.57 | N |  | 2011-12-08 | Y | 1079 | 1079 |  | TBD |  |  | TBD |  |  |  | TBD |  | Complete | 2011-12-19 | TBD
BB21A01 | LEWIS | Lewis County Courthouse | RO | CHOUSE | FTX1441AHZG |  |  |  |  | per FTR; site already has fiber- router only | WVNET |  | N | N/A |  |  |  |  | N/A |  | 0 |  | Complete |  |  | No Build Required |  |  |  | Complete | N/A | TBD |  | Waiting on Router | N/A
BB21A02 | LEWIS | ALUM BRIDGE ELEMENTARY SCHOOL | RO | K12 | FTX1442A2CR | 334 |  | 2011-08-25 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-08-25 | Ready | 2012-01-05
BB21A03 | LEWIS | JANE LEW SCHOOL | RO | K12 | FTX1442A1TR | 335 |  | 2011-08-09 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-08-09 | Ready | 2012-01-05
BB21A04 | LEWIS | LEWIS COUNTY HIGH SCHOOL | RO | K12 | FTX1442A1YP | 336 |  | 2011-08-11 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-08-11 | Ready | 2012-01-05
BB21A05 | LEWIS | PETERSON-CENTRAL ELEMENTARY SCHOOL | RO | K12 | FTX1442A2BW | 337 |  | 2011-08-08 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-08-08 | Ready | 2012-01-05
BB21A06 | LEWIS | ROANOKE ELEMENTARY SCHOOL | FR | K12 | FTX1442AKFC | 338 |  | 2011-07-19 |  | fiber and router needed | K-12 | 2011-08-15 | Y | Y | 443617.79 | N |  | 2011-09-08 | Y | 69207 | 69207 | 2012-04-01 | 2012-04-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2011-07-19 | TBD
BB21A07 | LEWIS | ROBERT L. BLAND MIDDLE SCHOOL | RO | K12 | FTX1442A1TA | 339 |  | 2011-08-09 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-08-09 | Ready | 2012-01-05
BB21A08 | LEWIS | Louis Bennett Public Library | FR | LIB | FTX1439A14F | 805 |  | 2012-06-14 |  | fiber and router needed | WVNET | 2011-10-17 | Y | Y | 23104 | N |  | 2012-03-23 | Y | 1216 | 1216 | 2012-06-01 | 2012-06-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2012-06-14 | TBD
BB21A09 | LEWIS | Lewis-Gilmer E-911 | FR | PSAP | FTX1436AJUD | 1387 |  | 1/25/2012 |  | fiber and router needed |  | 2011-10-17 | Y | Y | 19177.69 | N |  | 2012-03-23 | Y | 1110 | 1110 | 2012-06-01 | Complete | 2012-04-25 | N | No Build Required |  |  | 2012-04-25 | Complete | 2012-04-25 | Complete | 1/25/2012 | Ready | 2012-04-27
BB21A10 | LEWIS | Weston Lewis - Troop 3 State Police | FR | SP | FTX1439A25Y | 1085 |  | 2011-12-29 |  | fiber and router needed | State Police | 2011-09-21 | Y | Y | 32291.27 | N |  | 2012-03-23 | Y | 3250 | 3250 | 2012-06-01 | 2012-06-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2011-12-29 | TBD
BB21A11 | LEWIS | Stonewall Jackson Memorial Hospital | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB22A01 | LINCOLN | Lincoln County Courthouse | FR | CHOUSE | FTX1441A0PS |  |  |  |  | fiber and router needed | WVNET | 2011-12-19 | Y | Y | 12879.87 | Y | 2012-01-04 | 2012-05-02 | Y | 550 | 550 | 2012-07-01 | 2012-07-01 |  | N | No Build Required |  |  |  | TBD |  | TBD |  | TBD
BB22A02 | LINCOLN | DUVAL PK-8 | FR | K12 | FTX1443AK5P | 100 |  | 2011-07-19 |  | fiber and router needed | K-12 | 2011-12-08 | Y | Y | 24168.72 | N |  | 2012-05-02 | Y | 1600 | 1600 | 2012-07-01 | Complete | 2012-08-20 | N | No Build Required |  |  | 2012-08-20 | Complete | 2012-08-20 | Complete | 2011-07-19 | Ready | 2012-08-24
BB22A03 | LINCOLN | GUYAN VALLEY MIDDLE | RO | K12 | FTX1443A23N | 101 |  | 2011-07-18 |  | per FTR- site has Armstrong facilities/fiber | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-07-18 | Ready | 2012-01-05
BB22A04 | LINCOLN | HAMLIN PK-8 | RO | K12 | FTX1437A1PE | 102 |  | 2011-07-19 |  | per FTR- site has Armstrong facilities/fiber | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-07-19 | Ready | 2012-01-05
BB22A05 | LINCOLN | HARTS INTERMEDIATE | RO | K12 | FTX1439AH00 | 103 |  | 2011-06-01 |  | per FTR- site has Armstrong facilities/fiber | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-06-01 | Ready | 2012-01-05
BB22A06 | LINCOLN | HARTS PRIMARY | RO | K12 | FTX1439AH0E | 104 |  | 2011-06-01 |  | per FTR- site has Armstrong facilities/fiber | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-06-01 | Ready | 2012-01-05
BB22A07 | LINCOLN | LINCOLN CO HIGH | FR | K12 | FTX1439AH19 | 105 |  | 2011-07-27 |  | fiber and router needed | K-12 | 2012-01-11 | Y | Y | 693703.42 | N |  | 5/25/2012; 6/8/12 | Y | 75283 | 75283 | 2012-07-01 | 2012-07-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2011-07-27 | TBD
BB22A08 | LINCOLN | MIDWAY ELEMENTARY SCHOOL | FR | K12 | FTX1438A2DW | 106 |  | 2011-07-19 |  | fiber and router needed | K-12 | 2011-09-07 | Y | Y | 16657.26 | Y | 2011-09-13 | 2012-05-02 | Y | 4443 | 4443 | 2012-07-01 | Complete | 2012-09-05 | Y | TBD |  |  |  | TBD |  | Complete | 2011-07-19 | TBD
BB22A09 | LINCOLN | RANGER ELEMENTARY SCHOOL | FR | K12 | FTX1438A2CD | 107 |  | 2011-07-20 |  | fiber and router needed | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | 2012-07-01 | Complete | 2012-05-17 | N | No Build Required |  |  | 2012-05-17 | Complete | 2012-05-17 | Complete | 2011-07-20 | Ready |  | *Fiber Update - Frontier Stopped Construction on this location due to Armstrong Fiber building out to this facility before Frontier could complete BTOP build. Nick Patel - 5/17/12.
BB22A10 | LINCOLN | WEST HAMLIN ELEMENTARY SCHOOL | RO | K12 | FTX1439AH0F | 108 |  | 2011-07-19 |  | per FTR- site has Armstrong facilities/fiber | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-07-19 | Ready | 2012-01-05
BB22A11 | LINCOLN | Hamlin-Lincoln County Public Library | FR | LIB | FTX1439AK0A | 754 |  | 2012-03-15 |  | fiber and router needed | WVNET | 2011-12-19 | Y | Y | 6463.04 | N |  | 2012-05-02 | Y | 417 | 417 | 2012-07-01 | 2012-07-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2012-03-15 | TBD
BB22A12 | LINCOLN | Branchland Outpost Library | FR | LIB | FTX1439AJZZ | 738 |  | 2012-03-15 |  | fiber and router needed | WVNET | 2012-01-17 | Y | Y | 42238.86 | N |  | 2012-05-02 | Y | 5420 | 5420 | 2012-07-01 | Complete | 2012-09-18 | Y | TBD |  |  |  | TBD |  | Complete | 2012-03-15 | TBD
BB22A13 | LINCOLN | Lincoln County 9-1-1 | FR | PSAP | FTX1436A1RC | 1363 |  | 11/10/2012 |  | fiber and router needed |  | 2011-12-19 | Y | Y | 99517.17 | N |  | 2012-06-08 | Y | 4815 | 4815 | 2012-07-01 | 2012-07-01 |  | N | No Build Required |  |  |  | TBD |  | TBD | 11/10/2012 | TBD
BB22A14 | LINCOLN | Hamlin Lincoln - Troop 5 State Police | FR | SP | FTX1439A24L | 1061 |  | 2012-01-20 |  | fiber and router needed | State Police | 2011-12-19 | Y | Y | 5580.22 | N |  | 3/15/2012; 5/2/2012 | Y | 220 | 220 | 2012-07-01 | 2012-07-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2012-01-20 | TBD
BB22A15 | LINCOLN | Guyan Valley Wellness Center | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB22A16 | LINCOLN | Duvall Middle School Health Center | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB22A17 | LINCOLN | Lincoln Primary Care Center | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB22A18 | LINCOLN | LCHS Panther Center for Health | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB22A19 | LINCOLN | West Hamlin Elementary Wellness Center | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB22A20 | LINCOLN | Valley Health - Harts/Robert C. Byrd Center | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB23A01 | LOGAN | Logan County Courthouse | FR | CHOUSE | FTX1441AJ00 | 562 | Delivered and Installed by Tech | 2012-08-21 |  | fiber and router needed | WVNET | 2011-12-01 | Y | Y | 7862.2 | N |  | 2011-12-13 | Y | 420 | 420 | 2012-08-01 | Complete | 2012-01-11 | N | No Build Required |  |  | 2012-01-11 | Complete | 2012-01-11 | Complete | 2012-08-21 | Ready | 2012-09-14
BB23A02 | LOGAN | Logan Parole Office | FR | CORR | FTX1444A00Z | 620 | Delivered by Courier | 2012-07-18 |  | fiber and router needed | WVOT | 2011-12-01 | Y | Y | 12155.91 | N |  | 2011-12-13 | Y | 530 | 530 | 2012-08-01 | Complete | 2012-01-24 | N | No Build Required |  |  | 2012-01-24 | Complete | 2012-01-24 | Complete | 2012-07-18 | Ready
BB23A03 | LOGAN | BUFFALO ELEMENTARY SCHOOL | RO | K12 | FTX1439AH08 | 109 |  | 2011-07-28 |  |  | K-12 | TBD | Y | N |  |  |  |  | N | 0 | 0 | 2012-08-01 | 2012-08-01 | N/A | N | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-07-28 | Ready | 2012-01-05
BB23A04 | LOGAN | CHAPMANVILLE EAST ELEMENTARY SCHOOL | RO | K12 | FTX1437A1PZ | 110 |  | 2011-07-20 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-07-20 | Ready | 2012-01-05
BB23A05 | LOGAN | CHAPMANVILLE MIDDLE SCHOOL | RO | K12 | FTX1438A2C5 | 111 |  | 2011-07-20 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-07-20 | Ready | 2012-01-05
BB23A06 | LOGAN | HOLDEN CENTRAL ELEMENTARY SCHOOL | RO | K12 | FTX1437AJJ6 | 113 |  | 2011-07-27 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-07-27 | Ready | 2012-01-05
BB23A07 | LOGAN | HUGH DINGESS ELEMENTARY SCHOOL | RO | K12 | FTX1437AJHR | 114 |  | 2011-06-01 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-06-01 | Ready | 2012-01-05
BB23A08 | LOGAN | JUSTICE ELEMENTARY SCHOOL | RO | K12 | FTX1437AJJ7 | 115 |  | 2011-07-21 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-07-21 | Ready | 2012-01-05
BB23A09 | LOGAN | LOGAN MIDDLE SCHOOL | RO | K12 | FTX1437AJHW | 116 |  | 2011-07-21 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-07-21 | Ready | 2012-01-05
BB23A10 | LOGAN | OMAR ELEMENTARY SCHOOL | RO | K12 | FTX1437A1QW | 117 |  | 2011-07-27 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-07-27 | Ready | 2012-01-05
BB23A11 | LOGAN | SOUTH MAN ELEMENTARY SCHOOL | RO | K12 | FTX1438A2CF | 118 |  | 2011-09-19 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-09-19 | Ready | 2012-01-05
BB23A12 | LOGAN | VERDUNVILLE ELEMENTARY SCHOOL | RO | K12 | FTX1437AJHU | 119 |  | 2011-08-16 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-08-16 | Ready | 2012-01-05
BB23A13 | LOGAN | WEST CHAPMANVILLE ELEMENTARY SCHOOL | RO | K12 | FTX1437A1QG | 120 |  | 2011-07-21 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-07-21 | Ready | 2012-01-05
BB23A14 | LOGAN | WILLIS VOCATIONAL CENTER | RO | K12 | FTX1437A1NJ | 121 |  | 2011-07-28 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-07-28 | Ready | 2012-01-05
BB23A15 | LOGAN | Chapmanville Public Library | RO | LIB | FTX1439AJVD | 840 |  | 2012-08-15 |  | per FTR; site already has fiber- router only | WVNET |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-08-15 | Ready | 2012-08-24
BB23A16 | LOGAN | Logan Area Public Library | FR | LIB | FTX1439A153 | 838 |  | 2012-08-15 |  | fiber and router needed | WVNET | 2011-12-01 | Y | Y | 13859.44 | N |  | 2012-06-08 | Y | 1280 | 1280 | 2012-08-01 | Complete | 2012-08-29 | N | No Build Required |  |  | 2012-08-31 | Complete | 2012-08-31 | Complete | 2012-08-15 | Ready | 2012-09-07
BB23A17 | LOGAN | Buffalo Creek Memorial Library | FR | LIB | FTX1439A185 | 736 |  | 2012-02-24 |  | fiber and router needed | WVNET | 2011-12-01 | Y | Y | 15366.72 | N |  | 2012-05-24 | Y | 1500 | 1500 | 2012-08-01 | Complete | 2012-05-31 | Y | Scheduled | 2012-07-09 |  |  | TBD |  | Complete | 2012-02-24 | TBD
BB23A18 | LOGAN | Williamson Public Library | FR | LIB | FTX1439A15Z | 766 |  | 2012-04-23 |  | fiber and router needed | WVNET | 2011-12-09 | Y | Y | 7535.32 | Y | 2011-12-13 | 2011-12-22 | Y | 360 | 360 | 2012-08-01 | Complete | 2012-01-31 | N | No Build Required |  |  | 2012-01-31 | Complete | 2012-01-31 | Complete | 2012-04-23 | Ready | 2012-01-31
BB23A19 | LOGAN | Logan County Emergency Services | FR | PSAP | FTX1436AJUH | 1352 |  | 2012-01-31 |  | fiber and router needed |  | 2011-12-09 | Y | Y | 32978.81 | N |  | 2012-06-08 | Y | 2029 | 2029 | 2012-08-01 | Complete | 2012-08-29 | N | No Build Required |  |  | 2012-08-31 | Complete | 2012-08-31 | Complete | 2012-01-31 | Ready | 2012-09-07
BB23A20 | LOGAN | Southwestern Regional Jail | FR | RJAIL | FTX1436A1TW | 650 |  |  |  | fiber and router needed | WVOT | 2011-12-01 | Y | Y | 41247.23 | Y |  |  | N |  | TBD | 2012-08-01 | Complete | 2012-09-05 | N | No Build Required |  |  | 2012-09-05 | Complete | 2012-09-05 | TBD |  | Waiting on Router
BB23A21 | LOGAN | Logan Logan - Troop 5 State Police | FR | SP | FTX1436A24K | 1060 |  | 2012-01-13 |  | fiber and router needed | State Police | 2012-04-30 | Y | Y | 246967.52 | Y | 2012-05-02 | 2012-05-25 | Y |  | TBD | 2012-08-01 | 2012-08-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2012-01-13 | TBD
BB23A22 | LOGAN | BCI Troop 5 Command - Logan State Police | FR | SP | FTX1439A25D | 1073 |  | 2012-01-13 |  | fiber and router needed | State Police | 2011-12-12 | Y | Y | 8763.48 | N |  | 2011-12-19 | Y | 483 | 483 | 2012-08-01 | Complete | 2012-01-17 | N | No Build Required |  |  | 2012-01-17 | Complete | 2012-01-17 | Complete | 2012-01-13 | Ready | 2012-01-26
BB23A23 | LOGAN | Community Health Foundation at Logan | REM | TMED | [5 empty] | per FTR; site already has fiber- router only | ? |  | N | N/A |  |  |  |  | N/A |  | 0 | 2012-08-01 | Complete |  | N | Removed |  |  |  | Removed | N/A | N/A | N/A | Removed |  | *3/5/12 - No Longer in the same facility - in a new facility/modular unit and operate from there. The the old organization has gone bankrupt - Location is now Lincoln Primary Care/Southern WV Health Care - 650 East MacDonald Avenue, Mann, WV, 25635. Nick Patel - 3/5/12*
BB23A24 | LOGAN | Community Health Foundation of Man | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB23A25 | LOGAN | Logan General Hospital | RO | TMED | [5 empty] | PENDING GIT REVIEW FOR BUILD | ? | TBD | Y | N |  |  |  |  | N |  | TBD | 2012-08-01 | 2012-08-01 |  | N | No Build Required |  |  |  | Complete | N/A | TBD |  | Waiting on Router | N/A
BB24A01 | MARION | Marion County Courthouse | FR | CHOUSE | FTX1441A0PQ | 596 | Delivered and Installed by Tech | 2012-08-30 |  | fiber and router needed | WVNET | 2011-04-15 | Y | Y | 5441.9 | N |  | 2011-05-26 | Y | 515 | 515 | 2012-02-01 | Complete | 2012-03-21 | Y | Complete | 2012-06-28 | 2012-05-30 | 2012-07-19 | Complete | 2012-07-19 | Complete | 2012-08-30 | Ready | 2012-09-14 | *FBO Update - Wrong job submitted - Re-Bid required - Michelle - Gudenkauf Administrator - 4/16/12* *FBO Update - Will not be able to touch this site until May 8th due to the locations secondary circumstances. - Rick Singer - 4/25/12*
BB24A02 | MARION | Marion County Youth Reporting | FR | DJS | FTX1444AHKB | 478 |  |  |  | fiber and router needed | WVOT | 2011-04-15 | Y | Y | 16423.02 | N |  | 2012-01-17 | Y | 1987 | 1987 | 2012-02-01 | Complete | 2012-03-05 | Y | Complete | 2012-08-01 | 2012-08-09 | 2012-07-20 | Complete | 2012-07-20 | TBD |  | Waiting on Router
BB24A03 | MARION | BARNES LEARNING CENTER (ALC) | RO | K12 | FTX1442AKFD | 340 |  | 2011-10-11 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-10-11 | Ready | 2012-01-05
BB24A04 | MARION | BARRACKVILLE ELEM/MIDDLE SCHOOL | RO | K12 | FTX1442A1TP | 341 |  | 2011-10-10 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-10-10 | Ready | 2012-01-05
BB24A05 | MARION | BLACKSHERE ELEMENTARY SCHOOL | RO | K12 | FTX1442A1T5 | 342 |  | 2011-10-06 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-10-06 | Ready | 2012-01-05
BB24A06 | MARION | EAST DALE ELEMENTARY SCHOOL | RO | K12 | FTX1442A1HG | 343 |  | 2011-10-07 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-10-07 | Ready | 2012-01-05
BB24A07 | MARION | EAST FAIRMONT HIGH SCHOOL | RO | K12 | FTX1442AKEA | 344 |  | 2011-10-03 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-10-03 | Ready | 2012-01-05
BB24A08 | MARION | EAST FAIRMONT JUNIOR HIGH SCHOOL | RO | K12 | FTX1442A1T8 | 345 |  | 2011-10-11 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-10-11 | Ready | 2012-01-05
BB24A09 | MARION | EAST PARK ELEMENTARY SCHOOL | RO | K12 | FTX1442A1XM | 346 |  | 2012-04-19 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-04-19 | Ready | 2012-05-18
BB24A10 | MARION | FAIRMONT HIGH SCHOOL | RO | K12 | FTX1442A1TT | 347 |  | 2011-10-11 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-10-11 | Ready | 2012-01-05
BB24A11 | MARION | FAIRVIEW ELEMENTARY SCHOOL | RO | K12 | FTX1442A1T7 | 348 |  | 2011-10-10 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-10-10 | Ready | 2012-01-05
BB24A12 | MARION | FAIRVIEW MIDDLE SCHOOL | RO | K12 | FTX1442AKEH | 349 |  | 2011-10-10 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-10-10 | Ready | 2012-01-05
BB24A13 | MARION | JAYENNE ELEMENTARY SCHOOL | RO | K12 | FTX1442A2CN | 350 |  | 2011-10-03 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-10-03 | Ready | 2012-01-05
BB24A14 | MARION | MANNINGTON MIDDLE SCHOOL | RO | K12 | FTX1442A2SL | 351 |  | 2011-10-06 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-10-06 | Ready | 2012-01-05
BB24A15 | MARION | MARION COUNTY ADULT & COMMUNITY EDUC CTR | RO | K12 | FTX1442A2DS | 352 |  |  |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | TBD |  | Waiting on Router | N/A
BB24A16 | MARION | MARION COUNTY VOC-TECH CENTER | RO | K12 | FTX1442AKET | 353 |  | 2011-10-06 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-10-06 | Ready | 2012-01-05
BB24A17 | MARION | MONONGAH ELEMENTARY | RO | K12 | FTX1442A2C4 | 354 |  |  |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | TBD |  | Waiting on Router | N/A
BB24A18 | MARION | MONONGAH MIDDLE SCHOOL | RO | K12 | FTX1442AKEP | 355 |  | 2011-10-12 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-10-12 | Ready | 2012-01-05
BB24A19 | MARION | NORTH MARION HIGH SCHOOL | RO | K12 | FTX1442A2P0 | 356 |  | 2011-10-06 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-10-06 | Ready | 2012-01-05
BB24A20 | MARION | PLEASANT VALLEY ELEM SCHOOL | RO | K12 | FTX1442A2D6 | 357 |  | 2011-10-03 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-10-03 | Ready | 2012-01-05
BB24A21 | MARION | RIVESVILLE ELEM/MIDDLE SCHOOL | RO | K12 | FTX1442AKEC | 358 |  | 2011-10-12 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-10-12 | Ready | 2012-01-05
BB24A22 | MARION | WATSON ELEMENTARY SCHOOL | RO | K12 | FTX1442A1DD | 359 |  | 2011-10-03 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-10-03 | Ready | 2012-01-05
BB24A23 | MARION | WEST FAIRMONT MIDDLE | RO | K12 | FTX1442A2BX | 360 |  | 2011-09-20 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-09-20 | Ready | 2012-01-05
BB24A24 | MARION | WHITE HALL ELEMENTARY | RO | K12 | FTX1442A2C1 | 361 |  | 2012-04-17 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-04-17 | Ready | 2012-05-18
BB24A25 | MARION | Marion County Public Library | FR | LIB | FTX1439A13X | 828 |  | 2012-07-23 |  | fiber and router needed | WVNET | 2011-04-15 | Y | Y | 9735 | N |  | 2011-05-26 | Y | 1305 | 1305 | 2012-02-01 | Complete | 2012-04-10 | Y | Complete | 2012-03-02 | 2012-04-16 | 2012-04-23 | Complete | 2012-04-23 | Complete | 2012-07-23 | Ready |  | *FBO No Longer Required - Work was already completed on site when visited - Rick Singer - Gudenkauf - 4/16/12*
BB24A26 | MARION | Fairview Public Library | FR | LIB | FTX1439A18E | 830 |  | 2012-07-23 |  | fiber and router needed | WVNET | 2011-04-05 | Y | Y | 7195 | N |  | 2011-05-26 | Y | 750 | 750 | 2012-03-01 | Complete | 2011-10-28 | Y | Complete | 2012-04-02 | 2012-03-14 | 2012-04-16 | Complete | 2012-04-16 | Complete | 2012-07-23 | Ready |  | **LCR WAS LISTED ON MIKE TORDORVICH'S MEMO TO APPROVE 26 LCRs ON 4/15/2011**
BB24A27 | MARION | Mannington Public Library | FR | LIB | FTX1439A16R | 829 |  | 2012-07-23 |  | fiber and router needed | WVNET | 2011-04-15 | Y | Y | 3991 | N |  | 2011-05-26 | Y | 535 | 535 | 2012-03-01 | Complete | 2011-09-13 | Y | Complete | 2012-03-02 | 2012-03-02 | 2012-03-26 | Complete | 2012-03-26 | Complete | 2012-07-23 | Ready |  | *FBO Update - Revised completion date from sontractors of 2/23/2012 - 2/22/12*
BB24A28 | MARION | Region 6–Planning and Development Council (Doddrill, Harrison, Marion, Monongalia, Preston, Taylor) | FR | PDEV | FTX1436A1Y1 | 1020 | 1ZX560410300469360 | 2011-09-29 |  | fiber and router needed | ? | 2011-04-05 | Y | Y | 6822 | N |  | 2011-05-26 | Y | 700 | 700 | 2012-03-01 | Complete | 2011-05-04 | Y | Complete | 2012-04-27 | 2012-03-28 | 2012-04-16 | Complete | 2012-04-16 | Complete | 2011-09-29 | Ready | 2012-04-19 | **LCR WAS LISTED ON MIKE TORDORVICH'S MEMO TO APPROVE 26 LCRs ON 4/15/2011**
BB24A29 | MARION | Marion Central Comm-911 | FR | PSAP | FTX1436AJUT | 1390 |  | 2012-01-30 |  | fiber and router needed |  | 2011-11-30 | Y | Y | 5500 | N |  | 2011-12-08 | Y | 0 | 0 | 2012-03-01 | 2012-03-01 | 2/29/11 | N | No Build Required |  |  | 2012-02-29 | Complete | 2012-02-29 | Complete | 2012-01-30 | Ready | 2012-03-02 | 12/22/11: LCR WAS APPROVED ON 12/8/11 AND LCR FINAL APPROVAL NOTICE WAS SENT TO CAI/FTR. WILL NOT BE RESENDING LCR FINAL APPROVAL NOTICE.
BB24A30 | MARION | Fairmont Marion - Troop 1 State Police | FR | SP | FTX1439A25E | 1074 |  | 2011-12-14 |  | fiber and router needed | State Police | 2011-04-05 | Y | Y | 6822 | N |  | 2011-05-26 | Y | 700 | 700 | 2012-03-01 | Complete | 2011-04-29 | Y | Complete | 2012-03-06 | 2012-03-02 | 2012-03-26 | Complete | 2012-03-26 | Complete | 2011-12-14 | Ready | 2012-03-29 | **LCR WAS LISTED ON MIKE TORDORVICH'S MEMO TO APPROVE 26 LCRs ON 4/15/2011** *FBO Revised - Revised Date of Completion to 2/21/12*
BB24A31 | MARION | BCI Fairmont State Police | FR | SP | FTX1439A24G | 1058 |  | 2011-12-14 |  | fiber and router needed | State Police | 2011-04-15 | Y | Y | 8597 | N |  | 2012-01-17 | Y | 1150 | 1150 | 2012-02-01 | Complete | 2012-04-10 | Y | Complete | 2012-07-20 | 2012-06-05 | 2012-06-18 | Complete | 2012-06-18 | Complete | 2011-12-14 | Ready | 2012-06-22
BB24A32 | MARION | MVA(Mon Valley Assn) Health Centers Inc Nancy Vandergrift (Updated list 8/25/10) | FR | TMED | FTX1444AJ1M | 874 | 1ZX560410300469333 | 2011-09-28 |  | fiber and router needed | ? | 2011-08-02 | Y | Y | 5978 | N |  | 2011-09-14 | Y | 400 | 400 | 2011-10-26 | Complete | 2011-10-05 | N | No Build Required |  |  | 2011-10-26 | Complete | 2011-10-26 | Complete | 2011-09-28 | Ready | 2012-01-05
BB24A33 | MARION | Fairmont WVUHS | RO | TMED | FTX1444AJ1G | 871 | 1ZX560410300467906 | 2011-10-03 |  | per FTR; site already has fiber- router only | ? |  | N | N/A |  |  |  |  | N/A |  | 0 |  | Complete |  |  | No Build Required |  |  |  | Complete | N/A | Complete | 2011-10-03 | Ready | 2012-02-02
BB25A01 | MARSHALL | Marshall County Courthouse | FR | CHOUSE | FTX1441AJ01 |  |  |  |  | fiber and router needed | WVNET | 2011-10-04 | Y | Y | 21163 | N |  | 2011-12-08 | Y | 2100 | 2100 | 2012-02-01 | Complete | 2012-01-06 | Y | Complete | 2012-04-06 | 2012-03-02 | 2012-03-14 | Complete | 2012-03-14 | TBD |  | Waiting on Router |  | *FBO Update - Revised completion date from contractors of 2/22/2012 - 2/23/12*
BB25A02 | MARSHALL | Northern Correctional Facility | FR | CORR | FTX1441AJ1P | 621 |  |  |  | fiber and router needed | WVOT | 2011-10-04 | Y | Y | 60515 | Y | 2011-10-26 | 2011-12-08 | Y | 7500 | 7500 | 2012-03-01 | Complete | 2012-05-21 | N | No Build Required |  |  | 2012-05-21 | Complete | 2012-05-21 | TBD |  | Waiting on Router
BB25A03 | MARSHALL | Northern Region Office | FR | CORR | FTX1444AJ1J | 622 |  |  |  | fiber and router needed | WVOT | 2011-10-04 | Y | Y | 24563 | N |  | 2012-01-31 | Y | 2100 | 2100 | 2012-03-01 | Complete | 2012-05-18 | Y | Scheduled | 2012-07-18 |  |  | TBD |  | TBD |  | TBD |  | *FBO Hold - FBO Approved Pending EA Review - 6/29/12* *FBO Update - EA Approved 9/11/12*
BB25A04 | MARSHALL | Cameron Elementary School | FR | K12 | FTX1443AK5Z | 301 |  | 2011-06-29 |  | fiber and router needed | K-12 | 2011-10-04 | Y | Y | 31866.5 | N |  | 2011-10-18 | Y | 3600 | 3600 | 2012-03-01 | Complete | 2012-02-20 | N | No Build Required |  |  | 2012-02-20 | Complete | 2012-02-20 | Complete | 2011-06-29 | Ready | 2012-02-23
BB25A05 | MARSHALL | CAMERON HIGH SCHOOL | FR | K12 | FTX1443AK4C | 302 |  |  |  | fiber and router needed | K-12 | 2011-10-04 | Y | Y | 146409.95 | N |  | 2011-10-18 | Y | 17550 | 17550 | 2012-03-01 | Complete | 2012-02-20 | N | No Build Required |  |  | 2012-02-20 | Complete | 2012-02-20 | TBD |  | Waiting on Router
BB25A06 | MARSHALL | CENTER MCMECHEN ELEMENTARY SCHOOL | FR | K12 | FTX1443AK4W | 303 |  | 2011-08-08 |  | fiber and router needed | K-12 | 2011-10-04 | Y | Y | 10465.52 | N |  | 2011-12-08 | Y | 1086 | 1086 | 2011-12-01 | Complete | 2011-11-13 | Y | Complete | 2012-02-20 | 2012-02-10 | 2012-02-28 | Complete | 2012-02-28 | Complete | 2011-08-08 | Ready | 2012-03-02 | *FBO Revised - Revised Date of Completion to 2/6/12*
BB25A07 | MARSHALL | CENTRAL ELEMENTARY SCHOOL | FR | K12 | FTX1443A23T | 304 |  | 2011-08-15 |  | fiber and router needed | K-12 | 2011-10-04 | Y | Y | 16578.96 | N |  | 2011-12-08 | Y | 1200 | 1200 | 2012-02-01 | Complete | 2012-01-06 | Y | Complete | 2012-03-28 | 2012-02-21 | 2012-03-09 | Complete | 2012-03-09 | Complete | 2011-08-15 | Ready | 2012-03-16
BB25A08 | MARSHALL | GLEN DALE ELEMENTARY SCHOOL | FR | K12 | FTX1442A2DQ | 305 |  | 2011-08-05 |  | fiber and router needed | K-12 | 2011-10-04 | Y | Y | 12490.61 | N |  | 2011-10-18 | Y | 1025 | 1025 | 2011-12-01 | Complete | 2011-11-14 | Y | Complete |  | 2012-01-18 | 2012-01-18 | Complete | 2012-01-18 | Complete | 2011-08-05 | Ready | 2012-01-20 | *FBO - Not required due to location completing FBO on own - 12/15/11*
BB25A09 | MARSHALL | JOHN MARSHALL HIGH SCHOOL | FR | K12 | FTX1443AK6P | 306 |  | 2011-10-05 |  | fiber and router needed | K-12 | 2011-10-04 | Y | Y | 12329.79 | N |  | 2011-10-18 | Y | 800 | 800 | 2011-12-01 | Complete | 2011-11-15 | Y | Complete |  | 2011-12-21 | 2011-12-21 | Complete | 2011-12-21 | Complete | 2011-10-05 | Ready | 2012-01-05 | *FBO - Not required due to location completing FBO on own - 12/15/11*
BB25A10 | MARSHALL | MCNINCH ELEMENTARY | FR | K12 | FTX1443AK46 | 308 |  | 2011-08-05 |  | fiber and router needed | K-12 | 2011-10-04 | Y | Y | 25744.89 | Y | 2011-10-26 | 2011-12-08 | Y | 5000 | 5000 | 2012-03-01 | Complete | 2012-01-06 | Y | Complete | 2012-03-20 | 2012-02-21 | 2012-03-19 | Complete | 2012-03-19 | Complete | 2011-08-05 | Ready | 2012-03-23
BB25A11 | MARSHALL | MOUNDSVILLE JUNIOR HIGH SCHOOL | FR | K12 | FTX1443AK3X | 309 |  | 2011-08-05 |  | fiber and router needed | K-12 | 2011-10-04 | Y | Y | 10381.59 | N |  | 2011-12-08 | Y | 3550 | 3550 | 2012-02-01 | Complete | 2012-01-11 | N | No Build Required |  |  | 2012-01-12 | Complete | 2012-01-12 | Complete | 2011-08-05 | Ready | 2012-01-13
BB25A12 | MARSHALL | SAND HILL ELEMENTARY SCHOOL | FR | K12 | FTX1443AK4E | 311 |  | 2011-11-23 |  | fiber and router needed | K-12 | 2011-10-04 | Y | Y | 10346.48 | N |  | 2011-10-18 | Y | 1200 | 1200 | 2011-12-01 | Complete | 2011-11-15 | Y | Complete |  | 2012-01-19 | 2012-01-19 | Complete | 2012-01-19 | Complete | 2011-11-23 | Ready | 2012-01-26 | *FBO - Not required due to location completing FBO on own - 12/15/11*
BB25A13 | MARSHALL | Sherrard Middle School | FR | K12 | FTX1443A239 | 314 |  | 2011-08-05 |  | fiber and router needed | K-12 | 2011-10-04 | Y | Y | 41000.37 | Y | 2011-11-01 | 2011-12-08 | Y | 4944 | 4944 | 2012-03-01 | Complete | 2012-01-26 | Y | Complete | 2012-04-25 | 2012-03-19 | 2012-04-09 | Complete | 2012-04-09 | Complete | 2011-08-05 | Ready | 2012-04-13 | *FBO Approval - Approved by Mike Todorovich and John Dunlap - 3/5/12* *FBO Revision - Dave (Gudenkauf) Stated the location had existing conduit and the Final Invoice will reflect a much lower price for the work completed. - 3/14/12* *FBO Update - Price of Final invoice is now $3500.00 - Utilized existing conduit to get to the Demarc. - 3/19/12*
BB25A14 | MARSHALL | WASHINGTON LANDS ELEMENTARY SCHOOL | FR | K12 | FTX1437A1NR | 315 |  | 2011-08-08 |  | fiber and router needed | K-12 | 2011-10-04 | Y | Y | 60259.05 | N |  | 2011-12-08 | Y | 10000 | 10000 | 2012-02-01 | Complete | 2012-09-20 | Y | TBD |  |  |  | TBD |  | Complete | 2011-08-08 | TBD
BB25A15 | MARSHALL | City- County SEE Moundsville-Marshall County | RO | LIB | [5 empty] | per FTR; site already has fiber- router only | WVNET |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | TBD |  | Waiting on Router | N/A
BB25A16 | MARSHALL | Moundsville-Marshall County Public Library | FR | LIB | FTX1439A17B | 718 |  | 2012-01-31 |  | fiber and router needed | WVNET | 2011-10-04 | Y | Y | 18656.77 | N |  | 2011-12-08 | Y | 1500 | 1500 | 2012-03-01 | Complete | 2012-04-10 | Y | Complete | 2012-04-19 | 2012-05-07 | 2012-04-26 | Complete | 2012-04-26 | Complete | 2012-01-31 | Ready | 2012-05-04 | Name of library officially changed 7/1/03 Keg
BB25A17 | MARSHALL | Benwood-McMechen Public Library | FR | LIB | FTX1439AJZG | 723 |  | 2012-01-24 |  | fiber and router needed | WVNET | 2011-10-04 | Y | Y | 15631.93 | N |  | 2011-10-18 | Y | 1900 | 1900 | 2011-12-01 | Complete | 2011-11-14 | Y | Complete | 2012-03-14 | 2012-02-10 | 2012-03-08 | Complete | 2012-03-08 | Complete | 2012-01-24 | Ready | 2012-03-21 | *FBO Revised - Revised Date of Completion to 2/8/12*
BB25A18 | MARSHALL | Cameron Public Library | FR | LIB | FTX1439AJW8 | 724 |  | 2012-01-25 |  | fiber and router needed | WVNET | 2011-10-04 | Y | Y | 3555.8 | N |  | 2011-10-18 | Y | 300 | 300 | 2012-03-01 | Complete | 2012-02-20 | N | No Build Required |  |  | 2012-02-20 | Complete | 2012-02-20 | Complete | 2012-01-25 | Ready | 2012-02-23
BB25A19 | MARSHALL | Marshall County E-9-1-1 | FR | PSAP | FTX1436AJUY | 1370 |  | 2012-01-24 |  | fiber and router needed |  | 2011-10-04 | Y | Y | 19901.82 | Y | 2011-10-26 | 2011-12-08 | Y | 1200 | 1200 | 2012-03-01 | Complete | 2012-01-06 | Y | Complete | 2012-08-03 | 2012-06-05 | 2012-06-25 | Complete | 2012-06-25 | Complete | 2012-01-24 | Ready |  | *FBO on Hold - Larry Newell 304-845-1920 (911 Director), and Howard Coffield 304-780-9866 (Commissioner) at the existing d-mark which is located in the Marshall County Courthouse basement. It doesn’t make sense to terminate two cables at the same location and Mr Newell/Mr Coffield suggested that we leave the fiber coil on the pole in front of the 911 Center. According to them there will be a new building built in the near future and they could utilize that unused fiber cable for the new de-mark after the new building is built. In the meantime the 911 center could be fed by the terminal already in place at the courthouse. (The courthouse is only using a couple fibers.) - Rick Singer - Gudenkauf - 4/17/12* *FBO Update - Per Tiger Team - Go to Demarc. If building will not be constructed until next year that is too long to allow the entrance fiber to just hang there. The fibr can be utilized within that year. If the facility is moving then they can place a TCR to move the Demarc to the new location when that time comes. - John Dunlap - 4/24/12*
BB25A20 | MARSHALL | Northern Regional Jail | FR | RJAIL | FTX1414AKFH | 653 |  |  |  | fiber and router needed | WVOT | 2011-10-04 | Y | Y | SEE BB25A02 | Y | 2011-10-26 | 2011-12-08 | Y | SEE BB25A02 | Included | 2012-02-01 | Complete | 2012-05-21 | N | No Build Required |  |  | 2012-05-21 | Complete | 2012-05-21 | TBD |  | Waiting on Router
BB25A21 | MARSHALL | Moundsville Marshall - Troop 1 State Police | FR | SP | FTX1439A26R | 1097 |  | 2011-12-19 |  | fiber and router needed | State Police | 2011-10-04 | Y | Y | 8410.8 | Y | 10/26/2011; 11/8/2011 | 2011-12-08 | Y | 1000 | 1000 | 2012-03-01 | Complete | 2012-01-06 | Y | Complete | 2012-02-27 | 2012-02-15 | 2012-02-29 | Complete | 2012-02-29 | Complete | 2011-12-19 | Ready | 2012-03-02 | *FBO Revised - Revised Date of Completion to 2/14/12*
BB26A01 | MASON | Mason County Courthouse | FR | CHOUSE | FTX1441A0PU |  |  |  |  | fiber and router needed | WVNET | 2011-10-06 | Y | Y | 8382.04 | N |  | 2012-03-30 | Y | 725 | 725 | 2012-08-01 | Complete | 2012-04-25 | Y | Complete | 2012-05-16 | 2012-05-29 | 2012-06-14 | Complete | 2012-06-14 | TBD |  | Waiting on Router
BB26A02 | MASON | Lakin Correctional Center | RO | CORR | FTX1444A00U | 623 |  | 2012-03-09 |  | per FTR; site already has fiber- router only | WVOT |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-03-09 | Ready | 2012-03-15
BB26A03 | MASON | ASHTON ELEMENTARY SCHOOL | RO | K12 | FTX1437A1PU | 70 |  | 2011-09-02 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-09-02 | Ready | 2012-01-05
BB26A04 | MASON | BEALE ELEMENTARY SCHOOL | RO | K12 | FTX1442AKE4 | 71 |  | 2011-07-07 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-07-07 | Ready | 2012-01-05
BB26A05 | MASON | LEON ELEMENTARY SCHOOL | RO | K12 | FTX1437A1Q6 | 72 |  | 2011-09-02 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-09-02 | Ready | 2012-01-05
BB26A06 | MASON | MASON COUNTY VOCATIONAL CENTER | RO | K12 | FTX1437AJJ5 | 73 |  | 2011-07-07 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-07-07 | Ready | 2012-01-05
BB26A07 | MASON | NEW HAVEN ELEMENTARY SCHOOL | FR | K12 | FTX1437AJJF | 74 |  | 2011-07-22 |  | fiber and router needed | K-12 | 2011-11-06 | Y | Y | 18890.98 | N |  | 2011-11-09 | Y | 1178 | 1178 | 2012-06-01 | Complete | 2011-12-28 | N | No Build Required |  |  | 2012-01-10 | Complete | 2012-01-10 | Complete | 2011-07-22 | Ready | 2012-01-13
BB26A08 | MASON | POINT PLEASANT INTERMEDIATE | RO | K12 | FTX1437A1NH | 75 |  | 2011-09-02 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-09-02 | Ready | 2012-01-05
BB26A09 | MASON | POINT PLEASANT PRIMARY | RO | K12 | FTX1443A23Z | 76 |  | 2011-07-07 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-07-07 | Ready | 2012-01-05
BB26A10 | MASON | ROOSEVELT ELEMENTARY SCHOOL | RO | K12 | FTX1443AK4R | 77 |  | 2011-09-02 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-09-02 | Ready | 2012-01-05
BB26A11 | MASON | Mason City Public Library | FR | LIB | FTX1439A14J | 713 |  | 2012-02-08 |  | fiber and router needed | WVNET | 2011-11-21 | Y | Y | 9975.79 | N |  | 2012-03-30 | Y | 1100 | 1100 | 2012-08-01 | Complete | 2012-04-26 | Y | Complete | 2012-05-31 | 2012-07-09 | 2012-08-31 | Complete | 2012-08-31 | Complete | 2012-02-08 | Ready | 2012-09-07
BB26A12 | MASON | Hannan Public Library | FR | LIB | FTX1439A190 | 717 |  | 2012-03-22 |  | fiber and router needed | WVNET | 2011-02-13 | Y | Y | 13542.39 | N |  | 2012-03-30 | Y | 1030 | 1030 | 2012-08-01 | Complete | 2012-04-26 | Y | Complete | 2012-05-14 | 2012-07-09 | 2012-08-31 | Complete | 2012-08-31 | Complete | 2012-03-22 | Ready | 2012-09-07
BB26A13 | MASON | Mason County Public Library | FR | LIB | FTX1439AJZH | 755 |  | 2012-03-07 |  | fiber and router needed | WVNET | 2011-10-06 | Y | Y | 5194.15 | N |  | 2011-10-18 | Y | 340 | 340 | 2011-12-01 | Complete | 2011-11-13 | N | No Build Required |  |  | 2011-11-13 | Complete | 2011-11-13 | Complete | 2012-03-07 | Ready | 2012-04-05
BB26A14 | MASON | New Haven Public Library | FR | LIB | FTX1439A157 | 714 |  | 2012-03-22 |  | fiber and router needed | WVNET | 2011-11-06 | Y | Y | 23031.3 | N |  | 2012-03-30 | Y | 2111 | 2111 | 2012-08-01 | Complete | 2012-06-21 | N | No Build Required |  |  | 2012-06-21 | Complete | 2012-06-21 | Complete | 2012-03-22 | Ready | 2012-06-22
BB26A15 | MASON | 911 Center | FR | PSAP | FTX1436AJUV | 1366 |  | 2012-01-10 |  | fiber and router needed |  | 2011-10-06 | Y | Y | 12689.41 | N |  | 2012-03-30 | Y | 1935 | 1935 | 2012-08-01 | Complete | 2012-04-25 | N | No Build Required |  |  | 2012-04-25 | Complete | 2012-04-25 | Complete | 2012-01-10 | Ready | 2012-04-27
BB26A16 | MASON | Mason County Detachment Mason - Troop 5 State Police | FR | SP | FTX1439A23V | 1042 |  | 2012-01-20 |  | fiber and router needed | State Police | 2011-11-06 | Y | Y | 204743.77 | N |  | 2011-11-10 | Y | 36178 | 36178 |  | TBD | 2012-06-01 | N | No Build Required |  |  | 2012-06-11 | Complete | 2012-06-11 | Complete | 2012-01-20 | Ready
BB33A01 | MCDOWELL | McDowell County Courthouse | FR | CHOUSE | FTX1441A0PY |  |  |  |  | fiber and router needed | WVNET | 2011-11-14 | Y | Y | 16041.02 | N |  | 2011-12-08 | Y | 1220 | 1220 | 2012-09-01 | Complete | 2012-02-29 | N | No Build Required |  |  | 2012-02-29 | Complete | 2012-02-29 | TBD |  | Waiting on Router
BB27A02 | MERCER | Princeton Parole Office | FR | CORR | FTX1444AJ0X | 627 | Courier Delivery | 2012-06-25 |  | fiber and router needed | WVOT | 2011-11-29 | Y | Y | 18375.94 | Y | 2012-05-07 | 12/8/2011; 5/10/12 | Y | 3215 | 3215 | 2012-09-01 | 2012-09-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2012-06-25 | TBD
BB27A03 | MERCER | Mercer County Youth Reporting | FR | DJS | FTX1444AJ12 | 479 |  | 2012-04-13 |  | fiber and router needed | WVOT | 2011-11-29 | Y | Y | 13812.08 | N |  | 2012-04-09 | Y | 997 | 997 | 2012-09-01 | 2012-09-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2012-04-13 | TBD
BB27A04 | MERCER | WVIEP - SAM PERDUE (SOUTHRN REG) JUVENILE CENTER DJS | FR | K12 | FTX1438A2CS | 14 |  | 2011-01-28 |  | fiber and router needed | K-12 | 2011-11-29 | Y | Y | 13303.17 | N |  | 2011-12-08 | Y | 1111 | 1111 | 2012-09-01 | 2012-09-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2011-01-28 | TBD
BB27A05 | MERCER | Craft Memorial Library | FR | LIB | FTX1439A149 |  |  | 2012-04-26 |  | fiber and router needed | WVNET | 2011-09-23 | Y | Y | 14678.24 | N |  | 2011-10-06 | Y | 1215 | 1215 | 2012-09-01 | 2012-09-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2012-04-26 | TBD
BB27A06 | MERCER | Princeton Public Library | FR | LIB | FTX1439A14L |  |  | 2012-04-26 |  | fiber and router needed | WVNET | 2011-11-21 | Y | Y | 12346.08 | N |  | 2012-04-09 | Y | 390 | 390 | 2012-09-01 | Complete | 2012-06-06 | N | No Build Required |  |  | 2012-06-06 | Complete | 2012-06-06 | Complete | 2012-04-26 | Ready | 2012-06-08
BB27A07 | MERCER | Region 1–Planning and Development Council (McDowell, Mercer, Monroe, Raleigh, Summers, Wyoming ) | FR | PDEV | FTX1436A1UU | 1029 | 1ZX560410300487877 | 2011-12-21 |  | fiber and router needed | ? | 2011-11-30 | Y | Y | 14097.8 | N |  | 2011-12-08 | Y | 393 | 393 | 2012-10-01 | Complete | 2012-03-30 | Y | TBD |  |  |  | TBD |  | Complete | 2011-12-21 | TBD
BB27A08 | MERCER | 911 Comm Center | FR | PSAP | FTX1436AJTM | 1353 |  | 2011-12-21 |  | fiber and router needed |  | 2011-11-30 | Y | Y | 372482.42 | N |  | 2012-04-09 | Y | 49993 | 49993 | 2012-10-01 | 2012-10-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2011-12-21 | TBD
BB27A09 | MERCER | Princeton / Mercer - Troop 6 State Police | FR | SP | FTX1439A26Y | 1104 |  | 2012-01-05 |  | fiber and router needed | State Police | 2011-11-14 | Y | Y | 13241.86 | N |  | 2011-12-08 | Y | 481 | 481 | 2012-10-01 | Complete | 2012-04-10 | Y | Scheduled | 2012-06-01 |  |  | TBD |  | Complete | 2012-01-05 | TBD
BB27A10 | MERCER | Princeton Turnpike / Mercer State Police | FR | SP | FTX1439A23Q | 1039 |  | 2012-01-05 |  | fiber and router needed | State Police | 2011-11-28 | Y | Y | 16469.55 | N |  | 2011-12-08 | Y | 1765 | 1765 | 2012-10-01 | Complete | 2012-03-27 | N | No Build Required |  |  | 2012-03-27 | Complete | 2012-03-27 | Complete | 2012-01-05 | Ready | 2012-04-19
BB27A11 | MERCER | BCI Bluefield / Mercer - Troop 6 State Police | FR | SP | FTX1439A26X | 1103 |  | 2012-01-25 |  | fiber and router needed | State Police | 2011-10-24 | Y | Y | 18976.49 | N |  | 2012-02-24 | Y | 2954 | 2954 | 2012-10-01 | Complete | 2012-04-09 | Y | Complete | 2012-05-23 | 2012-07-03 | 2012-07-03 | Complete | 2012-07-03 | Complete | 2012-01-25 | Ready | 2012-09-28
BB27A12 | MERCER | Bluefield Memorial Hospital | REM | TMED | FTX1443A28E | 928 | Courier Delivery |  |  | PER GIT DECISION: CAI HAS FIBER AT LOCATION; ROUTER ONLY. | ? | N/A | Y | Y |  |  |  |  | N |  | TBD | 2012-10-01 | 2012-10-01 |  | N | Removed |  |  |  | Removed | N/A | N/A | N/A | Removed
BB27A13 | MERCER | Green Valley Family Med (Bluefield off site) | FR | TMED | FTX1436A1SB | 890 | 1ZX560410300484101 | 2012-04-24 |  | fiber and router needed | ? | 2011-11-28 | Y | Y | 15134.17 | N |  | 2011-12-08 | Y | 1450 | 1450 | 2012-10-01 | 2012-10-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2012-04-24 | TBD
BB27A01 | MERCER | Mercer County Courthouse | FR | CHOUSE | FTX1441AJ06 |  |  |  |  | fiber and router needed | WVNET | 2011-11-30 | Y | Y | 27597.75 | N |  | 2011-12-08 | Y | 5703 | 5703 | 2012-09-01 | Complete | 2012-04-06 | Y | TBD |  |  |  | TBD |  | TBD |  | TBD |  | *FBO Issue - Issue to get into the building - Window - Conduit. 2 Ft of sand stone*
BB28A02 | MINERAL | Keyser Parole Office | FR | CORR | FTX1444AHKQ | 628 |  |  |  | fiber and router needed | WVOT | 2011-09-13 | Y | Y | 1750 | N |  | 2011-11-09 | Y | 160 | 160 | 2012-01-01 | Complete | 2011-11-14 | Y | Complete |  | 2012-02-16 | 2012-03-22 | Complete | 2012-03-22 | TBD |  | Waiting on Router |  | *FBO Not Required - Completed by Customer - Ester Hagy (Nichols Construction) - 02/15/12*
BB28A03 | MINERAL | *MINERAL COUNTY VOC-TECH SCHOOL Shared with Administrative Offices (Shared with board office--cannot determine actual counts) | FR | K12 | FTX1437A1NN | 446 |  | 2011-07-26 |  | fiber and router needed | K-12 | 2011-09-13 | Y | Y | 24442.7 | N |  | 2011-11-09 | Y | 3295 | 3295 | 2012-01-01 | Complete | 2011-12-23 | Y | Complete | 2012-05-09 | 2012-07-02 | 2012-05-25 | Complete | 2012-05-25 | Complete | 2011-07-26 | Ready | 2012-06-08
BB28A04 | MINERAL | BURLINGTON PRIMARY | FR | K12 | FTX1442AKEM | 447 |  | 2011-07-26 |  | fiber and router needed | K-12 | 2011-05-16 | Y | Y | 9608.4 | Y | 2011-06-15 | 5/19/11; 7/5/2011 | Y | 1240 | 1240 | 2011-12-01 | Complete | 2011-11-18 | N | No Build Required |  |  | 2011-11-18 | Complete | 2011-11-18 | Complete | 2011-07-26 | Ready | 2012-01-05
BB28A05 | MINERAL | ELK GARDEN SCHOOL | FR | K12 | FTX1443AK4P | 448 |  | 2011-07-26 |  | fiber and router needed | K-12 | 2011-09-13 | Y | Y | $ 32,902.00 ($4,054.00) | Y | 9/13/2011; 4/27/2012 | 11/9/2011; 5/10/12 | Y | 4400 | 4400 | 2012-06-01 | Complete | 2012-07-31 | N | No Build Required |  |  | 2012-07-31 | Complete | 2012-07-31 | Complete | 2011-07-26 | Ready | 2012-08-03
BB28A06 | MINERAL | FORT ASHBY PRIMARY | FR | K12 | FTX1443AK5J | 449 |  | 2011-07-27 |  | fiber and router needed | K-12 | 2011-05-16 | Y | Y | 20157.6 | Y | 2011-06-15 | 5/19/11; 7/5/2011 | Y | 2940 | 2940 | 2012-01-01 | Complete | 2011-12-01 | N | No Build Required |  |  | 2011-12-05 | Complete | 2011-12-05 | Complete | 2011-07-27 | Ready | 2012-01-05
BB28A07 | MINERAL | FOUNTAIN PRIMARY SCHOOL | FR | K12 | FTX1443AK4D | 450 |  | 2012-02-03 |  | fiber and router needed | K-12 | 2011-09-13 | Y | Y | 36567.02 | N |  | 2011-11-09 | Y | 4887 | 4887 | 2012-01-01 | Complete | 2011-12-27 | N | No Build Required |  |  | 2012-01-03 | Complete | 2012-01-03 | Complete | 2012-02-03 | Ready | 2012-01-05
BB28A08 | MINERAL | FRANKFORT HIGH SCHOOL | FR | K12 | FTX1443AK59 | 451 |  | 2011-07-27 |  | fiber and router needed | K-12 | 2011-09-13 | Y | Y | 51866.22 | Y | 2011-09-13 | 2011-11-09 | Y | 2727 | 2727 | 2012-01-01 | Complete | 2011-12-08 | Y | Complete | 2012-05-15 | 2012-07-02 | 2012-05-25 | Complete | 2012-05-25 | Complete | 2011-07-27 | Ready | 2012-06-08
BB28A09 | MINERAL | FRANKFORT INTERMEDIATE SCHOOL | FR | K12 | FTX1443AK3T | 452 |  | 2011-07-27 |  | fiber and router needed | K-12 | 2011-05-16 | Y | Y | 20524.6 | Y | 2011-06-15 | 2011-05-19 | Y | 2690 | 2690 | 2012-01-01 | Complete | 2011-09-26 | N | No Build Required |  |  | 2011-12-05 | Complete | 2011-12-05 | Complete | 2011-07-27 | Ready | 2012-01-05
BB28A10 | MINERAL | FRANKFORT MIDDLE SCHOOL | FR | K12 | FTX1443AK50 | 453 |  | 2011-07-27 |  | fiber and router needed | K-12 | 2011-09-13 | Y | Y | 42958.13 | Y | 2011-09-15 | 2011-11-09 | Y | 3157 | 3157 | 2012-01-01 | Complete | 2011-11-29 | Y | Scheduled | 2012-05-20 |  |  | TBD |  | Complete | 2011-07-27 | TBD |  | *FBO On Hold - Pending EA Approval - 5/22/12 - Nick Patel* *FBO Update - EA Approved - 8/13/12* *FBO Update - Lance Approves construction costs - 8/27/12*
BB28A11 | MINERAL | KEYSER HEADSTART SCHOOL | FR | K12 | FTX1438A2BW | 454 |  | 2012-02-03 |  | fiber and router needed | K-12 | 2011-09-13 | Y | Y | 72972.5 | N |  | 2011-09-16 | Y | 6915 | 6915 | 2012-01-01 | Complete | 2011-11-29 | N | No Build Required |  |  | 2011-11-29 | Complete | 2011-11-29 | Complete | 2012-02-03 | Ready | 2012-02-17
BB28A12 | MINERAL | KEYSER HIGH SCHOOL | FR | K12 | FTX1438A2DX | 455 |  | 2011-07-26 |  | fiber and router needed | K-12 | 2011-09-13 | Y | Y | 159666.04 | N |  | 2011-09-16 | Y | 22210 | 22210 | 2012-01-01 | Complete | 2011-12-20 | N | No Build Required |  |  | 2011-12-20 | Complete | 2011-12-20 | Complete | 2011-07-26 | Ready | 2012-01-05
BB28A13 | MINERAL | KEYSER PRIMARY / MIDDLE SCHOOL | FR | K12 | FTX1438A2C6 | 456 |  | 2011-07-26 |  | fiber and router needed | K-12 | 2011-09-13 | Y | Y | 5373.3 | N |  | 2011-11-09 | Y | 905 | 905 | 2012-01-01 | Complete | 2011-12-15 | N | No Build Required |  |  | 2011-12-13 | Complete | 2011-12-13 | Complete | 2011-07-26 | Ready | 2012-01-05
BB28A14 | MINERAL | MINERAL COUNTY ALTERNATIVE SCHOOL | FR | K12 | FTX1438A2DN | 457 |  | 2011-07-28 |  | fiber and router needed | K-12 | 2011-09-13 | Y | Y | 18052.1 | N |  | 2011-09-16 | Y | 2445 | 2445 | 2012-01-01 | Complete | 2011-11-29 | N | No Build Required |  |  | 2011-11-29 | Complete | 2011-11-29 | Complete | 2011-07-28 | Ready | 2012-01-05
BB28A15 | MINERAL | NEW CREEK PRIMARY SCHOOL | FR | K12 | FTX1438A2CG | 458 |  | 2011-07-26 |  | fiber and router needed | K-12 | 2011-09-13 | Y | Y | 94281.4 | Y | 2011-09-13 | 2011-11-10 | Y | 12690 | 12690 | 2012-01-01 | Complete | 2011-12-21 | N | No Build Required |  |  | 2011-12-21 | Complete | 2011-12-21 | Complete | 2011-07-26 | Ready | 2012-01-05
BB28A16 | MINERAL | WILEY FORD PRIMARY SCHOOL | FR | K12 | FTX1439AH12 | 459 |  | 2011-07-27 |  | fiber and router needed | K-12 | 2011-09-13 | Y | Y | 29909.04 | N |  | 2011-11-09 | Y | 1040 | 1040 | 2012-01-01 | Complete | 2011-12-30 | N | No Build Required |  |  | 2012-01-03 | Complete | 2012-01-03 | Complete | 2011-07-27 | Ready | 2012-01-05
BB28A17 | MINERAL | WVIEP - BURLINGTON CENTER | FR | K12 | FTX1438A2E0 | 460 |  | 2011-07-26 |  | fiber and router needed | K-12 | 2011-05-16 | Y | Y | 9768.7 | Y | 2011-06-15 | 2011-05-19 | Y | 1195 | 1195 | 2011-12-01 | Complete | 2011-11-18 | N | No Build Required |  |  | 2011-11-18 | Complete | 2011-11-18 | Complete | 2011-07-26 | Ready | 2012-01-05
BB28A18 | MINERAL | Fort Ashby Public Library | FR | LIB | FTX1439AJW6 | 820 |  | 2012-07-26 |  | fiber and router needed | WVNET | 2011-05-16 | Y | Y | 14244.7 | Y | 2011-06-15 | 2011-05-19 | Y | 1795 | 1795 | 2012-01-01 | Complete | 2011-12-01 | N | No Build Required |  |  | 2011-12-05 | Complete | 2011-12-05 | Complete | 2012-07-26 | Ready | 2012-08-10
BB28A19 | MINERAL | Keyser-Mineral County Public Library | FR | LIB | FTX1439A172 | 827 |  | 2012-07-25 |  | fiber and router needed | WVNET | 2011-09-13 | Y | Y | 11199.2 | N |  | 2011-11-09 | Y | 1420 | 1420 | 2012-06-01 | Complete | 2011-11-18 | Y | Complete |  | 2012-02-16 | 2012-01-19 | Complete | 2012-01-19 | Complete | 2012-07-25 | Ready | 2012-08-03 | *FBO Not Required - Locations have already completed the FBO. Frontier Pulled to Demarc. - 12/20/11*
BB28A20 | MINERAL | Piedmont Public Library | FR | LIB | FTX1439AJY8 | 813 |  | 2012-07-25 |  | fiber and router needed | WVNET | 2011-09-13 | Y | Y | 5866 | Y | 2011-09-13 | 2011-11-09 | Y | 642 | 642 | 2012-01-01 | Complete | 2011-12-30 | Y | Complete |  | 2012-02-16 | 2012-01-19 | Complete | 2012-01-19 | Complete | 2012-07-25 | Ready | 2012-08-03 | *FBO Not Required - Locations have already completed the FBO to complete by owner to Dmarc. - 1/8/12* *FBO Update - Trip Charges Declined due to a notification of FBO Cancellation and contractor proceeded to attempt an assesment of location.2/27/12*
BB28A21 | MINERAL | Burlington Public Library | FR | LIB | FTX1439A155 | 819 |  | 2012-07-26 |  | fiber and router needed | WVNET | 2011-05-16 | Y | Y | 6699 | Y | 2011-06-15 | 5/19/11; 7/5/2011 | Y | 850 | 850 | 2012-06-01 | Complete | 2011-11-21 | N | No Build Required |  |  | 2011-11-23 | Complete | 2011-11-23 | Complete | 2012-07-26 | Ready | 2012-08-10
BB28A22 | MINERAL | 911 Center | FR | PSAP | FTX1436AJTG | 1363 |  | 2012-03-01 |  | fiber and router needed |  | 2011-09-13 | Y | Y | 5071.1 | N |  | 2011-09-16 | Y | 675 | 675 | 2012-06-01 | Complete | 2011-12-20 | N | No Build Required |  |  | 2011-12-20 | Complete | 2011-12-20 | Complete | 2012-03-01 | Ready | 2012-03-08
BB28A23 | MINERAL | Keyser Mineral - Troop 2 State Police | FR | SP | FTX1439A243 | 1048 |  | 2011-12-14 |  | fiber and router needed | State Police | 2011-09-18 | Y | Y | 97684.98 | N |  | 2011-11-10 | Y | 13113 | 13113 | 2012-06-01 | Complete | 2012-01-19 | N | No Build Required |  |  | 2012-01-19 | Complete | 2012-01-19 | Complete | 2011-12-14 | Ready | 2012-01-20
BB28A24 | MINERAL | BCI Fort Ashby Mineral County State Police | FR | SP | FTX1439A25J | 1078 |  | 2011-12-15 |  | fiber and router needed | State Police | 2011-05-16 | Y | Y | 90374 | Y | 2011-06-15 | 5/19/11; 7/5/2011 | Y | 12000 | 12000 | 2012-06-01 | Complete | 2012-01-19 | N | No Build Required |  |  | 2012-01-19 | Complete | 2012-01-19 | Complete | 2011-12-15 | Ready | 2012-01-20
BB28A01 | MINERAL | Mineral County Courthouse | FR | CHOUSE | FTX1441AJ02 | 551 | Delivered and Installed by Tech | 2012-07-20 |  | fiber and router needed | WVNET | 2011-09-13 | Y | Y | 4932 | N |  | 2011-11-09 | Y | 580 | 580 | 2011-12-01 | Complete | 2011-11-14 | Y | Complete |  | 2012-01-23 | 2012-01-20 | Complete | 2012-01-20 | Complete | 2012-07-20 | Ready | 2012-08-03 | *FBO Not Required - Frontier used existing conduit to complete to the Dmarc - 01/23/12*
BB29A02 | MINGO | DINGESS ELEMENTARY SCHOOL | FR | K12 | FTX1442AKEG | 78 |  | 2011-06-02 |  | fiber and router needed | K-12 | 2011-11-14 | Y | Y | 268258.39 | Y | 11/17/2011; 1/30/2012; 4/24/2012; 5/21/12 | 2012-03-29 | Y | 39979 | 39979 | 2012-08-01 | Complete | 2012-08-11 | Y | TBD |  |  |  | TBD |  | Complete | 2011-06-02 | TBD
BB29A03 | MINGO | Mingo County Public Library | FR | LIB | FTX1439A173 | 764 |  | 2012-04-23 |  | fiber and router needed | WVNET | 2011-11-16 | Y | Y | 5719.38 | N |  | 2012-02-24 | Y | 780 | 780 | 2012-08-01 | Complete | 2012-03-09 | N | No Build Required |  | 2012-03-15 | 2012-03-15 | Complete | 2012-03-15 | Complete | 2012-04-23 | Ready | 2012-04-27
BB29A04 | MINGO | Gilbert Public Library | FR | LIB | FTX1439A158 | 765 |  | 2012-04-23 |  | fiber and router needed | WVNET | 2011-11-14 | Y | Y | 14076.84 | N |  | 2012-03-29 | Y | 749 | 749 | 2012-08-01 | Complete | 2012-05-01 | Y | Complete |  | 2012-07-03 | 2012-05-21 | Complete | 2012-05-21 | Complete | 2012-04-23 | Ready | 2012-05-25 | *FBO Cancelled - Network Side contractor notified us the location was completed to the Demarc. 5/25/12*
BB29A05 | MINGO | Kermit Public Library | FR | LIB | FTX1439A174 | 740 |  | 2012-02-23 |  | fiber and router needed | WVNET | 2011-12-07 | Y | Y | 32793.3 | N |  | 2012-03-29 | Y | 2362 | 2362 | 2012-08-01 | Complete | 2012-04-24 | N | No Build Required |  |  | 2012-04-24 | Complete | 2012-04-24 | Complete | 2012-02-23 | Ready | 2012-04-27
BB29A06 | MINGO | Matewan Public Library | FR | LIB | FTX1439AJVA | 753 |  | 2012-03-27 |  | fiber and router needed | WVNET | 2011-11-14 | Y | Y | 12930.13 | N |  | 2012-02-24 | Y | 974 | 974 | 2012-09-01 | Complete | 2012-03-11 | N | No Build Required |  | 2012-03-15 | 2012-03-15 | Complete | 2012-03-15 | Complete | 2012-03-27 | Ready | 2012-04-05
BB29A07 | MINGO | Mingo County 9-1-1 | FR | PSAP | FTX1436AJV5 | 1348 |  | 2012-01-31 |  | fiber and router needed |  | 2011-11-17 | Y | Y | 90795.7 | N |  | 2012-03-29 | Y | 10696 | 10696 | 2012-09-01 | Complete | 2012-05-20 | N | No Build Required |  |  | 2012-05-20 | Complete | 2012-05-20 | Complete | 2012-01-31 | Ready | 2012-05-25
BB29A08 | MINGO | Gilbert / Mingo - Troop 5 State Police | FR | SP | FTX1439A23N | 1038 |  | 2012-01-13 |  | fiber and router needed | State Police | 2011-11-14 | Y | Y | 12582.77 | N |  | 2011-11-16 | Y | 319 | 319 | 2012-09-01 | Complete | 2011-11-28 | N | No Build Required |  |  | 2012-01-24 | Complete | 2012-01-24 | Complete | 2012-01-13 | Ready | 2012-01-26
BB29A09 | MINGO | Williamson / Mingo - Troop 5 State Police | FR | SP | FTX1439A242 | 1047 |  | 2012-01-13 |  | fiber and router needed | State Police | 2011-11-10 | Y | Y | 6376.02 | N |  | 2011-11-16 | Y | 319ft | Included | 2012-09-01 | Complete | 2012-04-10 | N | No Build Required |  |  | 2012-04-10 | Complete | 2012-04-10 | Complete | 2012-01-13 | Ready | 2012-04-13
BB29A10 | MINGO | Gilbert Medical Center | FO | TMED | [5 empty] | POC - 'Fiber Only | ? | 2011-12-09 | Y | Y | 19287.54 | N |  | 2012-03-26 | Y | 880 | 880 | 2012-09-01 | 2012-09-01 |  | N | No Build Required |  |  | 2012-06-01 | Complete | 2012-06-01 | N/A | N/A | Ready |  | *Fiber Update - Frontier was instructed to stop all build due to CAI claiming to receive funding from the Telehealth alliance - Nick Patel - 6/1/12* *Router Update - Router was retrieved from this lcoation due to the CAI claiming to be members of the Telehealth alliance*
BB29A11 | MINGO | Williamson Memorial Hospital | RO | TMED | FTX1444A05D | 931 | Delivered by Courier | 2012-07-18 |  | per FTR; site already has fiber- router only | ? |  | N | N/A |  |  |  |  | N/A |  | 0 |  | Complete |  |  | No Build Required |  |  | N/A | Complete | N/A | Complete | 2012-07-18 | Ready | 2012-08-03
BB29A12 | MINGO | Valley Health - Stepptown | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB29A01 | MINGO | Mingo County Courthouse | FR | CHOUSE | FTX1441A0Q5 |  |  |  |  | fiber and router needed | WVNET | 2011-11-15 | Y | Y | 11560.38 | N |  | 2012-03-29 | Y | 1631 | 1631 | 2012-08-01 | Complete | 2012-04-09 | N | No Build Required |  |  | 2012-04-09 | Complete | 2012-04-09 | TBD |  | Waiting on Router
BB30A02 | MONONGALIA | ALTERNATIVE LEARNING CENTER | FR | K12 | FTX1442A2C2 | 362 |  | 2011-08-25 |  | fiber and router needed | K-12 | 2011-04-15 | Y | Y | 18530.64 | N |  | 2011-09-26 | Y | 2484 | 2484 | 2012-02-01 | Complete | 2011-10-28 | Y | Complete |  | 2012-02-17 |  | TBD |  | Complete | 2011-08-25 | TBD |  | *FBO Not Required - Location was completed to Dmarc when went to site. Gudenkauf - Trip Charge will be genetrated - Gudenkauf Corp. - 2/15/2012*
BB30A03 | MONONGALIA | CLAY-BATTELLE HIGH SCHOOL | FR | K12 | FTX1442A2CJ | 363 |  | 2011-08-24 |  | fiber and router needed | K-12 | 2011-04-15 | Y | Y | 15755.52 | N |  | 2011-05-26 | Y | 2112 | 2112 | 2012-02-01 | Complete | 2011-10-14 | Y | Complete |  | 2012-02-10 | 2012-04-12 | Complete | 2012-04-12 | Complete | 2011-08-24 | Ready | 2012-04-19 | *FBO Not Required - pulled to Demarc - Dave Robinson & Rick Singer (Gudenkauf Corporation) - Will Be Charged for Trip -2/8/12*
BB30A04 | MONONGALIA | DAYBROOK ELEMENTARY | FR | K12 | FTX1443AK4Q | 364 |  | 2011-08-31 |  | fiber and router needed | K-12 | 2011-04-15 | Y | Y | 236295 | N |  | 2012-01-17 | Y | 31675 | 31675 | 2012-02-01 | Complete | 2012-08-10 | N | No Build Required |  |  | 2012-08-27 | Complete | 2012-08-27 | Complete | 2011-08-31 | Ready | 2012-08-31 | *FBO Not Required - Location was completed to Dmarc when went to site. Gudenkauf - Trip Charge will be genetrated - 2/15/2012*
BB30A05 | MONONGALIA | EASTON ELEMENTARY SCHOOL | RO | K12 | FTX1442A1YV | 365 |  | 2011-08-30 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-08-30 | Ready | 2012-01-05
BB30A06 | MONONGALIA | MASON-DIXON ELEMENTARY SCHOOL | FR | K12 | FTX1442A1ZD | 366 |  | 2011-08-24 |  | fiber and router needed | K-12 | 2011-04-15 | Y | Y | 22066.68 | N |  | 2011-05-26 | Y | 2958 | 2958 | 2012-02-01 | Complete | 2011-10-14 | Y | Complete |  | 2012-02-10 | 2012-04-12 | Complete | 2012-04-12 | Complete | 2011-08-24 | Ready | 2012-04-19 | *FBO Not Required - Fiber pulled to Dmarc - Dave Robinson & Rick Singer (Gudenkauf Corporation) - Will Be Charged for Trip -2/8/12*
BB30A07 | MONONGALIA | MYLAN PARK ELEMENTARY SCHOOL | FR | K12 | FTX1442A1ZP | 367 |  | 2011-08-25 |  | fiber and router needed | K-12 | 2011-04-15 | Y | Y | 93652.84 | N |  | 2011-09-26 | Y | 12554 | 12554 | 2012-02-01 | 2012-02-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2011-08-25 | TBD
BB30A08 | MONONGALIA | RIDGEDALE ELEMENTARY | RO | K12 | FTX1442A2CC | 368 |  | 2011-08-30 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-08-30 | Ready | 2012-01-05
BB30A09 | MONONGALIA | SUNCREST PRIMARY SCHOOL | RO | K12 | FTX1442A1XD | 369 |  | 2011-08-29 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-08-29 | Ready | 2012-01-05
BB30A10 | MONONGALIA | WOODBURN ELEMENTARY | RO | K12 | FTX1442A1TF | 370 |  | 2011-08-29 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-08-29 | Ready | 2012-01-05
BB30A11 | MONONGALIA | Cheat Area Public Library | FR | LIB | FTX1439AJYG | 690 |  | 2011-11-29 |  | fiber and router needed | WVNET | 2011-04-15 | Y | Y | 1865 | N |  | 2011-09-26 | Y | 250 | 250 | 2011-12-01 | Complete | 2011-11-06 | Y | Complete |  | 2012-02-17 | 2012-02-16 | Complete | 2012-02-16 | Complete | 2011-11-29 | Ready | 2012-02-23 | *FBO Not Required - Location was completed to Dmarc when went to site. Gudenkauf - Trip Charge will be genetrated - Gudenkauf Corp. - 2/15/2012*
BB30A12 | MONONGALIA | Clinton District Public Library | FR | LIB | FTX1439A14B | 798 |  | 2012-06-04 |  | fiber and router needed | WVNET | 2011-04-15 | Y | Y | 8638.68 | N |  | 2011-05-26 | Y | 1158 | 1158 | 2012-02-01 | Complete | 2011-08-02 | Y | Complete | 2012-03-23 | 2012-03-02 | 2012-05-10 | Complete | 2012-05-10 | Complete | 2012-06-04 | Ready | 2012-06-08 | *FBO Revised - Revised Date of Completion to 3/20/12* *FBO On Hold - Update - Mark Mckenzie - Frontier does not have enough space to set up a Demarc. Recommend Sending Lance Host out to assess the situation - 3/26/12* *FBO Update - Lance Host - completed his assessment. LIB has mounted backboard in the maintenance room as a Demarc. Will be discussed at this weeks Tiger team - Nick Patel - 4/2/12* *FBO Hold Update - Mark McKenzie will be sending a tech out to this location to let us know if the members of his team can complete the termination of the Fiber at the Demarc. - 4/3/12* *FBO Update - 5/22/12 - Fiber Completed to the Demarc - Mark McKenzie - Tiger Team Meeting.
BB30A13 | MONONGALIA | Morgantown Public Library | FR | LIB | FTX1439A15M | 673 |  | 2011-09-23 |  |  | WVNET | 2011-04-15 | Y | Y | 4849 | N |  | 2011-05-26 | Y | 650 | 650 | 2012-09-01 | Complete | 2011-09-06 | N | No Build Required |  |  | 2011-09-14 | Complete | 2011-09-14 | Complete | 2011-09-23 | Ready | 2012-01-05
BB30A14 | MONONGALIA | Clay Battelle Public Library | FR | LIB | FTX1439AJYD | 732 |  | 2012-02-08 |  | fiber and router needed | WVNET | 2011-05-16 | Y | Y | 7833 | N |  | 2011-05-26 | Y | 1050 | 1050 | 2012-02-01 | Complete | 2011-10-14 | Y | Complete |  | 2012-03-14 | 2012-08-27 | Complete | 2012-08-27 | Complete | 2012-02-08 | Ready | 2012-08-31 | *FBO No Longer Required - Clay-Battelle Library (BB30A14) FTR# 1203505 is ready for Frontier. The cable was placed into the building by a private contractor hired by Sandra Throckmorton (Library Supv.) The fiber has been strapped directly to the building exterior and ran inside to the equipment room. The remaining slack is coiled inside the equipment room and still needs terminated. FYI.. Sandra’s phone number is: 304-432-8531. Dave will be forwarding an invoice for the trip charge in the morning. Thanks Nick. Rick Singer / Gudenkauf Corp. - 3/7/12*
BB30A15 | MONONGALIA | MECCA 911 | FR | PSAP | FTX1436AJV1 | 1389 |  | 2012-01-30 |  | fiber and router needed |  | 2011-04-15 | Y | Y | 22745.54 | N |  | 2011-05-26 | Y | 3049 | 3049 | 2012-02-01 | Complete | 2011-10-03 | Y | Complete | 2012-03-22 | 2012-03-02 | 2012-04-12 | Complete | 2012-04-12 | Complete | 2012-01-30 | Ready | 2012-04-19 | *FBO Revised - Revised Date of Completion to 2/27/12* *FBO On Hold - State says FBO complete on 3/12. Conduit is not placed into building at proper location. Needs to go back to state complete properly - Rob Hugart - Frontier - 3/30/12* *4/2/12 - Spoke to POC - Jason Rice - Stated the Fiber location is in correct place. Ready for termination, testing and provisioning. - Nick Patel - 4/2/12*
BB30A16 | MONONGALIA | Morgantown Monongalia - Troop 1 State Police | FR | SP | FTX1439A26S | 1098 |  | 2011-12-14 |  | fiber and router needed | State Police | 2011-04-15 | Y | Y | 24618 | N |  | 2012-01-17 | Y | 3300 | 3300 | 2012-02-01 | Complete | 2012-01-31 | N | No Build Required |  |  | 2012-01-31 | Complete | 2012-01-31 | Complete | 2011-12-14 | Ready | 2012-02-10
BB30A17 | MONONGALIA | Clay-Battelle Community Health Services Assn | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB30A18 | MONONGALIA | WVU Children's Hospital | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB30A19 | MONONGALIA | Marketing | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB30A20 | MONONGALIA | MIMG Lab | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB30A21 | MONONGALIA | Mon Kids | FR | TMED | FTX1436A1TQ | 886 | 1ZX560410300480329 | 2011-12-12 |  | fiber and router needed | ? | 2011-08-02 | Y | Y | 5230 | N |  | 2011-09-26 | Y | 550 | 550 | 2011-12-01 | Complete | 2011-10-27 | Y | Complete |  | 2012-02-17 | 2012-03-12 | Complete | 2012-03-12 | Complete | 2011-12-12 | Ready | 2012-03-16 | *FBO Not Required - Location was completed to Dmarc when went to site. Gudenkauf - Trip Charge will be genetrated - Gudenkauf Corp. - 2/15/2012*
BB30A22 | MONONGALIA | HHP | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB30A23 | MONONGALIA | Hospice | RO | TMED | FTX1443A292 | 919 | 1ZX560410300507952 | 2012-03-21 |  | PER FTR ON 10/03/11, THIS CAI ALREADY HAS FIBER AT LOCATION. | ? |  | N | N/A |  |  |  |  | N/A |  | 0 |  | Complete |  |  | No Build Required |  |  |  | Complete | N/A | Complete | 2012-03-21 | Ready | 2012-03-23 | *Router Update - Shipped to ATTN: IT DEPT, Monongalia Medical Hospital, 1200 JD Anderson Drive, Morgantown, WV
BB30A24 | MONONGALIA | RHA (REGIONAL HEALTHCARE ASSOCIATES) | RO | TMED |  |  | Courier Delivery | 2012-07-10 |  | per FTR; site already has fiber- router only | ? |  | N | N/A |  |  |  |  | N/A |  | 0 |  | Complete |  |  | No Build Required |  |  |  | Complete | N/A | Complete | 2012-07-10 | Ready | 2012-07-13
BB30A25 | MONONGALIA | Bio Med | RO | TMED | FTX1443AK9F | 918 | 1ZX560410300507952 | 2012-03-21 |  | PER FTR ON 10/03/11, THIS CAI ALREADY HAS FIBER AT LOCATION. | ? |  | N | N/A |  |  |  |  | N/A |  | 0 |  | Complete |  |  | No Build Required |  |  |  | Complete | N/A | Complete | 2012-03-21 | Ready | 2012-03-23 | *Router Update - Shipped to ATTN: IT DEPT, Monongalia Medical Hospital, 1200 JD Anderson Drive, Morgantown, WV
BB30A26 | MONONGALIA | IT | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB30A27 | MONONGALIA | Mon EMS | RO | TMED | FTX1436A1V5 | 917 | 1ZX560410300507952 | 2012-03-21 |  | PER FTR ON 10/03/11, THIS CAI ALREADY HAS FIBER AT LOCATION. | ? |  | N | N/A |  |  |  |  | N/A |  | 0 |  | Complete |  |  | No Build Required |  |  |  | Complete | N/A | Complete | 2012-03-21 | Ready | 2012-03-23 | *Router Update - Shipped to ATTN: IT DEPT, Monongalia Medical Hospital, 1200 JD Anderson Drive, Morgantown, WV
BB30A28 | MONONGALIA | CT Surgeons | REM | TMED |  |  |  |  | D | PER FTR: SITE MOVED; REFUSED BTOP SERVICES. REMOVED FROM BUILD LIST | ? |  | N | N/A |  |  |  |  | N/A |  | 0 |  | Removed |  |  | Removed |  |  |  | Removed | N/A | N/A | N/A | Removed
BB30A29 | MONONGALIA | ROC | RO | TMED | FTX1444AJ1N | 868 | 1ZX560410300468085 | 2011-10-03 |  | PER FTR ON 10/03/11, THIS CAI ALREADY HAS FIBER AT LOCATION. | ? |  | N | N/A |  |  |  |  | N/A |  | 0 |  | Complete |  |  | No Build Required |  |  |  | Complete | N/A | Complete | 2011-10-03 | Ready | 2012-02-02
BB30A30 | MONONGALIA | Ruby | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB30A31 | MONONGALIA | Sleep Lab | RO | TMED | FTX1444AJ1K | 869 | 1ZX560410300467915 | 2011-10-03 |  | PER FTR ON 10/03/11, THIS CAI ALREADY HAS FIBER AT LOCATION. | ? |  | N | N/A |  |  |  |  | N/A |  | 0 |  | Complete |  |  | No Build Required |  |  |  | Complete | N/A | Complete | 2011-10-03 | Ready | 2012-02-02
BB30A32 | MONONGALIA | Cheat Lake | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB30A33 | MONONGALIA | Scott Ave | RO | TMED | FTX1444A01H | 870 | 1ZX560410300467924 | 2011-10-03 |  | PER FTR ON 10/03/11, THIS CAI ALREADY HAS FIBER AT LOCATION. | ? |  | N | N/A |  |  |  |  | N/A |  | 0 |  | Complete |  |  | No Build Required |  |  |  | Complete | N/A | Complete | 2011-10-03 | Ready | 2012-02-02
BB30A34 | MONONGALIA | Urgent Care | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB30A01 | MONONGALIA | Monongalia County Courthouse | FR | CHOUSE | FTX1441A0PW | 578 | Delivered and Installed by Tech | 2012-08-30 |  | fiber and router needed | WVNET | 2011-04-15 | Y | Y | 7527.14 | N |  | 2011-05-26 | Y | 1009 | 1009 | 2012-09-01 | Complete | 2011-08-13 | N | No Build Required |  |  | 2011-09-15 | Complete | 2011-09-15 | Complete | 2012-08-30 | Ready | 2012-09-14
BB31A02 | MONROE | JAMES MONROE HIGH SCHOOL | RO | K12 | FTX1439AH0S | 15 |  | 2011-08-02 |  |  | K-12 |  | N | N/A |  |  |  |  | N/A |  | 0 | 2012-09-01 | Complete |  | N | No Build Required |  |  |  | Complete | N/A | Complete | 2011-08-02 | Ready | 2012-01-27
BB31A03 | MONROE | MONROE VOC-TECH | RO | K12 | FTX1438A2DR | 16 |  |  |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A |  | 0 | 2012-09-01 | Complete |  | N | No Build Required |  |  |  | Complete | N/A | TBD |  | Waiting on Router | N/A
BB31A04 | MONROE | MOUNTAIN VIEW ELEM/MIDDLE SCHOOL | RO | K12 | FTX1439AH13 | 17 |  | 2011-07-28 |  |  | K-12 |  | N | N/A |  |  |  |  | N/A |  | 0 | 2012-09-01 | Complete |  | N | No Build Required |  |  |  | Complete | N/A | Complete | 2011-07-28 | Ready | 2012-01-27
BB31A05 | MONROE | PETERSTOWN ELEMENTARY | RO | K12 | FTX1438A2D1 | 18 |  | 2011-08-02 |  |  | K-12 |  | N | N/A |  |  |  |  | N/A |  | 0 | 2012-09-01 | Complete |  | N | No Build Required |  |  |  | Complete | N/A | Complete | 2011-08-02 | Ready | 2012-01-27
BB31A06 | MONROE | PETERSTOWN MIDDLE SCHOOL | RO | K12 | FTX1439AH09 | 19 |  | 2011-07-28 |  |  | K-12 |  | N | N/A |  |  |  |  | N/A |  | 0 | 2012-09-01 | Complete |  | N | No Build Required |  |  |  | Complete | N/A | Complete | 2011-07-28 | Ready | 2012-01-27
BB31A07 | MONROE | Peterstown Public Library | FR | LIB | FTX1439A15B | 785 |  | 2012-05-18 |  | fiber and router needed | WVNET | 2011-12-01 | Y | Y | $18,798.48 ($25,291.77) | Y | 2011-12-02 | 2012-05-02 | Y | 2688 | 2688 | 2012-09-01 | Complete | 2012-06-18 | Y | Scheduled | 2012-08-24 |  |  | TBD |  | Complete | 2012-05-18 | TBD |  | * FBO Notified - Contractor notified WVOT and Frontier that FBO is required at this site. Frontier confirmed the contractor has the network side of build. 6/18/12* *FBO Hold - Pending EA Review - 7/13/12* *FBO Update - EA Approved - 7/24/12*
BB31A08 | MONROE | Monroe County Public Library | FR | LIB | FTX1439A15Y | 784 |  | 2012-05-25 |  | fiber and router needed | WVNET | 2011-11-27 | Y | Y | 9378.9 | N |  | 2012-05-02 | Y | 1277 | 1277 | 2012-09-01 | Complete | 2012-09-12 | N | No Build Required |  |  | 2012-09-12 | Complete | 2012-09-12 | Complete | 2012-05-25 | Ready | 2012-09-14
BB31A09 | MONROE | Monroe County 911 | FR | PSAP | FTX1436AJUW | 1349 |  | 2012-02-22 |  | fiber and router needed |  | 2011-11-27 | Y | Y | 5977.96 | N |  | 2011-12-08 | Y | 400 | 400 | 2012-09-01 | Complete | 2012-01-30 | N | No Build Required |  |  | 2012-01-30 | Complete | 2012-01-30 | Complete | 2012-02-22 | Ready | 2012-02-24
BB31A10 | MONROE | Union Monroe - Troop 6 State Police | FR | SP | FTX1439A252 | 1070 |  | 2012-01-24 |  | fiber and router needed | State Police | 2011-11-27 | Y | Y | 12530.97 | N |  | 2012-05-02 | Y | 2065 | 2065 | 2012-09-01 | Complete | 2012-09-17 | N | No Build Required |  |  | 2012-09-17 | Complete | 2012-09-17 | Complete | 2012-01-24 | Ready | 2012-09-21
BB31A11 | MONROE | James Monroe High School Wellness Center | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB31A12 | MONROE | Peterstown Elementary/Middle School Health Center | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB31A13 | MONROE | Monroe County Health Center | FO | TMED | [5 empty] | POC; Fiber Only | ? | 2012-04-09 | Y | Y | 107499.45 | N |  | 2012-05-02 | Y | 16437 | 16437 | 2012-09-01 | 2012-09-01 |  | N | No Build Required |  |  |  | N/A | N/A | N/A | N/A | Ready |  | *Fiber Update - Frontier has been instructed to stop all build to this location due the the CAI claiming to receive funding from the Telehealth Alliance. Nick Patel - 6/8/12*
BB31A14 | MONROE | Monroe County Health Center | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB31A15 | MONROE | Mountain View Elementary/Middle School | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB31A01 | MONROE | Monroe County Courthouse | FR | CHOUSE | FTX1441A0PV |  |  |  |  | fiber and router needed | WVNET | 2011-11-27 | Y | Y | 28760.35 | N |  | 2011-12-08 | Y | 2089 | 2089 | 2012-09-01 | Complete | 2012-01-30 | N | No Build Required |  |  | 2012-01-30 | Complete | 2012-01-30 | TBD |  | Waiting on Router
BB32A02 | MORGAN | *PAW PAW ELEMENTARY & HIGH SCHOOLS | FR | K12 | FTX1438A2C0 | 461 |  | 2011-06-28 |  | fiber and router needed | K-12 | 2011-06-13 | Y | Y | 8687 | N |  | 2011-07-05 | Y | 1050 | 1050 | 2012-02-02 | Complete | 2012-01-19 | Y | Complete | 2012-02-07 | 2012-02-13 | 2012-02-21 | Complete | 2012-02-21 | Complete | 2011-06-28 | Ready | 2012-02-23
BB32A03 | MORGAN | BERKELEY SPRINGS HIGH SCHOOL | RO | K12 | FTX1438A2CZ | 462 |  | 2011-06-28 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-06-28 | Ready | 2012-01-05
BB32A04 | MORGAN | GREENWOOD ELEMENTARY SCHOOL | FR | K12 | FTX1439AH0V | 463 |  | 2011-06-28 |  | fiber and router needed | K-12 | 2011-06-13 | Y | Y | 570425.54 | Y | 2011-08-23 | 2011-10-18 | Y | 76749 | 76749 | 2012-02-02 | Complete | 2012-05-29 | N | No Build Required |  |  | 2012-05-29 | Complete | 2012-05-29 | Complete | 2011-06-28 | Ready | 2012-06-08
BB32A05 | MORGAN | PLEASANT VIEW ELEMENTARY SCHOOL | RO | K12 | FTX1439AH10 | 464 |  | 2011-06-29 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-06-29 | Ready | 2012-01-05
BB32A06 | MORGAN | WARM SPRINGS INTERMEDIATE | RO | K12 | FTX1439AH18 | 465 |  | 2011-06-29 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-06-29 | Ready | 2012-01-05
BB32A07 | MORGAN | WARM SPRINGS MIDDLE SCHOOL | RO | K12 | FTX1438A2D4 | 466 |  | 2011-06-29 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-06-29 | Ready | 2012-01-05
BB32A08 | MORGAN | WIDMYER ELEMENTARY | RO | K12 | FTX1438A2CV | 467 |  | 2011-06-28 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-06-28 | Ready | 2012-01-05
BB32A09 | MORGAN | Morgan County Public Library | FR | LIB | FTX1439A16C | 812 |  | 2012-07-17 |  | fiber and router needed | WVNET | 2011-06-13 | Y | Y | 8145.24 | N |  | 2011-07-05 | Y | 994 | 994 | 2012-02-02 | Complete | 2012-01-19 | N | No Build Required |  |  | 2012-01-19 | Complete | 2012-01-19 | Complete | 2012-07-17 | Ready | 2012-08-03
BB32A10 | MORGAN | Paw Paw Public Library | FR | LIB | FTX1439A14V | 822 |  | 2012-07-26 |  | fiber and router needed | WVNET | 2011-06-13 | Y | Y | 17616.62 | Y | (7/25/11); (8/23/11); (8/31/11) | 2011-10-18 | Y | 2247 | 2247 | 2012-02-02 | Complete | 2011-11-17 | N | No Build Required |  |  | 2012-01-20 | Complete | 2012-01-20 | Complete | 2012-07-26 | Ready | 2012-08-03
BB32A11 | MORGAN | Morgan County 911 | FR | PSAP | FTX1436AJTF | 1344 |  | 11/21/2011 |  | fiber and router needed |  | 2011-06-13 | Y | Y | 43085.54 | N |  | 2011-07-05 | Y | 5794 | 5794 | 2012-02-02 | Complete | 2012-01-24 | N | No Build Required |  |  | 2012-01-24 | Complete | 2012-01-24 | Complete | 11/21/2011 | Ready | 2012-02-02 | **ON 1/4/12, WVOT RECEIVED REVISED COPY OF THIS LCR WITH NEW ADDRESS PROVIDED TO GIT. POSTED TO SHAREPOINT FOR REVIEW ON 1/4/12. ON 1/9/12, REVISED COPY WAS APPROVED THROUGH GIT PROCESS AND A COPY IS SAVED ON FILE. THERE WILL NOT BE ANOTHER LCR APPROVAL NOTICE SUBMITTED TO FTR/AGENCIES.
BB32A12 | MORGAN | Berkeley Springs / Morgan - Troop 2 State Police | FR | SP | FTX1439A24P | 1064 |  | 2011-12-13 |  | fiber and router needed | State Police | 2011-06-13 | Y | Y | 23644.48 | N |  | 2011-07-05 | Y | 3188 | 3188 | 2012-02-02 | Complete | 2012-01-24 | N | No Build Required |  |  | 2012-01-24 | Complete | 2012-01-24 | Complete | 2011-12-13 | Ready | 2012-01-26
BB32A13 | MORGAN | Mountaineer Community Health Center, Inc. | FR | TMED | FTX1436A1VL | 862 | 1ZX560410300467960 | 2011-10-26 |  | fiber and router needed | ? | 2011-06-13 | Y | Y | 13357.2 | Y | 2011-09-13 | 2011-09-14 | Y | 1688 | 1688 | 2012-02-02 | Complete | 2012-01-24 | N | No Build Required |  |  | 2012-01-24 | Complete | 2012-01-24 | Complete | 2011-10-26 | Ready | 2012-01-26
BB32A01 | MORGAN | Morgan County Courthouse | FR | CHOUSE | FTX1441A0Q3 | 546 | Delivered and Installed by Tech | 2012-05-31 |  | fiber and router needed | WVNET | 2011-06-13 | Y | Y | 23115.58 | N |  | 2011-07-05 | Y | 3403 | 3403 | 2012-01-01 | Complete | 2011-12-01 | N | No Build Required |  |  | 2011-12-01 | Complete | 2011-12-01 | Complete | 2012-05-31 | Ready | 2012-08-10
BB33A02 | MCDOWELL | McDowell County Correctional Ctr - Welch Facility | FR | CORR | FTX1444A00L | 624 |  |  |  | fiber and router needed | WVOT | 2011-11-21 | Y | Y | 13080.76 | N |  | 2012-05-10 | Y | 352 | 352 | 2012-09-01 | 2012-09-01 |  | N | No Build Required |  |  |  | TBD |  | TBD |  | TBD
BB33A03 | MCDOWELL | Stevens Correctional Center | FR | CORR | FTX1444AJ1H | 625 | 1ZX560410300502340 | 2012-03-02 |  | fiber and router needed | WVOT | 2011-07-26 | Y | Y | 8984.3 | N |  |  | N |  | TBD | 2012-09-01 | Complete | 2012-02-29 | N | No Build Required |  |  | 2012-02-29 | Complete | 2012-02-29 | Complete | 2012-03-02 | Ready | 2012-03-08
BB33A04 | MCDOWELL | Welch Parole Office | FR | CORR | FTX1444AJ1Q | 626 |  |  |  | fiber and router needed | WVOT | 2011-09-30 | Y | Y | 18678.27 | N |  | 2011-10-06 | Y | 1792 | 1792 | 2012-09-01 | Complete | 2012-02-29 | N | No Build Required |  |  | 2012-02-29 | Complete | 2012-02-29 | TBD |  | Waiting on Router
BB33A05 | MCDOWELL | ANAWALT ELEMENTARY SCHOOL | RO | K12 | FTX1439AH1A | 1 |  | 2011-12-13 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 |  | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-12-13 | Ready | 2012-01-05
BB33A06 | MCDOWELL | BIG CREEK HIGH SCHOOL | REM | K12 | FTX1438A2D8 | 2 |  | 2011-12-12 | E | SCHOOL CLOSED- REMOVE FROM LIST | K-12 |  | N | N/A |  |  |  |  | N/A |  | 0 |  | Removed |  |  | Removed |  |  |  | Removed | N/A | N/A | N/A | Removed
BB33A07 | MCDOWELL | FALL RIVER ELEMENTARY SCHOOL | RO | K12 | FTX1438A2D3 | 4 |  | 2011-12-12 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 |  | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-12-12 | Ready | 2012-01-05
BB33A08 | MCDOWELL | IAEGER ELEMENTARY SCHOOL | FR | K12 | FTX1438A2BF | 5 |  | 2011-12-12 |  | fiber and router needed | K-12 | 2011-12-09 | Y | Y | 29974.53 | N |  | 2012-07-13 | Y | 3484 | 3484 | 2012-09-01 | 2012-09-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2011-12-12 | TBD
BB33A09 | MCDOWELL | IAEGER HIGH SCHOOL | REM | K12 | FTX1439AH0J | 6 |  |  | E | SCHOOL CLOSED- REMOVE FROM LIST | K-12 |  | N | N/A |  |  |  |  | N/A |  | 0 |  | Removed |  |  | Removed |  |  |  | Removed | N/A | N/A | N/A | Removed
BB33A10 | MCDOWELL | KIMBALL ELEMENTARY SCHOOL | RO | K12 | FTX1439AH1J | 7 |  | 2011-12-14 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 |  | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-12-14 | Ready | 2012-01-05
BB33A11 | MCDOWELL | MCDOWELL COUNTY VO-TECH CENTER | RO | K12 | FTX1439AH17 | 8 |  | 2011-08-26 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 |  | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-08-26 | Ready | 2012-01-05
BB33A12 | MCDOWELL | MOUNT VIEW HIGH SCHOOL | RO | K12 | FTX1438A2BX | 9 |  | 2011-12-14 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 |  | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-12-14 | Ready | 2012-01-05
BB33A13 | MCDOWELL | PHOENIX CENTER | FR | K12 | FTX1439AH0K | 10 |  | 2011-12-15 |  | fiber and router needed | K-12 | 2011-10-28 | Y | Y | 13467.13 | N |  | 2011-11-07 | Y | 676 | 676 | 2012-09-01 | Complete | 2012-03-02 | N | No Build Required |  |  | 2012-03-05 | Complete | 2012-03-05 | Complete | 2011-12-15 | Ready | 2012-03-08
BB33A14 | MCDOWELL | SANDY RIVER MIDDLE SCHOOL | FR | K12 | FTX1438A2CW | 11 |  | 2011-12-12 |  | fiber and router needed | K-12 | 2011-12-01 | Y | Y | 9652.35 | N |  | 2012-07-13 | Y | 1067 | 1067 | 2012-09-01 | Complete | 2012-08-27 | N | No Build Required |  | 2012-09-20 | 2012-08-27 | Complete | 2012-08-27 | Complete | 2011-12-12 | Ready | 2012-08-31
BB33A15 | MCDOWELL | SOUTHSIDE K-8 | FR | K12 | FTX1438A2BZ | 12 |  | 2011-08-26 |  | fiber and router needed | K-12 | 2012-04-13 | Y | Y | 441178.9 | Y | 4/25/2012; 4/27/2012 |  | N |  | TBD | 2012-09-01 | 2012-09-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2011-08-26 | TBD
BB33A16 | MCDOWELL | WELCH ELEMENTARY SCHOOL | RO | K12 | FTX1438A2C2 | 13 |  | 2011-12-15 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-12-15 | Ready | 2012-01-05
BB33A17 | MCDOWELL | Bradshaw Public Library | FR | LIB | FTX1439AJYB |  |  |  |  | fiber and router needed | WVNET | 2011-12-19 | Y | Y | 6673.7 | N |  | 2012-07-13 | Y | 362 | 362 | 2012-09-01 | 2012-09-01 |  | N | No Build Required |  |  |  | TBD |  | TBD |  | TBD
BB33A18 | MCDOWELL | Iaeger Public Library | FR | LIB | FTX1439A16F |  |  |  |  | fiber and router needed | WVNET | 2011-12-01 | Y | Y | 7973.06 | Y | 2011-12-09 | 2012-07-13 | Y | 260 | 260 | 2012-09-01 | Complete | 2012-08-30 | Y | TBD |  |  |  | TBD |  | TBD |  | TBD
BB33A19 | MCDOWELL | Northfork Public Library | FR | LIB | FTX1439A16Q | 678 |  | 2011-10-18 |  | fiber and router needed | WVNET | 2011-10-07 | Y | Y | 23899.74 | N |  | 2012-07-13 | Y | 2430 | 2430 | 2012-09-01 | 2012-09-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2011-10-18 | TBD
BB33A20 | MCDOWELL | McDowell Public Library | FR | LIB | FTX1439A15G | 680 |  | 2012-02-15 |  | fiber and router needed | WVNET | 2011-10-28 | Y | Y | 28044.72 | N |  | 2011-11-07 | Y | 1240 | 1240 | 2012-09-01 | Complete | 2012-03-01 | N | No Build Required |  |  | 2012-03-05 | Complete | 2012-03-05 | Complete | 2012-02-15 | Ready | 2012-03-08
BB33A21 | MCDOWELL | War Public Library | FR | LIB | FTX1439AJWB |  |  |  |  | fiber and router needed | WVNET | 2012-04-26 | Y | Y | 42124 | N |  | 2012-07-13 | Y | 3194 | 3194 | 2012-09-01 | 2012-09-01 |  | N | No Build Required |  |  |  | TBD |  | TBD |  | TBD
BB33A22 | MCDOWELL | Emergency Comm Center | FR | PSAP | FTX1436AJUQ | 1346 |  | 2011-12-20 |  | fiber and router needed |  | 2011-10-07 | Y | Y | 13990.34 | N |  | 2011-10-18 | Y | 100 | 100 | 2012-06-01 | Complete | 2012-01-18 | N | No Build Required |  |  | 2012-01-18 | Complete | 2012-01-18 | Complete | 2011-12-20 | Ready | 2012-02-24
BB33A23 | MCDOWELL | Welch / McDowell - Troop 6 State Police | FR | SP | FTX1439A23K | 1035 |  | 2012-01-05 |  | fiber and router needed | State Police | 2011-09-23 | Y | Y | 16110.37 | N |  | 2011-10-06 | Y | 1461 | 1461 | 2012-06-01 | Complete | 2012-02-29 | N | No Build Required |  |  | 2012-02-29 | Complete | 2012-02-29 | Complete | 2012-01-05 | Ready | 2012-03-02
BB33A24 | MCDOWELL | Welch Community Hospital | FR | TMED | FTX1436A1S6 | 889 | 1ZX560410300481793 | 2011-11-21 |  | fiber and router needed | ? | 2011-11-02 | Y | Y | 15598.61 | N |  | 2011-11-09 | Y | 1864 | 1864 | 2012-06-01 | Complete | 2012-03-08 | N | No Build Required |  |  | 2012-03-08 | Complete | 2012-03-08 | Complete | 2011-11-21 | Ready | 2012-03-21
BB33A25 | MCDOWELL | Tug River Health Association, Inc. | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB33A26 | MCDOWELL | Big Creek HS/Iaeger HS Health Center of Tug River | REM | TMED |  |  |  |  | D | SITE CLOSED: REMOVE FROM BUILD/ROUTER LIST | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB33A27 | MCDOWELL | Tugriver Health Clinic Northfork | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A |  | 0 |  | Removed |  |  | Removed |  |  |  | Removed | N/A | N/A | N/A | Removed
BB33A28 | MCDOWELL | Catterson Health Center | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB33A29 | MCDOWELL | Tugriver Mt. View Health Center | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB33A30 | MCDOWELL | Tug River Total Fitness | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A |  | 0 |  | Removed |  |  | Removed |  |  |  | Removed | N/A | N/A | N/A | Removed
BB34A01 | NICHOLAS | Nicholas County Courthouse | FR | CHOUSE | FTX1441A0QA | 567 | Delivered and Installed by Tech | 2012-08-15 |  | fiber and router needed | WVNET | 2011-10-28 | Y | Y | 10022 | N |  | 2011-11-07 | Y | 750 | 750 | 2012-01-01 | Complete | 2011-12-20 | N | No Build Required |  |  | 2011-12-20 | Complete | 2011-12-20 | Complete | 2012-08-15 | Ready | 2012-09-14
BB34A02 | NICHOLAS | Panther Creek Elementary | FR | K12 | FTX1442A1YU | 216 |  | 2012-03-07 |  | fiber and router needed | K-12 | 2011-10-31 | Y | Y | 23784.39 | N |  | 2011-11-07 | Y | 5878 | 5878 | 2012-01-01 | Complete | 2011-12-20 | N | No Build Required |  |  | 2011-12-20 | Complete | 2011-12-20 | Complete | 2012-03-07 | Ready | 2012-04-12
BB34A03 | NICHOLAS | Beaver Elementary | FR | K12 | FTX1442A207 | 219 |  | 2012-03-02 |  | fiber and router needed | K-12 | 2011-11-01 | Y | Y | 9565.92 | N |  | 2011-11-07 | Y | 1239 | 1239 | 2012-04-01 | Complete | 2012-03-07 | Y | Complete | 2012-07-09 | 2012-07-25 | 2012-08-29 | Complete | 2012-08-29 | Complete | 2012-03-02 | Ready | 2012-08-31
BB34A04 | NICHOLAS | Dixie Elementary | FR | K12 | FTX1439AH0J | 6 |  | 2012-03-02 |  | fiber and router needed | K-12 | 2011-11-02 | Y | Y | 12839.88 | N |  | 2012-04-09 | Y | 778 | 778 | 2012-06-01 | 2012-06-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2012-03-02 | TBD
BB34A05 | NICHOLAS | Glade Creek Elementary | FR | K12 | FTX1438A2DM | 50 |  | 2012-02-29 |  | fiber and router needed | K-12 | 2011-11-01 | Y | Y | 11690.55 | N |  | 2012-04-09 | Y | 1489 | 1489 | 2012-06-01 | Complete | 2012-05-10 | Y | Complete | 2012-07-14 | 2012-07-25 | 2012-08-29 | Complete | 2012-08-29 | Complete | 2012-02-29 | Ready | 2012-08-31
BB34A06 | NICHOLAS | Craigsville Public Library | FR | LIB | FTX1439A15X | 776 |  | 2012-05-01 |  | fiber and router needed | WVNET | 2011-11-02 | Y | Y | 26858.91 | N |  | 2012-04-09 | Y | 2099 | 2099 | 2012-06-01 | 2012-06-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2012-05-01 | TBD
BB34A07 | NICHOLAS | Richwood Public Library | FR | LIB | FTX1439AJWH | 743 |  | 2012-02-06 |  | fiber and router needed | WVNET | 2011-11-01 | Y | Y | 29092.51 | N |  | 2012-04-09 | Y | 2626 | 2626 | 2012-06-01 | Complete | 2012-09-04 | Y | Scheduled | 2012-09-10 |  |  | TBD |  | Complete | 2012-02-06 | TBD |  | * FBO Notified - Contractor notified WVOT and Frontier that FBO is required at this site. Frontier confirmed the contractor has the network side of build. 6/11/12* *FBO Update - Pending EA MAP and GPS Coords before Submitting to the EA Rep for Review. Nick Patel - 8/13/12* *FBO Update - EA Map Recieved - Pending EA Review - 8/13/12*
BB34A08 | NICHOLAS | Summersville Public Library | FR | LIB | FTX1439AJVJ | 742 |  | 2012-02-06 |  | fiber and router needed | WVNET | 2011-10-31 | Y | Y | 18069.91 | N |  | 2012-04-09 | Y | 2194 | 2194 | 2012-06-01 | 2012-06-01 |  | N | No Build Required |  |  | 2012-08-20 | Complete | 2012-08-20 | Complete | 2012-02-06 | Ready | 2012-08-24
BB34A09 | NICHOLAS | Region 4 –Planning and Development Council (Fayette, Greenbrier, Nicholas, Pocahontas, Webster) | FR | PDEV | FTX1436A1TP | 1026 | 1ZX560410300480356 | 2011-11-15 |  | fiber and router needed | ? | 2011-10-31 | Y | Y | 24499.22 | N |  | 2012-04-09 | Y | 3550 | 3550 | 2012-06-01 | Complete | 2012-05-10 | Y | Complete | 2012-06-11 | 2012-07-25 | 2012-08-27 | Complete | 2012-08-27 | Complete | 2011-11-15 | Ready | 2012-08-31
BB34A10 | NICHOLAS | Nicholas County 9-1-1 | FR | PSAP | FTX1436AJV6 | 1357 |  | 2012-02-22 |  | fiber and router needed |  | 2011-10-28 | Y | Y | 7024.53 | N |  | 2012-01-27 | Y | 213 | 213 | 2012-06-01 | Complete | 2012-05-21 | N | No Build Required |  |  | 2012-05-21 | Complete | 2012-05-21 | Complete | 2012-02-22 | Ready | 2012-05-25
BB34A11 | NICHOLAS | Richwood Nicholas - Troop 6 State Police | FR | SP | FTX1439A25X | 1084 |  | 2012-01-24 |  | fiber and router needed | State Police | 2011-10-31 | Y | Y | 9660.92 | N |  | 2012-04-09 | Y | 461 | 461 | 2012-06-01 | Complete | 2012-09-04 | Y | Scheduled | 2012-09-26 |  |  | TBD |  | Complete | 2012-01-24 | TBD
BB34A12 | NICHOLAS | Summersville Nicholas - Troop 6 | FR | SP | FTX1439A25G | 1076 |  | 2012-01-24 |  | fiber and router needed | State Police | 2011-11-09 | Y | Y | 29690.92 | N |  | 2011-11-16 | Y | 5423 | 5423 | 2012-04-01 | Complete | 2012-03-07 | Y | Complete | 2012-03-30 | 2012-06-05 | 2012-09-01 | Complete | 2012-09-01 | Complete | 2012-01-24 | Ready | 2012-09-07
BB34A13 | NICHOLAS | BCI Summersville Nicholas State Police | FR | SP | FTX1439A253 | 1071 |  | 2012-01-24 |  | fiber and router needed | State Police | 2011-12-01 | Y | Y | 7856.01 | N |  | 2011-12-08 | Y | 1058 | 1058 | 2012-06-01 | Complete | 2012-05-24 | Y | Complete | 2012-07-09 | 2012-06-05 |  | TBD |  | Complete | 2012-01-24 | TBD
BB34A14 | NICHOLAS | Central WV Community Clinic | FR | TMED | FTX1436A1W7 | 863 | 1ZX560410300468094 | 2011-10-13 |  | fiber and router needed | ? | 2011-11-01 | Y | Y | 16463.28 | N |  | 2011-11-07 | Y | 4448 | 4448 | 2012-04-01 | Complete | 2012-02-03 | N | No Build Required |  |  | 2012-02-03 | Complete | 2012-02-03 | Complete | 2011-10-13 | Ready | 2012-02-10
BB34A15 | NICHOLAS | NRHA Lisa Elliott Center | FR | TMED | FTX1436A1Y8 | 903 | 1ZX560410300484469 | 2012-01-18 |  | fiber and router needed | ? | 2011-12-01 | Y | Y | 22208.34 | N |  | 2012-04-09 | Y | 2929 | 2929 | 2012-06-01 | Complete | 2012-05-15 | Y | Complete | 2012-07-11 | 2012-07-25 | 2012-09-26 | Complete | 2012-09-26 | Complete | 2012-01-18 | Ready | 2012-09-28
BB34A16 | NICHOLAS | NRHA Richwood Wellness Center | FR | TMED | FTX1436A1TB | 925 | Courier Delivery | 2012-06-25 |  | fiber and router needed | ? | 2011-12-19 | Y | Y | 12887.63 | N |  | 2012-04-09 | Y | 649 | 649 | 2012-06-01 | Complete | 2012-09-04 | Y | TBD |  |  |  | TBD |  | Complete | 2012-06-25 | TBD
BB34A17 | NICHOLAS | NRHA Summersville Wellness Center | FR | TMED | FTX1436A1Y0 | 904 | 1ZX560410300484549 | 2012-01-18 |  | fiber and router needed | ? | 2011-11-09 | Y | Y | 37852.11 | N |  | 2012-04-09 | Y | 6847 | 6847 | 2012-07-01 | Complete | 2012-08-31 | N | No Build Required |  |  | 2012-09-01 | Complete | 2012-09-01 | Complete | 2012-01-18 | Ready | 2012-09-07
BB34A18 | NICHOLAS | Richwood Family Practice | FR | TMED | FTX1436A1UL | 856 | 1ZX560410300456454 | 2011-12-02 |  | fiber and router needed | ? | 2011-10-31 | Y | Y | 31370.59 | N |  | 2012-04-09 | Y | 4349 | 4349 | 2012-07-01 | Complete | 2012-09-04 | Y | TBD |  |  |  | TBD |  | Complete | 2011-12-02 | TBD
BB34A19 | NICHOLAS | Summersville Memorial Hospital - Telecom Room | FR | TMED | FTX1436A1V3 | 857 | 1ZX560410300456427 | 2011-09-21 |  | fiber and router needed | ? | 2011-10-31 | Y | Y | 24324.21 | N |  | 2012-04-09 | Y | 2471 | 2471 | 2012-07-01 | 2012-07-01 |  | N | No Build Required | 2012-09-25 | Y |  | TBD |  | Complete | 2011-09-21 | TBD
BB34A20 | NICHOLAS | Summersville Specialty Clinic - Telecom Room | FR | TMED | FTX1436A1Y7 | 858 | 1ZX560410300456445 | 2011-09-21 |  | fiber and router needed | ? | 2011-11-01 | Y | Y | 12161.16 | N |  | 2011-11-07 | Y | 1657 | 1657 | 2012-04-01 | Complete | 2012-02-03 | Y | Scheduled | 2012-08-20 |  |  | TBD |  | Complete | 2011-09-21 | TBD
BB35A01 | OHIO | Ohio County Courthouse | FR | CHOUSE | FTX1441A0Q1 | 573 | Delivered and Installed by Tech | 2012-06-26 |  | fiber and router needed | WVNET | 2011-10-04 | Y | Y | 8607.4 | Y | 10/17/2011; 10/31/2011 | 2011-11-07 | Y | 390 | 390 | 2011-12-01 | Complete | 2011-11-17 | N | No Build Required |  |  | 2011-12-01 | Complete | 2011-12-01 | Complete | 2012-06-26 | Ready | 2012-08-10
BB35A02 | OHIO | Ohio County Correctional Center | FR | CORR | FTX1444AHKT | 629 |  | 2012-03-08 |  | fiber and router needed | WVOT | 2011-10-04 | Y | Y | SEE BB35A01 | Y | SEE BB35A01 | 2011-11-07 | Y | SEE BB35A01 | Included | 2011-12-01 | Complete | 2011-11-17 | N | No Build Required |  |  | 2011-12-01 | Complete | 2011-12-01 | Complete | 2012-03-08 | Ready | 2012-04-05
BB35A03 | OHIO | Wheeling Parole Office | RO | CORR | FTX1444A005 | 630 |  | 2012-04-18 |  | per FTR; site already has fiber- router only | WVOT |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-04-18 | Ready | 2012-04-27
BB35A04 | OHIO | BETHLEHEM ELEMENTARY SCHOOL | FR | K12 | FTX1442A2SD | 268 |  | 2011-08-11 |  | fiber and router needed | K-12 | 2011-10-04 | Y | Y | 20772.06 | Y | 2011-10-31 | 2011-12-22 | Y | 3757 | 3757 | 2011-12-01 | Complete | 2011-11-16 | Y | Complete | 2012-05-02 | 2012-03-14 | 2012-03-20 | Complete | 2012-03-20 | Complete | 2011-08-11 | Ready | 2012-03-23 | *FBO ON Hold - FTR need to do a re-route on Fiber Path - Gudenkauf - 2/8/12* *FBO - FTR completed Re-route -customer requires 4" conduit annd weatherhead. 2/14/12* *FBO Update - Revised completion date from sontractors of 3/16/2012 - 2/22/12*
BB35A05 | OHIO | BRIDGE STREET MIDDLE SCHOOL | FR | K12 | FTX1443AK5T | 269 |  | 2011-08-10 |  | fiber and router needed | K-12 | 2011-10-04 | Y | Y | 9589.83 | N |  | 10/18/2011; 1/5/2012 | Y | 613 | 613 | 2011-12-01 | Complete | 2011-11-16 | Y | Complete | 2012-07-27 | 2012-06-05 | 2012-06-27 | Complete | 2012-06-27 | Complete | 2011-08-10 | Ready | 2012-08-03 | *FBO Revised - Revised Date of completion to 1/23/12* *FBO On Hold - Location's Demarc is now in a room that will be demolished. Suggestion made that Lace Host go out and do an advisement on where to place new Demarc. - Nick Patel - 3/27/12* *FBO Hold - Update - The location of the Demarc cannot go into a classroom so we are requesting that Lance go out to this location to designate a new location for the Demarc. - John Miller - 3/30/12* *FBO Hold update - Lance Reccommended to get contractors to install 60 Ft of 1 1/4 in EMT Conduit to the main office of the school in the Telcom Room. Waiting on the final paperwork from Lance on the site and its full printout. - Lance Host - 4/12/12* *FBO Update - Current innerduct is right beside a gas line. Could be a hazard. Cannot go around window directly above duct. requesting basement floorplans. forwarded to John Miller and to speak to Frontier about the current scenario. Rick Singer - 4/25/12* *FBO Update - 1st Final Invoice was $8869.00. Second is required due to locations of demarc being deconstructed. 5-25-12 - Nick Patel.*
BB35A06 | OHIO | ELM GROVE ELEMENTARY SCHOOL | FR | K12 | FTX1442A2CE | 270 |  | 2011-08-10 |  | fiber and router needed | K-12 | 2011-10-04 | Y | Y | 11170.33 | N |  | 2011-10-18 | Y | 1369 | 1369 | 2011-12-01 | Complete | 2011-11-16 | Y | Complete | 2012-01-11 | 2012-02-01 | 2012-02-08 | Complete | 2012-02-08 | Complete | 2011-08-10 | Ready | 2012-02-10 | *FBO Revised - Revised Date of completion to 1/25/12*
BB35A07 | OHIO | MADISON ELEMENTARY | FR | K12 | FTX1442A2C8 | 271 |  | 2011-08-09 |  | fiber and router needed | K-12 | 2011-10-04 | Y | Y | 10601.86 | Y | 2011-10-31 | 2011-12-22 | Y | 983 | 983 | 2011-12-01 | Complete | 2011-11-18 | Y | Complete | 2012-04-05 | 2012-03-22 | 2012-03-10 | Complete | 2012-03-10 | Complete | 2011-08-09 | Ready | 2012-03-16 | *FBO ON Hold - FTR need to do a re-route on Fiber Path - Gudenkauf - 2/8/12* *FBO - FTR Completed Re-route completed pending K12 information as to whether they want the customer premise work done internally or whether BTOP funding will bring to extended Dmarc, then into building. 2/14/12* *FBO Update - We will go to the Dmarc. Nowhere Else - John Dunlap - 2/21/12*
BB35A08 | OHIO | MIDDLE CREEK ELEMENTARY SCHOOL | FR | K12 | FTX1442A2C7 | 272 |  | 2011-08-10 |  | fiber and router needed | K-12 | 2011-10-04 | Y | Y | 22419.86 | N |  | 2011-10-18 | Y | 5168 | 5168 | 2011-12-01 | Complete | 2011-11-13 | Y | Complete | 2012-01-10 | 2012-01-31 | 2012-02-29 | Complete | 2012-02-29 | Complete | 2011-08-10 | Ready | 2012-03-02 | *FBO Revised - Revised Date of Completion to 1/31/12*
BB35A09 | OHIO | RITCHIE ELEMENTARY SCHOOL | FR | K12 | FTX1442A2SC | 273 |  | 2011-08-05 |  | fiber and router needed | K-12 | 2011-10-04 | Y | Y | 46455.49 | Y | 2011-10-31 | 2011-12-22 | Y | 5972 | 5972 | 2012-03-01 | Complete | 2012-02-21 | Y | Complete | 2012-05-28 | 2012-03-23 | 2012-03-26 | Complete | 2012-03-26 | Complete | 2011-08-05 | Ready | 2012-03-29
BB35A10 | OHIO | STEENROD ELEMENTARY SCHOOL | FR | K12 | FTX1443A23F | 274 |  | 2011-08-09 |  | fiber and router needed | K-12 | 2011-10-04 | Y | Y | 21804.254 | Y | 10/31/2011; 12/13/2011 | 2012-01-05 | Y | 2240 | 2240 | 2012-03-01 | Complete | 2012-04-17 | N | No Build Required |  |  | 2012-04-17 | Complete | 2012-04-17 | Complete | 2011-08-09 | Ready | 2012-04-19
BB35A11 | OHIO | TRIADELPHIA MIDDLE SCHOOL | FR | K12 | FTX1443AK5X | 275 |  | 2011-08-10 |  | fiber and router needed | K-12 | 2011-10-04 | Y | Y | 10366.44 | N |  | 2011-12-22 | Y | 1272 | 1272 | 2012-02-01 | Complete | 2012-04-20 | Y | Complete | 2012-07-03 | 2012-08-14 |  | TBD |  | Complete | 2011-08-10 | TBD |  | *FBO Hold - EA Required Pending Approval - Pending John Dunlap approval - 5/29/12* *FBO Update - Lace has submitted a 3rd party look at the location and information has been forwarded to the contractors - 6/19/12* *FBO Update - Contractors responded to the information Lace has reviewed for this location. John Dunlap is reviewing - 6/29/12* *FBO Hold - Update - John Dunlap approved - 7/3/12*
BB35A12 | OHIO | WARWOOD SCHOOL | FR | K12 | FTX1443A23E | 276 |  | 2011-08-12 |  | fiber and router needed | K-12 | 2011-10-04 | Y | Y | 38382.12 | Y | 2011-10-31 | 2011-12-22 | Y | 4930 | 4930 | 2012-03-01 | Complete | 2012-02-29 | N | No Build Required |  |  | 2012-02-29 | Complete | 2012-02-29 | Complete | 2011-08-12 | Ready | 2012-03-02
BB35A13 | OHIO | WEST LIBERTY ELEMENTARY SCHOOL | FR | K12 | FTX1442AKE9 | 277 |  | 2011-08-09 |  | fiber and router needed | K-12 | 2011-10-04 | Y | Y | 16716.59 | N |  | 2011-12-22 | Y | 783 | 783 | 2012-02-01 | 2012-02-01 |  | Y | Complete | 2012-03-21 | 2012-02-21 | 2012-03-09 | Complete | 2012-03-09 | Complete | 2011-08-09 | Ready | 2012-03-16
BB35A14 | OHIO | WHEELING MIDDLE SCHOOL | FR | K12 | FTX1442A2BY | 278 |  | 2011-08-11 |  | fiber and router needed | K-12 | 2011-10-04 | Y | Y | 14233.41 | Y | 2011-10-31 | 2011-12-22 | Y | 1253 | 1253 | 2012-03-01 | Complete | 2012-02-21 | Y | Complete | 2012-07-11 | 2012-04-30 | 2012-04-30 | Complete | 2012-04-30 | Complete | 2011-08-11 | Ready | 2012-05-04
BB35A15 | OHIO | WHEELING PARK HIGH SCHOOL | FR | K12 | FTX1442A2D7 | 279 |  | 2011-10-06 |  | fiber and router needed | K-12 | 2011-10-04 | Y | Y | 12726.37 | Y | 2011-11-10 | 2011-11-16 | Y | 1300 | 1300 | 2011-12-01 | Complete | 2011-11-21 | N | No Build Required |  |  | 2011-11-21 | Complete | 2011-11-21 | Complete | 2011-10-06 | Ready | 2012-01-05
BB35A16 | OHIO | WOODSDALE ELEMENTARY SCHOOL | FR | K12 | FTX1442AKF5 | 280 |  | 2011-08-12 |  | fiber and router needed | K-12 | 2011-10-04 | Y | Y | 17371.51 | Y | 2011-10-31 | 2011-12-22 | Y | 1076 | 1076 | 2012-03-01 | Complete | 2012-05-21 | Y | Complete | 2012-07-11 | 2012-07-03 | 2012-06-25 | Complete | 2012-06-25 | Complete | 2011-08-12 | Ready | 2012-08-03 | *Existing conduit has no access - Mark McKenzie - 6/19/12*
BB35A17 | OHIO | WVIEP - NORTHERN REGIONAL JUVENILE CENTER DJS | FR | K12 | FTX1442A2CS | 281 |  |  |  | fiber and router needed | K-12 | 2011-10-04 | Y | Y | 27954.52 | N |  | 2011-12-22 | Y | 2126 | 2126 | 2012-02-01 | Complete | 2012-03-31 | N | No Build Required |  |  | 2012-04-03 | Complete | 2012-04-03 | TBD |  | Waiting on Router
BB35A18 | OHIO | Ohio County Public Library | FR | LIB | FTX1439A15F | 727 |  | 2012-01-25 |  | fiber and router needed | WVNET | 2011-10-04 | Y | Y | 15599.79 | N |  | 2011-11-07 | Y | 925 | 925 | 2011-12-01 | Complete | 2011-11-18 | Y | Complete | 2012-01-16 | 2012-01-09 | 2012-01-31 | Complete | 2012-01-31 | Complete | 2012-01-25 | Ready | 2012-02-02 | *FBO Revised - Revised Date of Completion to 1/9/12*
BB35A19 | OHIO | Region 10–Bel-O-Mar Regional Council and Interstate Planning Commission (Marshall, Ohio, Wetzel - + Belmont Co, OH) | FR | PDEV | FTX1436A1QR | 1024 | 1ZX560410300476709 | 2011-10-27 |  | fiber and router needed | ? | 2011-10-04 | Y | Y | 11773.53 | N |  | 2011-10-18 | Y | 726 | 726 | 2011-12-01 | Complete | 2011-11-14 | Y | Complete | 2012-02-02 | 2012-02-01 | 2012-02-07 | Complete | 2012-02-07 | Complete | 2011-10-27 | Ready | 2012-02-10 | *FBO Revised - Revised Date of Completion to 1/24/12*
BB35A20 | OHIO | Wheeling-Ohio Comm | FR | PSAP | FTX1436AJUS | 1347 |  | 1/18/2012 |  | fiber and router needed |  | 2011-10-04 | Y | Y | SEE BB35A01 | Y | SEE BB35A01 | 2011-11-07 | Y | SEE BB35A01 | Included | 2011-12-01 | Complete | 2011-11-17 | N | No Build Required |  |  | 2011-12-01 | Complete | 2011-12-01 | Complete | 1/18/2012 | Ready | 2012-02-02
BB35A21 | OHIO | Wheeling Ohio - Troop 1 State Police | FR | SP | FTX1439A26U | 1100 |  | 2011-12-19 |  | fiber and router needed | State Police | 2011-10-04 | Y | Y | 7791.51 | Y | 2011-10-31 | 2011-11-07 | Y | 328 | 328 | 2012-01-01 | Complete | 2011-12-07 | Y | Complete | 2012-01-24 | 2012-01-09 | 2012-03-19 | Complete | 2012-03-19 | Complete | 2011-12-19 | Ready | 2012-03-23 | *FBO Revised - Revised Date of Completion to 1/9/12*
BB35A22 | OHIO | Community Hospital | FR | TMED | FTX1436A1Y2 | 881 | 1ZX560410300477468 | 2012-01-24 |  | fiber and router needed | ? | 2011-10-04 | Y | Y | 10637.96 | N |  | 2011-10-18 | Y | 1240 | 1240 | 2011-12-01 | Complete | 2011-11-14 | Y | Complete | 2012-07-27 | 2012-07-30 | 2012-07-20 | Complete | 2012-07-20 | Complete | 2012-01-24 | Ready | 2012-08-03 | *FBO ON Hold - Broken steam pipe in work area - Gudenkauf - 1/12/12* *FBO Update - Location still has not repaired issue with steam pipes. Dave Robinson - 2/21/12* *FBO Update - Rick Singer has a meeting with Skip Kaneer Today - 5/16/12 - Rick Singer - GudenKauf - 5/16/12*
BB36A01 | PENDLETON | Pendleton County Courthouse | FR | CHOUSE | FTX1441A0Q2 | 569 | Delivered and Installed by Tech | 2012-08-08 |  | fiber and router needed | WVNET | 2011-05-06 | Y | Y | 23312.5 | N |  | 2011-05-19 | Y | 3125 | 3125 | 2011-10-24 | Complete | 2011-09-29 | N | No Build Required |  |  | 2011-10-24 | Complete | 2011-10-24 | Complete | 2012-08-08 | Ready | 2012-09-14 | **LCR WAS LISTED ON MIKE TORDORVICH'S MEMO TO APPROVE 26 LCRs ON 4/15/2011**
BB36A02 | PENDLETON | *FRANKLIN ELEMENTARY SCHOOL (Shared with board office--cannot determine actual counts) | FR | K12 | FTX1439AH11 | 468 |  | 2011-07-06 |  | fiber and router needed | K-12 | 2011-10-26 | Y | Y | 7434 | N |  | 2011-11-07 | Y | 882 | 882 | 2011-10-25 | Complete | 2011-10-25 | N | No Build Required |  |  | 2011-10-25 | Complete | 2011-10-25 | Complete | 2011-07-06 | Ready | 2012-01-05
BB36A03 | PENDLETON | BRANDYWINE ELEMENTARY SCHOOL | FR | K12 | FTX1438A2DK | 469 |  | 2011-07-06 |  | fiber and router needed | K-12 | 2011-05-06 | Y | Y | 14920 | N |  | 2011-04-15 | Y | 2000 | 2000 | 2011-10-24 | Complete | 2011-05-02 | N | No Build Required |  |  | 2011-10-24 | Complete | 2011-10-24 | Complete | 2011-07-06 | Ready | 2012-01-05 | **LCR WAS LISTED ON MIKE TORDORVICH'S MEMO TO APPROVE 26 LCRs ON 4/15/2011**
BB36A04 | PENDLETON | NORTH FORK ELEMENTARY SCHOOL | RO | K12 | FTX1438A2DY | 470 |  | 2011-07-06 |  | PENDING GIT REVIEW FOR BUILD; 5/1/12: PER GIT, JIMMY WILL BE SENDING A LETTER TO K12; FTR WILL NOT BE BUILDING TO THIS CAI; ROUTER ONLY | K-12 | N/A | Y | Y | N/A |  | N/A | N/A | Y | N/A | 0 | N/A | Complete | N/A | N | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-07-06 | Ready | 2012-05-04
BB36A05 | PENDLETON | PENDLETON COUNTY HIGH SCHOOL | FR | K12 | FTX1438A2CX | 471 |  | 2011-07-06 |  | fiber and router needed | K-12 | 2011-04-15 | Y | Y | 12473.12 | N |  | 2011-05-19 | Y | 1672 | 1672 | 2011-05-02 | Complete | 2011-04-24 | N | No Build Required |  |  | 2011-05-02 | Complete | 2011-05-02 | Complete | 2011-07-06 | Ready | 2012-01-05 | **LCR WAS LISTED ON MIKE TORDORVICH'S MEMO TO APPROVE 26 LCRs ON 4/15/2011**
BB36A06 | PENDLETON | Pendleton County Public Library | FR | LIB | FTX1439AJYF | 794 |  | 2012-05-31 |  | fiber and router needed | WVNET | 2011-05-06 | Y | Y | 8952 | N |  | 2011-05-19 | Y | 1200 | 1200 | 2011-10-25 | Complete | 2011-05-02 | N | No Build Required |  |  | 2011-10-25 | Complete | 2011-10-25 | Complete | 2012-05-31 | Ready | 2012-06-08 | **LCR WAS LISTED ON MIKE TORDORVICH'S MEMO TO APPROVE 26 LCRs ON 4/15/2011**
BB36A07 | PENDLETON | Pendleton 911 Center | FR | PSAP | FTX1436AJUA | 1362 |  | 2012-02-27 |  | fiber and router needed |  | TBD | Y | N |  |  |  |  | N |  | TBD | 2011-10-24 | Complete | 2011-10-19 | N | No Build Required |  |  | 2011-10-24 | Complete | 2011-10-24 | Complete | 2012-02-27 | Ready | 2012-03-08
BB36A08 | PENDLETON | Franklin Pendleton - Troop 3 State Police | FR | SP | FTX1439A26M | 1093 |  | 2011-12-14 |  | fiber and router needed | State Police | 2011-05-06 | Y | Y | 15703.3 | N |  | 2011-05-19 | Y | 2105 | 2105 | 2011-10-24 | Complete | 2011-05-02 | N | No Build Required |  |  | 2011-10-24 | Complete | 2011-10-24 | Complete | 2011-12-14 | Ready | 2012-01-05 | **LCR WAS LISTED ON MIKE TORDORVICH'S MEMO TO APPROVE 26 LCRs ON 4/15/2011**
BB36A09 | PENDLETON | Pendleton Community Care | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB36A10 | PENDLETON | Pendleton County High School Clinic | FO | TMED | [5 empty] | PER FTR: THIS CAI IS ON THE SAME PROPERTY AS BB36A05; SEE REFERENCED LCR FOR COST AND FIBER BUILD; THIS SITE WILL RECEIVE A ROUTER. POC; Denied router to this facililty | ? | 2011-04-15 | Y | Y | SEE BB36A05 | N |  | 2011-05-19 | Y | 0 | 0 | 2011-05-02 | Complete | 2011-04-24 | N | No Build Required |  |  | 2011-05-02 | Complete | 2011-05-02 | N/A | N/A | Ready |  | *Router Update - Location Denied Router - Nick Patel - 6.13.12*
BB36A11 | PENDLETON | North Fork Primary Care Clinic | RO | TMED | FTX1436A1YC | 864 | 1ZX560410300468101 | 2011-12-27 |  | PER GIT DECISION: CAI HAS FIBER AT LOCATION; ROUTER ONLY. | ? |  | N | N/A |  |  |  |  | N/A |  | 0 | 2012-08-01 | Complete |  | N | No Build Required |  |  |  | Complete | N/A | Complete | 2011-12-27 | Ready
BB37A01 | PLEASANTS | Pleasants County Courthouse | FR | CHOUSE | FTX1441A0PR | 583 | Delivered and Installed by Tech | 2012-08-02 |  | fiber and router needed | WVNET | 2011-06-08 | Y | Y | 18966.43 | N |  | 2011-09-08 | Y | 2351 | 2351 | 2012-02-01 | Complete | 2012-01-31 | N | No Build Required |  |  | 2012-02-07 | Complete | 2012-02-07 | Complete | 2012-08-02 | Ready | 2012-08-10
BB37A02 | PLEASANTS | St. Marys Correctional Center | FR | CORR | FTX1444A00T | 631 |  | 2012-03-23 |  | fiber and router needed | WVOT | 2011-06-08 | Y | Y | $ 45,141.76 (35938.40) | Y | 2012-03-28 | 2011-09-08 | Y | 9201 | 9201 | 2012-03-01 | Complete | 2012-02-29 | Y | Complete | 2012-06-13 | 2012-05-11 | 2012-06-29 | Complete | 2012-06-29 | Complete | 2012-03-23 | Ready | 2012-08-03 | 3/28/2012: A revised LCR was submitted by FTR to justify a cost increase needed to complete this build as originally engineered. Per FTR, there will be no EA impact from the revision. Revision posted to SharePoint on 3/29/2012.
BB37A03 | PLEASANTS | MID-OHIO VALLEY TECHNICAL INSTITUTE | FR | K12 | FTX1442AKF8 | 238 |  | 2012-02-08 |  | per Ed Kelemen, this site has Suddenlink Fiber. Router Only. Per FTR; Location is to receive Fiber | K-12 | 2011-06-08 | Y | Y | 35969.9 | N |  | 2011-09-08 | Y | 8206 | 8206 | 2012-03-01 | Removed | 2012-02-29 | Y | Removed |  | 2012-04-17 | 2012-06-29 | Removed | 2012-06-29 | N/A | 2012-02-08 | Removed | 2012-05-25 | *FBO Update - Frontier knows building will be moving their facilities and have said to stop FBO. K12 says the building will still be utilized therefore we will still need to complete the fiber build to this site. - Nick Patel - 4/11/12.*
BB37A04 | PLEASANTS | Pleasants County Public Library | FR | LIB | FTX1439A18M | 715 |  | 2012-01-05 |  | fiber and router needed | WVNET | 2011-06-08 | Y | Y | 10494.58 | N |  | 2011-09-08 | Y | 29737 | 29737 | 2012-03-01 | Complete | 2012-02-17 | Y | Complete | 2012-08-02 | 2012-07-03 |  | TBD |  | Complete | 2012-01-05 | TBD
BB37A05 | PLEASANTS | Pleasants County E-911 | FR | PSAP | FTX1436AJUX | 1350 |  | 1/17/2012 |  | fiber and router needed |  | 2011-06-08 | Y | Y | 18980.91 | N |  | 2011-06-29 | Y | 288 | 288 | 2012-03-01 | Complete | 2012-02-29 | N | No Build Required |  |  | 2012-02-29 | Complete | 2012-02-29 | Complete | 1/17/2012 | Ready | 2012-03-02
BB37A06 | PLEASANTS | St. Marys Pleasants - Troop 4 State Police | FR | SP | FTX1439A26V | 1101 |  | 2011-12-19 |  | fiber and router needed | State Police | 2011-06-08 | Y | Y | 34991.53 | N |  | 2011-09-08 | Y | 8112 | 8112 | 2012-03-01 | Complete | 2012-02-29 | Y | Complete | 2012-02-23 | 2012-02-27 | 2012-06-29 | Complete | 2012-06-29 | Complete | 2011-12-19 | Ready | 2012-08-03 | * FBO Notified - Contractor notified WVOT and Frontier that FBO is required at this site. Frontier confirmed the work is required and agreed to move forward with the FBO. 2/2/12* *FBO Revised - Revised Date of Completion to 2/23/12*
BB38A01 | POCAHONTAS | Pocahontas County Courthouse | FR | CHOUSE | FTX1441A0PN |  |  |  |  | fiber and router needed | WVNET | 2011-11-30 | Y | Y | 25283.08 | N |  | 2012-06-21 | Y | 3406 | 3406 | 2012-08-01 | Complete | 2012-08-10 | Y | TBD |  |  |  | TBD |  | TBD |  | TBD |  | * FBO Notified - Contractor notified WVOT and Frontier that FBO is required at this site. Frontier confirmed the work is required and agreed to move forward with the FBO - 7/30/12*
BB38A02 | POCAHONTAS | Denmar Correctional Center | FR | CORR | FTX1444A00S | 632 | Deliverd by courier | 2012-07-19 |  | fiber and router needed | WVOT | 2011-12-01 | Y | Y | 186963 | N |  |  | N |  | TBD | 2012-08-01 | 2012-08-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2012-07-19 | TBD
BB38A03 | POCAHONTAS | *MARLINTON ELEMENTARY SCHOOL | FR | K12 | FTX1442AKE6 | 224 |  | 2012-04-07 |  | fiber and router needed | K-12 | 2011-11-30 | Y | Y | 3590 | N |  | 2012-06-21 | Y | 400 | 400 | 2012-08-01 | Complete | 2012-08-10 | Y | TBD |  |  |  | TBD |  | Complete | 2012-04-07 | TBD |  | * FBO Notified - Contractor notified WVOT and Frontier that FBO is required at this site. Frontier confirmed the work is required and agreed to move forward with the FBO - 7/30/12*
BB38A04 | POCAHONTAS | GREEN BANK ELEMENTARY/MIDDLE SCHOOL | FR | K12 | FTX1442A1ZN | 225 |  | 2011-11-14 |  | fiber and router needed | K-12 | 2011-11-30 | Y | Y | 9810 | N |  | 2012-06-21 | Y | 1400 | 1400 | 2012-08-01 | 2012-08-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2011-11-14 | TBD
BB38A05 | POCAHONTAS | HILLSBORO ELEMENTARY/MIDDLE SCHOOL | FR | K12 | FTX1442A1TG | 226 |  | 2011-11-14 |  | fiber and router needed | K-12 | 2011-11-30 | Y | Y | 9434 | N |  | 2011-12-08 | Y | 1200 | 1200 | 2012-08-01 | 2012-08-01 |  | N | No Build Required |  |  | 2012-07-01 | Complete | 2012-07-01 | Complete | 2011-11-14 | Ready | 2012-09-21
BB38A06 | POCAHONTAS | MARLINTON MIDDLE SCHOOL | FR | K12 | FTX1442A1ZL | 227 |  | 2012-04-07 |  | fiber and router needed | K-12 | 2011-11-30 | Y | Y | 10963.7 | N |  | 2011-12-08 | Y | 1425 | 1425 | 2012-08-01 | 2012-08-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2012-04-07 | TBD
BB38A07 | POCAHONTAS | POCAHONTAS COUNTY HIGH SCHOOL | FR | K12 | FTX1439AH0Z | 228 |  | 2011-11-14 |  | fiber and router needed | K-12 | 2011-11-30 | Y | Y | 476139.84 | N |  |  | N |  | TBD | 2012-08-01 | 2012-08-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2011-11-14 | TBD
BB38A08 | POCAHONTAS | Durbin Public Library | FR | LIB | FTX1439A15P | 791 |  | 2012-05-30 |  | fiber and router needed | WVNET | 2011-11-30 | Y | Y | 66134.5 | Y | 2012-03-19 |  | N |  | TBD | 2012-08-01 | Complete | 2012-09-20 | Y | Scheduled | 2012-09-26 |  |  | TBD |  | Complete | 2012-05-30 | TBD |  | * FBO Notified - Contractor notified WVOT and Frontier that FBO is required at this site. Frontier confirmed the work is required and agreed to move forward with the FBO - 9/11/12* *FBO Update - As for Durbin, They have a new building just down the street. I know we have talked about this before, but I wanted to be sure they drop the fiber into the new permanent site and not the current rental property. Cris Spradling - LIB COMM - 9/13/12*
BB38A09 | POCAHONTAS | Green Bank Public Library | FR | LIB | FTX1439AK06 | 793 |  | 2012-05-30 |  | fiber and router needed | WVNET | 2011-11-30 | Y | Y | 4590 | N |  | 2012-06-21 | Y | 800 | 800 | 2012-09-01 | 2012-09-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2012-05-30 | TBD
BB38A10 | POCAHONTAS | Hillsboro Public Library | FR | LIB | FTX1439AK07 | 789 |  | 2012-05-29 |  | fiber and router needed | WVNET | 2011-11-30 | Y | Y | 5808.6 | N |  | 2012-06-21 | Y | 722 | 722 | 2012-09-01 | Complete | 2012-08-10 | Y | Scheduled | 2012-08-21 |  |  | TBD |  | Complete | 2012-05-29 | TBD |  | * FBO Notified - Contractor notified WVOT and Frontier that FBO is required at this site. Frontier confirmed the work is required and agreed to move forward with the FBO - 7/30/12*
BB38A11 | POCAHONTAS | Pocahontas Co. Free Libraries | FR | LIB | FTX1439A18P | 788 |  | 2012-05-30 |  | fiber and router needed | WVNET | 2011-11-30 | Y | Y | 4337 | N |  | 2011-12-08 | Y | 550 | 550 | 2012-09-01 | 2012-09-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2012-05-30 | TBD
BB38A12 | POCAHONTAS | Pocahontas County 911 | FR | PSAP | FTX1436AJUK | 1358 |  | 2012-02-22 |  | fiber and router needed |  | 2011-11-30 | Y | Y | 6661.3 | N |  | 2011-12-08 | Y | 825 | 825 | 2012-09-01 | 2012-09-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2012-02-22 | TBD
BB38A13 | POCAHONTAS | Marlinton Pocahontas-Troop 3 | FR | SP | FTX1439A26W | 1102 |  | 2012-01-24 |  | fiber and router needed | State Police | 2011-11-30 | Y | Y | 99876.82 | N |  |  | N |  | TBD | 2012-09-01 | 2012-09-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2012-01-24 | TBD
BB38A14 | POCAHONTAS | Northern Pocahontas County Health Clinic | FR | TMED | FTX1436A1SF | 923 |  | 2012-04-26 |  | fiber and router needed | ? | 2012-03-05 | Y | Y | 10550.72 | N |  | 2012-06-21 | Y | 969 | 969 | 2012-09-01 | 2012-09-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2012-04-26 | TBD
BB39A01 | PRESTON | Preston County Courthouse | FR | CHOUSE | FTX1441A0Q7 | 570 | Delivered and Installed by Tech | 2012-08-30 |  | fiber and router needed | WVNET | 2011-04-15 | Y | Y | 3357 | N |  | 2011-09-26 | Y | 450 | 450 | 2011-12-01 | Complete | 2011-11-06 | Y | TBD |  |  |  | TBD |  | Complete | 2012-08-30 | TBD |  | *FBO Hold - Pending EA Review - 8/13/12* *FBO Update - EA Approved - 9/4/12*
BB39A02 | PRESTON | AURORA ELEMENTARY | FR | K12 | FTX1442A2BV | 371 |  | 2011-10-14 |  | fiber and router needed | K-12 | 2011-04-15 | Y | Y | 9086.28 | N |  | 2011-05-19 | Y | 1218 | 1218 | 2011-12-01 | Complete | 2011-11-28 | Y | Complete |  | 2012-02-28 | 2012-06-19 | Complete | 2012-06-19 | Complete | 2011-10-14 | Ready | 2012-06-22 | *FBO Not Required - Innerduct Work already completed. Fiber spliced at pole and ready to be terminated to the Dmarc. Trip Charge will be Generated. Rick Singer - Gudenkauf. 2/28/12*
BB39A03 | PRESTON | BRUCETON SCHOOL | FR | K12 | FTX1442A2CK | 372 |  | 2011-10-19 |  | fiber and router needed | K-12 | 2011-10-25 | Y | Y | 27610 | N |  | 9/26/2011 (10/31/11-SEE NOTES) | Y | 1319 | 1319 | 2012-03-01 | Complete | 2012-06-13 | Y | Complete | 2012-04-12 | 2012-09-20 |  | TBD |  | Complete | 2011-10-19 | TBD |  | * FBO Notified - Contractor notified WVOT and Frontier that FBO is required at this site. Frontier confirmed the work is required and agreed to move forward with the FBO. 2/2/12* *FBO Hold - The entrance to Bruceton Mills School from the S Main Street side is going to be widened and the existing riser pole will be done away with. From what we’re being told S Main Street is going to be widened as well and the riser pole to be utilized is at the corner of Big Sandy St and S Main St. (We do not know who the Frontier Engineer (Michael Hall) will be.) Here is the Engineering Firms info: Slater Engineering (Dick Crane) 724-438-4010 - I will place this job on hold until further notice. - Rick Singer - Gudenkauf - 5/10/12* *FBO Update - FBR submitted requesting Re Evalution of work. - Nick Patel - 7/25/12* *FBO Hold - EA Approved - John D requested Lance review on this location - 8/10/12* *FBO Update - Pending Contractor Justification of work - 8/13/12* *FBO Update - Lance Approved work - 8/23/12*
BB39A04 | PRESTON | CENTRAL PRESTON MIDDLE SCHOOL | FR | K12 | FTX1442A2CA | 373 |  | 12/1/2011 8/9/12 |  | fiber and router needed | K-12 | 2011-04-15 | Y | Y | 71989 | N |  | 2011-09-26 | Y | 9650 | 9650 | 2011-09-15 | Complete | 2011-08-03 | N | No Build Required |  |  | 2011-09-15 | Complete | 2011-09-15 | Complete | 12/1/2011 8/9/12 | Ready | 2012-01-05
BB39A05 | PRESTON | FELLOWSVILLE ELEMENTARY SCHOOL | FR | K12 | FTX1442A1HL | 374 |  | 2011-12-01 |  | fiber and router needed | K-12 | 2011-04-15 | Y | Y | 6289 | N |  | 2012-01-17 | Y | 843 | 843 | 2012-03-01 | Complete | 2012-09-26 | Y | TBD |  |  |  | TBD |  | Complete | 2011-12-01 | TBD
BB39A06 | PRESTON | KINGWOOD ELEMENTARY SCHOOL | FR | K12 | FTX1442A1HR | 375 |  | 2011-07-22 |  | fiber and router needed | K-12 | 2011-04-15 | Y | Y | 15733.14 | N |  | 2011-09-26 | Y | 2109 | 2109 | 2011-12-01 | Complete | 2011-11-04 | Y | Complete | 2012-04-03 | 2012-03-14 |  | TBD |  | Complete | 2011-07-22 | TBD
BB39A07 | PRESTON | PRESTON HIGH SCHOOL | FR | K12 | FTX1442A1ZR | 376 |  | 2011-07-22 |  | fiber and router needed | K-12 | 2011-04-15 | Y | Y | SEE BB39A04 | N |  | 2011-09-26 | Y | 0 | 0 | 2011-09-15 | Complete | 2011-08-03 | N | No Build Required |  |  | 2011-09-15 | Complete | 2011-09-15 | Complete | 2011-07-22 | Ready | 2012-01-05
BB39A08 | PRESTON | ROWLESBURG SCHOOL | FR | K12 | FTX1442A1XA | 377 |  | 2011-10-17 |  | fiber and router needed | K-12 | 2011-04-15 | Y | Y | 47497.82 | N |  | 2011-09-26 | Y | 6367 | 6367 | 2011-12-01 | Complete | 2011-11-18 | Y | Complete |  | 2011-12-20 | 2012-02-02 | Complete | 2012-02-02 | Complete | 2011-10-17 | Ready | 2012-02-24 | *FBO Not Required - The Rowlesburg School #1202870 was already completed by Frontier. The cable is placed and terminal is mounted to the back board. Dave will be forwarding an invoice for the trip charge. Rick Singer - Gudenkauf - 1/26/12* *Alternate path found via Frontier Construction and customer*
BB39A09 | PRESTON | SOUTH PRESTON MIDDLE SCHOOL | REM | K12 | FTX1442A1ZK | 378 |  | 12/1/2011 9/10/12 | E | SCHOOL CLOSED (ASBESTOS) REMOVE FROM LIST | K-12 | 2011-04-15 | Y | Y | 9250.4 | N |  | 2011-09-26 | Y | 1240 | 1240 | 2012-03-01 | Removed | N/A | Y | Removed |  | 2012-01-05 |  | Removed | N/A | N/A | N/A | Removed |  | *FBO Not Required - Location has asbestos in building. Building will be torn down. - 1/5/12* *Router Deployed without approval a second time - 9/10/12*
BB39A10 | PRESTON | TERRA ALTA-EAST PRESTON SCHOOL | FR | K12 | FTX1442A1T3 | 379 |  | 2011-10-28 |  | fiber and router needed | K-12 | 2011-04-15 | Y | Y | 8952 | N |  | 2011-09-26 | Y | 1200 | 1200 | 2011-12-01 | Complete | 2011-11-04 | Y | Scheduled | 2012-08-21 |  |  | TBD |  | Complete | 2011-10-28 | TBD |  | *FBO On Hold - The fiber was terminated into the wrong building. The school is constructing a new wing and they need the fiber terminated into that location rather than the existing one. We’ve left this fiber at the pole outside of the building and corrected our records to reflect “pending FBO” on the Frontier side. It will not do any good to send Gudenkauf back out to the site because the construction of the new building is not complete yet. - Mark McKenzie - Frontier - 1/23/12* *FBO Update - Currently on hold after local request to wait for completion of new wing. The county has been informed that we will not wait for their new wing to be build. The fiber will be terminated in the old wing as originally engineered. Please remove from hold and schedule completion. - John Miller - K12 - 5/22/12* *FBO Hold - Pending EA Approval - Nick Patel - 7/26/12* *FBO Update - EA Approved - Teresa Schuller - 8/8/12* *FBO Hold - John D requested Lance Review - 8/9/12* *FBO Update - Pending Contractor Justification of work - 8/13/12* *Lance Approved Work - Pending John D Approval - 8/21/12* *FBO Update - John D. Approved - 9/27/12*
BB39A11 | PRESTON | TUNNELTON-DENVER ELEMENTARY | FR | K12 | FTX1442A2C9 | 380 |  | 2011-10-17 |  | fiber and router needed | K-12 | 2011-04-15 | Y | Y | 30772.5 | N |  | 2011-09-26 | Y | 4125 | 4125 | 2011-12-01 | Complete | 2011-11-18 | Y | Complete | 2012-03-30 | 2012-03-14 |  | TBD |  | Complete | 2011-10-17 | TBD
BB39A12 | PRESTON | VALLEY ELEMENTARY | FR | K12 | FTX1442A2CQ | 381 |  | 2011-10-11 |  | fiber and router needed | K-12 | 2011-04-15 | Y | Y | $ 30,443.95 ($20,701.50) | Y | 2011-09-26 | 2011-09-26 | Y | 3750 | 3750 | 2012-03-01 | Complete | 2012-02-28 | Y | Complete |  | 2012-03-08 | 2012-06-20 | Complete | 2012-06-20 | Complete | 2011-10-11 | Ready | 2012-06-22 | *FBO Not Required - Job Completed by customer - 3/8/12*
BB39A13 | PRESTON | WEST PRESTON MIDDLE SCHOOL | FR | K12 | FTX1442AKF2 | 382 |  | 2011-10-11 |  | fiber and router needed | K-12 | 2011-04-15 | Y | Y | 11294.44 ($223,742.85) | N | 2011-10-05 | 2011-10-18 | Y | 27930 | 27930 | 2012-03-01 | Complete | 2012-02-28 | Y | Complete | 2012-05-25 | 2012-08-14 |  | TBD |  | Complete | 2011-10-11 | TBD |  | *FBO Hold - Asbestos in walls issue. K12 is to place a bid for this work to be completed.* *FBO Update - No Asbestos in walls found. - John Miller - K12 - 7/3/12* *FBO Update - Local school contact, Bob Ridenour, has been in contact with Rick Singer, Gudenkauf, regarding collaboration with the asbestos contractor at West Preston Middle School. Bob requested that Gudenkauf mark the holes for drilling. Rick was to meet with the contractor this week.- John Miller - K12 - 7/17/12*
BB39A14 | PRESTON | Kingwood Public Library | FR | LIB | FTX1439A16D | 689 |  | 2011-11-29 |  | fiber and router needed | WVNET | 2011-04-15 | Y | Y | 11190 | N |  | 2011-09-26 | Y | 1500 | 1500 | 2011-12-01 | Complete | 2011-11-04 | N | No Build Required |  |  | 2011-11-28 | Complete | 2011-11-28 | Complete | 2011-11-29 | Ready | 2012-01-05
BB39A15 | PRESTON | Terra Alta Public Library | FR | LIB | FTX1439AJVF | 807 |  | 2012-06-29 |  | fiber and router needed | WVNET | 2011-04-15 | Y | Y | 6400.68 | N |  | 2011-09-26 | Y | 858 | 858 | 2011-12-01 | Complete | 2011-11-04 | Y | Complete |  | 2012-01-23 | 2011-11-28 | Complete | 2011-11-28 | Complete | 2012-06-29 | Ready | 2012-08-10 | *FBO Not Required - The library advised our Construction forces to utilize an existing portal rather than construct a new conduit to the pole. It should be noted that this is not per industry standards and may be something Lance sees should he visit this site, but we did what the customer asked us to do. It is complete to the DMARC. - Mark McKenzie - Frontier - 01/23/12*
BB39A16 | PRESTON | Preston County 911 | FR | PSAP | FTX1436AJUU | 1391 |  | 2012-01-30 |  | fiber and router needed |  | 2011-04-15 | Y | Y | 34032.52 | N |  | 2011-09-26 | Y | 4562 | 4562 | 2011-12-01 | Complete | 2011-11-04 | Y | Complete |  | 2012-02-27 | 2012-05-01 | Complete | 2012-05-01 | Complete | 2012-01-30 | Ready | 2012-05-04 | *FBO Not Required - BB39A16 #1202652 Preston County 911 Center is already done. Cable is in, terminal placed and spliced.. Thanks, Rick Singer - Trip Charge Will be generated - 2/20/12*
BB39A17 | PRESTON | Kingwood Preston - Troop 1 State Police | FR | SP | FTX1439A23S | 1040 |  | 2011-12-15 |  | fiber and router needed | State Police | 2011-04-15 | Y | Y | 3357 | N |  | 2011-05-19 | Y | 450 | 450 | 2011-09-15 | Complete | 2011-08-02 | N | No Build Required |  |  | 2011-09-15 | Complete | 2011-09-15 | Complete | 2011-12-15 | Ready | 2012-01-05
BB39A18 | PRESTON | Preston Memorial Hospital | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB40A01 | PUTNAM | Putnam County Courthouse | FR | CHOUSE | FTX1441A0Q0 | 576 | Delivered and Installed by Tech | 2012-07-24 |  | fiber and router needed | WVNET | 2011-05-23 | Y | Y | 6907 | Y | 2011-06-13 | 2011-07-05 | Y | 520 | 520 | 2011-08-18 | Complete | 2011-08-02 | N | No Build Required |  |  | 2011-08-18 | Complete | 2011-08-18 | Complete | 2012-07-24 | Ready | 2012-08-10
BB40A02 | PUTNAM | Putnam County Youth Reporting | FR | DJS | FTX1444AJ14 | 480 |  |  |  | fiber and router needed | WVOT | 2011-05-23 | Y | Y | 25514.6 | Y | 2011-06-13 | 2011-07-05 | Y | 2963 | 2963 | 2011-08-18 | Complete | 2011-08-04 | N | No Build Required |  |  | 2011-08-18 | Complete | 2011-08-18 | TBD |  | Waiting on Router
BB40A03 | PUTNAM | Buffalo Public Library | FR | LIB | FTX1439AK03 | 734 |  | 2012-02-09 |  | fiber and router needed | WVNET | 2011-11-09 | Y | Y | 7601.35 | N |  | 2012-02-15 | Y | 670 | 670 | 2012-08-01 | Complete | 2012-03-20 | N | No Build Required |  |  | 2012-03-20 | Complete | 2012-03-20 | Complete | 2012-02-09 | Ready | 2012-03-23
BB40A04 | PUTNAM | Hurricane Public Library | FR | LIB | FTX1439A14S | 744 |  | 2012-02-07 |  | fiber and router needed | WVNET | 2011-12-01 | Y | Y | 49567.19 | N |  | 2012-03-07 | Y | 2778 | 2778 | 2012-08-01 | 2012-08-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2012-02-07 | TBD
BB40A05 | PUTNAM | Poca Public Library | FR | LIB | FTX1439A19D | 685 |  | 2011-10-27 |  | fiber and router needed | WVNET | 2011-11-28 | Y | Y | 12843.41 | N |  | 2012-03-07 | Y | 1275 | 1275 | 2012-08-01 | Complete | 2012-05-09 | Y | Scheduled | 2012-06-14 |  |  | TBD |  | Complete | 2011-10-27 | TBD
BB40A06 | PUTNAM | Putnam County Public Library | FR | LIB | FTX1439AK09 | 763 |  | 2012-04-24 |  | fiber and router needed | WVNET | 2011-11-09 | Y | Y | 14237.04 | N |  | 2012-03-07 | Y | 589 | 589 | 2012-08-01 | Complete | 2012-05-04 | Y | Scheduled | 2012-09-17 |  |  | TBD |  | Complete | 2012-04-24 | TBD |  | *FBO - Existing conduit is full - can we install new conduit? Aaron Morrisson - 6/12/12* *FBO Update - Pending EA MAP and GPS Coords before Submitting to the EA Rep for Review. Nick Patel - 8/13/12* *FBO Hold Update - EA Map Received - Pending EA Review - Nick Patel - 3/18/12.*
BB40A07 | PUTNAM | Eleanor Public Library | FR | LIB | FTX1525AJM0 | 667 |  | 2011-06-27 |  | fiber and router needed | WVNET | 2011-04-08 | Y | Y | 9004.44 | N |  | 2011-06-29 | Y | 980 | 980 | 2011-04-22 | Complete | 2011-04-17 | N | No Build Required |  |  | 2011-04-22 | Complete | 2011-04-22 | Complete | 2011-06-27 | Ready | 2012-01-05 | **LCR WAS LISTED ON MIKE TORDORVICH'S MEMO TO APPROVE 26 LCRs ON 4/15/2011**
BB40A08 | PUTNAM | Putnam County 9-1-1 Center | FR | PSAP | FTX1436AJUZ | 1378 |  | 2012-01-30 |  | fiber and router needed |  | 2011-05-23 | Y | Y | 19540 | Y | 2011-06-13 | 2011-07-05 | Y | 1845 | 1845 | 2011-08-18 | Complete | 2011-08-18 | N | No Build Required |  |  | 2011-08-18 | Complete | 2011-08-18 | Complete | 2012-01-30 | Ready | 2012-02-17
BB40A09 | PUTNAM | Winfield Putnam - Troop 4 State Police | FR | SP | FTX1439A250 | 1069 |  | 2012-01-20 |  | fiber and router needed | State Police | 2011-10-03 | Y | Y | 23206 | N |  | 2012-02-15 | Y | 1506 | 1506 | 2012-08-01 | Complete | 2012-03-15 | Y | Complete | 2012-05-09 | 2012-07-02 | 2012-07-11 | Complete | 2012-07-11 | Complete | 2012-01-20 | Ready | 2012-08-03
BB40A10 | PUTNAM | CAMC Teays Valley Hospital | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB40A11 | PUTNAM | WomenCare Birth Center | FR | TMED | FTX1444AJ18 | 865 | 1ZX560410300467979 | 2011-09-14 |  | fiber and router needed | ? | 2011-12-08 | Y | Y | 8036.08 | N |  | 2012-03-07 | Y | 825 | 825 | 2012-08-01 | Complete | 2012-06-04 | Y | Scheduled | 2012-07-11 |  |  | TBD |  | Complete | 2011-09-14 | TBD
BB40A12 | PUTNAM | FamilyCare Teays Valley | FR | TMED | FTX1444AJ1S | 866 | 1ZX560410300467951 | 2011-09-14 |  | fiber and router needed | ? | 2011-12-08 | Y | Y | 64885.34 | N |  | 2012-03-07 | Y | 3329 | 3329 | 2012-08-01 | 2012-08-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2011-09-14 | TBD
BB40A13 | PUTNAM | Community Health Network of WV - HQ | FR | TMED | FTX1436A1US | 924 |  | 2012-07-11 |  | fiber and router needed | ? | 2011-11-30 | Y | Y | 13206.53 | N |  | 2011-12-08 | Y | 975 | 975 | 2012-08-01 | Complete | 2012-01-04 | N | No Build Required |  |  | 2012-01-04 | Complete | 2012-01-04 | Complete | 2012-07-11 | Ready | 2012-08-10 | * Contact Information - The main number for GOHELP is (304) 558-0079. Debbie Waller is the secretary and she can tell you how to reach Dave Campbell at CHN - Nancye Bazzle - 3/19/12* *Address Update - 5oo Summers Street Charleston, WV 25302*
BB40A14 | PUTNAM | Valley Health - Hurricane | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB40A15 | PUTNAM | Valley Health - Putnam WIC | FR | TMED | [5 empty] | fiber and router needed | ? | 2011-12-07 | Y | Y | 9803.9 | N |  | 2012-03-07 | Y | 493 | 493 | 2012-08-01 | Complete | 2012-05-04 | Y | Scheduled | 2012-06-11 |  |  | TBD |  | Complete |  | TBD
BB41A01 | RALEIGH | Raleigh County Courthouse | RO | CHOUSE | FTX1441A0Q9 |  |  |  |  | per Ed Kelemen, this site has Suddenlink Fiber; Router Only; Per FTR; BTOP fiber | WVNET | 2011-12-01 | Y | Y | $ 3,217.00 ($ 9,041.56) | Y |  | 2011-12-08 | Y | 350 | 350 | 2012-10-01 | Complete | 2012-04-26 | N | No Build Required |  |  | 2012-04-30 | Complete | N/A | TBD |  | Waiting on Router | N/A
BB41A02 | RALEIGH | Beckley Correctional Center | FR | CORR | FTX1443A29C | 633 | Courier Delivery | 2012-06-25 |  | fiber and router needed | WVOT | 2011-12-01 | Y | Y | 34958.48 | N |  | 2012-03-23 | Y | 3048 | 3048 | 2012-10-01 | 2012-10-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2012-06-25 | TBD
BB41A03 | RALEIGH | Beckley Parole Office | FR | CORR | FTX1444AHJW | 634 | Courier Delivery | 2012-06-25 |  | fiber and router needed | WVOT | 2011-11-28 | Y | Y | 27193.98 | N |  | 2012-03-23 | Y | 2967 | 2967 | 2012-10-01 | Complete | 2012-04-27 | N | No Build Required |  |  | 2012-04-27 | Complete | 2012-04-27 | Complete | 2012-06-25 | Ready | 2012-08-03
BB41A04 | RALEIGH | ACADEMY OF CAREERS AND TECHNOLOGY | RO | K12 | FTX1438A2CT | 20 |  | 2011-10-13 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-10-13 | Ready | 2012-01-05
BB41A05 | RALEIGH | BECKLEY ELEMENTARY SCHOOL | RO | K12 | FTX1439AH1C | 21 |  | 2011-09-27 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-09-27 | Ready | 2012-01-05
BB41A06 | RALEIGH | BECKLEY-STRATTON JUNIOR HIGH SCHOOL | RO | K12 | FTX1439AH15 | 22 |  | 2011-09-27 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-09-27 | Ready | 2012-01-05
BB41A07 | RALEIGH | BRADLEY ELEMENTARY SCHOOL | RO | K12 | FTX1439AH0H | 23 |  | 2011-11-02 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-11-02 | Ready | 2012-01-05
BB41A08 | RALEIGH | CLEAR FORK DISTRICT ELEMENTARY SCHOOL | RO | K12 | FTX1438A2CJ | 24 |  | 2011-11-21 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-11-21 | Ready | 2012-01-05
BB41A09 | RALEIGH | COAL CITY ELEMENTARY SCHOOL | RO | K12 | FTX1438A2DH | 25 |  | 2011-10-25 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-10-25 | Ready | 2012-01-05
BB41A10 | RALEIGH | CRAB ORCHARD ELEMENTARY SCHOOL | RO | K12 | FTX1439AH16 | 26 |  | 2011-11-07 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-11-07 | Ready | 2012-01-05
BB41A11 | RALEIGH | CRANBERRY-PROSPERITY ELEMENTARY SCHOOL | RO | K12 | FTX1439AH0Q | 27 |  | 2011-09-27 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-09-27 | Ready | 2012-01-05
BB41A12 | RALEIGH | CRESCENT ELEMENTARY SCHOOL | RO | K12 | FTX1439AH0A | 28 |  | 2012-01-10 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-01-10 | Ready | 2012-01-27
BB41A13 | RALEIGH | DANIELS ELEMENTARY SCHOOL | RO | K12 | FTX1438A2DZ | 29 |  | 2011-10-27 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-10-27 | Ready | 2012-01-05
BB41A14 | RALEIGH | FAIRDALE ELEMENTARY SCHOOL | RO | K12 | FTX1439AH0G | 30 |  | 2011-11-07 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-11-07 | Ready | 2012-01-05
BB41A15 | RALEIGH | GHENT ELEMENTARY SCHOOL | RO | K12 | FTX1438A2D0 | 31 |  | 2011-10-12 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-10-12 | Ready | 2012-01-05
BB41A16 | RALEIGH | HOLLYWOOD ELEMENTARY SCHOOL | RO | K12 | FTX1438A2D6 | 32 |  | 2011-10-27 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-10-27 | Ready | 2012-01-05
BB41A17 | RALEIGH | INDEPENDENCE HIGH SCHOOL | RO | K12 | FTX1439AH06 | 33 |  | 2011-10-25 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-10-25 | Ready | 2012-01-05
BB41A18 | RALEIGH | INDEPENDENCE JR HIGH SCHOOL | RO | K12 | FTX1438A2BE | 34 |  | 2011-10-25 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-10-25 | Ready | 2012-01-05
BB41A19 | RALEIGH | LESTER ELEMENTARY | RO | K12 | FTX1439AH2S | 35 |  | 2011-11-29 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-11-29 | Ready | 2012-01-05
BB41A20 | RALEIGH | LIBERTY HIGH | RO | K12 | FTX1439AH1E | 36 |  | 2011-11-07 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-11-07 | Ready | 2012-01-05
BB41A21 | RALEIGH | MABSCOTT ELEMENTARY | RO | K12 | FTX1439AH1B | 37 |  | 2011-12-09 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-12-09 | Ready | 2012-01-05
BB41A22 | RALEIGH | MARSH FORK ELEMENTARY SCHOOL | RO | K12 | FTX1438A2C3 | 38 |  | 2011-11-21 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-11-21 | Ready | 2012-01-05
BB41A23 | RALEIGH | MAXWELL HILL ELEMENTARY SCHOOL | RO | K12 | FTX1439AH02 | 39 |  | 2012-01-10 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-01-10 | Ready | 2012-01-27
BB41A24 | RALEIGH | PARK Middle | RO | K12 | FTX1438A2CQ | 40 |  | 2011-12-09 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-12-09 | Ready | 2012-01-05
BB41A25 | RALEIGH | SHADY SPRING ELEMENTARY SCHOOL | RO | K12 | FTX1438A2C4 | 41 |  | 2011-10-11 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-10-11 | Ready | 2012-01-05
BB41A26 | RALEIGH | SHADY SPRING HIGH SCHOOL | RO | K12 | FTX1438A2D2 | 42 |  | 2011-10-12 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-10-12 | Ready | 2012-01-05
BB41A27 | RALEIGH | SHADY SPRING JUNIOR HIGH SCHOOL | RO | K12 | FTX1439AH04 | 43 |  | 2011-10-12 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-10-12 | Ready | 2012-01-05
BB41A28 | RALEIGH | SOPHIA-SOAK CREEK ELEMENTARY SCHOOL | RO | K12 | FTX1438A2DS | 44 |  | 2011-10-25 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-10-25 | Ready | 2012-01-05
BB41A29 | RALEIGH | STANAFORD ELEMENTARY | RO | K12 | FTX1438A2CH | 45 |  | 2011-11-22 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-11-22 | Ready | 2012-01-05
BB41A30 | RALEIGH | STRATTON ELEMENTARY SCHOOL | RO | K12 | FTX1438A2C1 | 46 |  | 2011-11-22 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-11-22 | Ready | 2012-01-05
BB41A31 | RALEIGH | TRAP HILL MIDDLE SCHOOL | RO | K12 | FTX1438A2DU | 47 |  | 2011-11-07 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-11-07 | Ready | 2012-01-05
BB41A32 | RALEIGH | WOODROW WILSON HIGH SCHOOL | RO | K12 | FTX1438A2DQ | 48 |  | 2011-10-13 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-10-13 | Ready | 2012-01-05
BB41A33 | RALEIGH | WVIEP - BURLINGTON BECKLEY CENTER | FR | K12 | FTX1438A2BV | 49 |  | 2012-01-11 |  | fiber and router needed | K-12 | 2011-12-07 | Y | Y | 120249.48 | N |  | 2012-02-29 | Y | 15888 | 15888 | 2012-10-01 | 2012-10-01 | N/A | N | No Build Required |  |  |  | TBD |  | Complete | 2012-01-11 | TBD
BB41A34 | RALEIGH | Raleigh County Public Library | FR | LIB | FTX1439AJVG | 684 |  | 2011-10-28 |  | fiber and router needed | WVNET | 2011-12-01 | Y | Y | 15446.16 | Y | 2011-12-01 | 2012-03-23 | Y | 1976 | 1976 | 2012-10-01 | 2012-10-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2011-10-28 | TBD
BB41A35 | RALEIGH | Shady Spring Public Library | FR | LIB | FTX1439AJZY | 688 |  | 2011-10-31 |  | fiber and router needed | WVNET | 2011-11-30 | Y | Y | 31721.26 | N |  | 2012-03-23 | Y | 5539 | 5539 | 2012-10-01 | Complete | 2012-04-20 | Y | Scheduled | 2012-06-14 |  |  | TBD |  | Complete | 2011-10-31 | TBD
BB41A36 | RALEIGH | Sophia Public Library | FR | LIB | FTX1439A15S | 687 |  | 2012-05-10 |  | fiber and router needed | WVNET | 2011-12-07 | Y | Y | 17857.66 | N |  | 2012-03-23 | Y | 1731 | 1731 | 2012-10-01 | Complete | 2012-05-02 | Y | Scheduled | 2012-07-11 |  | 2012-09-26 | Complete | 2012-09-26 | Complete | 2012-05-10 | Ready | 2012-09-28
BB41A37 | RALEIGH | Marsh Fork Public Library | FR | LIB | FTX1439A16E | 835 |  | 2012-08-15 |  | fiber and router needed | WVNET | 2011-11-18 | Y | Y | 320815.84 | Y | 2012-02-15 | 2012-03-26 | Y | 29526 | 29526 | 2012-11-01 | 2012-11-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2012-08-15 | TBD
BB41A38 | RALEIGH | Raleigh County Emergency Services | FR | PSAP | FTX1436AJTP | 1382 |  | 2012-01-31 |  | fiber and router needed |  | 2011-11-30 | Y | Y | 14249.87 | N |  | 2012-01-09 | Y | 1203 | 1203 | 2012-11-01 | Complete | 2012-01-30 | N | No Build Required |  |  | 2012-01-30 | Complete | 2012-01-30 | Complete | 2012-01-31 | Ready | 2012-02-10
BB41A39 | RALEIGH | Southern Regional Jail | FR | RJAIL | FTX1436A1TH | 654 |  | 2012-03-30 |  | fiber and router needed | WVOT | 2011-11-10 | Y | Y | 12773.22 | N |  | 2011-11-16 | Y | 2493 | 2493 | 2012-11-01 | Complete | 2011-12-28 | N | No Build Required |  |  | 2011-12-28 | Complete | 2011-12-28 | Complete | 2012-03-30 | Ready | 2012-04-05
BB41A40 | RALEIGH | Beckley Turnpike Raleigh State Police | FR | SP | FTX1439A25V | 1082 |  | 2011-12-14 |  | fiber and router needed | State Police | 2011-12-01 | Y | Y | 135027.34 | N |  | 2011-12-13 | Y | 17879 | 17879 | 2012-11-01 | Complete | 2012-09-17 | N | No Build Required |  |  | 2012-09-17 | Complete | 2012-09-17 | Complete | 2011-12-14 | Ready | 2012-09-21
BB41A41 | RALEIGH | Beckley HQ Raleigh - Troop 6 State Police | RO | SP | FTX1439A26Z | 1105 |  | 2012-01-25 |  | 2/1/12: PER LANCE HOST, LOCATION ALREADY HAS FIBER. CAI WILL RECEIVE ROUTER ONLY. | State Police |  | N | N/A |  |  |  |  | N/A |  | 0 | 2012-11-01 | Complete |  | N | No Build Required |  |  |  | Complete | N/A | Complete | 2012-01-25 | Ready | 2012-02-02
BB41A42 | RALEIGH | BCI Beckley Raleigh State Police | FR | SP | FTX1439A26B | 1086 |  | 2012-01-05 |  | fiber and router needed | State Police | 2011-12-01 | Y | Y | 23626.54 | N |  | 2012-03-23 | Y | 2799 | 2799 | 2012-11-01 | Complete | 2012-08-10 | Y | Scheduled | 2012-07-25 |  | 2012-09-21 | Complete | 2012-09-21 | Complete | 2012-01-05 | Ready | 2012-09-28 | * FBO Notified - Contractor notified WVOT and Frontier that FBO is required at this site. Frontier confirmed the contractor has the network side of build. 6/11/12*
BB41A43 | RALEIGH | Whitesville Raleigh - Troop 6 (? Boone) State Police | FR | SP | FTX1439A25F | 1075 |  | 2012-01-19 |  | fiber and router needed | State Police | 2011-10-17 | Y | Y | 73775.79 ($ 86,984.00) | Y | 2011-12-02 | 2012-03-26 | Y | 8730 | 8730 | 2012-11-01 | Complete | 2012-05-25 | N | No Build Required |  |  | 2012-05-25 | Complete | 2012-05-25 | Complete | 2012-01-19 | Ready | 2012-06-08
BB41A44 | RALEIGH | NRHA RCCOA Wellness Center | FR | TMED | FTX1443A28Z | 909 | 1ZX560410300485968 | 2012-01-18 |  | fiber and router needed | ? | 2011-12-07 | Y | Y | 39888.16 | N |  | 2011-12-13 | Y | 5404 | 5404 | 2012-11-01 | Complete | 2012-02-28 | N | No Build Required |  |  | 2012-02-28 | Complete | 2012-02-28 | Complete | 2012-01-18 | Ready | 2012-03-02
BB41A45 | RALEIGH | NRHA Sophia Location | FR | TMED | FTX1436A1Y4 | 905 | 1ZX560410300484530 | 2012-01-18 |  | fiber and router needed | ? | 2011-12-01 | Y | Y | 10036.6 | N |  | 2011-12-13 | Y | 898 | 898 | 2012-11-01 | Complete | 2012-05-02 | Y | Scheduled | 2012-08-03 |  |  | TBD |  | Complete | 2012-01-18 | TBD
BB42A01 | RANDOLPH | Randolph County Courthouse | FR | CHOUSE | FTX1441A0Q4 | 594 | Delivered and Installed by Tech | 2012-08-08 |  | fiber and router needed | WVNET | 2011-10-17 | Y | Y | 19139.04 | N |  | 2012-04-09 | Y | 1017 | 1017 |  | TBD | 2012-05-03 | N | No Build Required |  |  | 2012-05-03 | Complete | 2012-05-03 | Complete | 2012-08-08 | Ready | 2012-09-14
BB42A02 | RANDOLPH | Huttonsville Correctional Center | RO | CORR | FTX1444AHKR | 605 | 1ZX560410300490130 | 2012-01-09 |  | per Ed Kelemen, this site has Suddenlink Fiber; Router Only | WVOT | 2011-08-15 | Y | Y | 10178.25 | N |  | 2011-08-17 | Y | 1572 | 1572 | 2012-07-01 | 2012-07-01 |  | N | No Build Required |  |  |  | TBD | N/A | Complete | 2012-01-09 | TBD | 2012-05-25
BB42A03 | RANDOLPH | Elkins Parole Office | FR | CORR | FTX1443AKA4 | 635 | Courier Delivery | 2012-07-11 |  | fiber and router needed | WVOT | 2011-10-17 | Y | Y | 23359 | N |  | 2012-04-09 | Y | 1550 | 1550 | 2012-09-01 | Complete | 2012-05-02 | N | No Build Required |  |  | 2012-05-02 | Complete | 2012-05-02 | Complete | 2012-07-11 | Ready | 2012-08-03
BB42A04 | RANDOLPH | BEVERLY ELEMENTARY SCHOOL | RO | K12 | FTX1442AKE7 | 383 |  | 2011-11-23 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-11-23 | Ready | 2012-01-05
BB42A05 | RANDOLPH | COALTON ELEMENTARY SCHOOL | FR | K12 | FTX1442AKEE | 384 |  | 2011-11-23 |  | fiber and router needed | K-12 | 2011-11-01 | Y | Y | 167079.37 | N |  | 2012-05-02 | Y | 21412 | 21412 |  | TBD | 2012-07-12 | Y | Scheduled | 2012-09-26 |  |  | TBD |  | Complete | 2011-11-23 | TBD
BB42A06 | RANDOLPH | ELKINS HIGH SCHOOL | RO | K12 | FTX1442AKEY | 385 |  | 2011-11-23 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-11-23 | Ready | 2012-01-05
BB42A07 | RANDOLPH | ELKINS MIDDLE SCHOOL | RO | K12 | FTX1442AKEB | 386 |  | 2011-11-23 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-11-23 | Ready | 2012-01-05
BB42A08 | RANDOLPH | GEORGE WARD ELEMENTARY SCHOOL | RO | K12 | FTX1442A2CF | 387 |  | 2011-11-23 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-11-23 | Ready | 2012-01-05
BB42A09 | RANDOLPH | HARMAN SCHOOL | FR | K12 | FTX1442A1YT | 388 |  | 2012-09-12 |  | fiber and router needed | K-12 | 2012-01-06 | Y | Y | 12101.5 | N |  | 2012-04-09 | Y | 813 | 813 | N/A | Complete | 2012-05-18 | Y | Complete |  | 2012-08-07 | 2012-07-06 | Complete | 2012-07-06 | Complete | 2012-09-12 | Ready | 2012-09-28 | FBO Cancelled - Location has been completed to the Demarc in end of July - Mark McKenzie - 8/7/12*
BB42A10 | RANDOLPH | HOMESTEAD ELEMENTARY SCHOOL | RO | K12 | FTX1443AK4L | 389 |  |  |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | TBD |  | Waiting on Router | N/A
BB42A11 | RANDOLPH | JENNINGS RANDOLPH ELEMENTARY SCHOOL | RO | K12 | FTX1442AKEZ | 390 |  | 2011-11-23 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-11-23 | Ready | 2012-01-05
BB42A12 | RANDOLPH | MIDLAND ELEMENTARY SCHOOL | RO | K12 | FTX1443AK55 | 391 |  | 2012-09-11 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-09-11 | Ready | 2012-09-28
BB42A13 | RANDOLPH | NORTH ELEMENTARY SCHOOL | RO | K12 | FTX1442A2D9 | 392 |  |  |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | TBD |  | Waiting on Router | N/A
BB42A14 | RANDOLPH | PICKENS ELEMENTARY/HIGH SCHOOL | FR | K12 | FTX1443AK52 | 393 |  | 2012-01-05 |  | fiber and router needed | K-12 | 2011-10-28 | Y | Y | 327077 | N |  | 2012-05-02 | Y | 31945 | 31945 |  | TBD |  | N | No Build Required |  |  |  | TBD |  | Complete | 2012-01-05 | TBD
BB42A15 | RANDOLPH | RANDOLPH CO VOC-TECH CENTER | RO | K12 | FTX1442AKEV | 394 |  | 2011-11-23 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-11-23 | Ready | 2012-01-05
BB42A16 | RANDOLPH | RANDOLPH COUNTY ALTERNATIVE CENTER | RO | K12 | FTX1442A1HP | 395 |  |  |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | TBD |  | Waiting on Router | N/A
BB42A17 | RANDOLPH | THIRD WARD ELEMENTARY SCHOOL | RO | K12 | FTX1442A2EC | 396 |  | 2012-09-12 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-09-12 | Ready | 2012-09-28
BB42A18 | RANDOLPH | TYGARTS VALLEY JR-SR HIGH SCHOOL | RO | K12 | FTX1442AKEJ | 397 |  | 2011-11-23 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-11-23 | Ready | 2012-01-05
BB42A19 | RANDOLPH | VALLEY HEAD ELEMENTARY SCHOOL | FR | K12 | FTX1442AKFA | 398 |  | 2011-11-23 |  | fiber and router needed | K-12 | 2011-08-15 | Y | Y | 8295.46 | N |  | 2011-08-17 | Y | 772 | 772 |  | TBD |  | N | No Build Required |  | 2012-09-04 |  | TBD |  | Complete | 2011-11-23 | TBD
BB42A20 | RANDOLPH | WVIEP - ELKINS MOUNTAIN SCHOOL | FR | K12 | FTX1442AKF3 | 399 |  | 2012-04-23 |  | fiber and router needed | K-12 | 2011-10-17 | Y | Y | 35813.43 | N |  | 2012-04-09 | Y | 2873 | 2873 |  | TBD |  | N | No Build Required |  |  |  | TBD |  | Complete | 2012-04-23 | TBD
BB42A21 | RANDOLPH | WVIEP - WEST VIRGINIA CHILDREN'S HOME | FR | K12 | FTX1443AK56 | 400 |  | 2012-04-24 |  | fiber and router needed | K-12 | 2011-09-21 | Y | Y | 40530.81 | Y | 10/10/2011; 10/17/2011; 10/24/2011 | 2012-04-09 | Y | 5505 | 5505 |  | TBD | 2012-08-03 | Y | TBD |  |  |  | TBD |  | Complete | 2012-04-24 | TBD |  | *FBO Hold - WVIEP Schools DEmarc Extensions Pending approval by the GIT*
BB42A22 | RANDOLPH | Belington Public Library | FR | LIB | FTX1439A183 | 779 |  | 2012-05-16 |  | fiber and router needed | WVNET | 2011-09-06 | Y | Y | 16954 | Y | 2011-09-13 | 2012-04-09 | Y | 1388 | 1388 |  | TBD | 2012-06-05 | Y | Complete | 2012-07-30 | 2012-07-30 | 2012-08-15 | Complete | 2012-08-15 | Complete | 2012-05-16 | Ready |  | * FBO Notified - Contractor notified WVOT and Frontier that FBO is required at this site. Frontier confirmed the contractor has the network side of build. 6/11/12*
BB42A23 | RANDOLPH | Elkins-Randolph County Public Library | FR | LIB | FTX1439AJW5 | 808 |  | 2012-06-28 |  | fiber and router needed | WVNET | 2011-10-10 | Y | Y | 20649.13 | Y | 2012-01-05 | 2012-04-09 | Y | 1975 | 1975 |  | TBD | 2012-08-03 | N | No Build Required |  |  | 2012-08-03 | Complete | 2012-08-03 | Complete | 2012-06-28 | Ready | 2012-08-10
BB42A24 | RANDOLPH | Helvetia Public Library | FR | LIB | FTX1439A18Q | 834 |  | 2012-09-25 |  | fiber and router needed | WVNET | 2011-09-06 | Y | Y | 15326 | N |  | 2012-04-09 | Y | 860 | 860 |  | TBD |  | N | No Build Required |  |  |  | TBD |  | Complete | 2012-09-25 | TBD
BB42A25 | RANDOLPH | Pioneer Memorial Public Library | FR | LIB | FTX1439A16B |  |  |  |  | fiber and router needed | WVNET | 2011-08-15 | Y | Y | 8820.99 | N |  | 2011-08-17 | Y | 941 | 941 |  | TBD | 2012-07-09 | N | No Build Required |  |  | 2012-07-09 | Complete | 2012-07-09 | TBD |  | Waiting on Router
BB42A26 | RANDOLPH | Tygart Valley Public Library | FR | LIB | FTX1439AJVR | 792 |  | 2012-05-30 |  | fiber and router needed | WVNET | 2011-08-15 | Y | Y | 7629.53 | N |  | 2011-08-17 | Y | 291 | 291 |  | TBD |  | N | No Build Required |  |  |  | TBD |  | Complete | 2012-05-30 | TBD
BB42A27 | RANDOLPH | Valley Head Public Library | FR | LIB | FTX1439A156 | 790 |  | 2012-05-30 |  | fiber and router needed | WVNET | 2011-08-15 | Y | Y | 7683.27 | N |  | 2011-08-17 | Y | 597 | 597 |  | TBD |  | N | No Build Required |  |  |  | TBD |  | Complete | 2012-05-30 | TBD |  | FBO Update - Valley Head Library is in a holding pattern at the moment. They are constructing a new addition. The Board of Education finally gave them permission to cross under the driveway with new power, phone/data, etc. All utilities will enter the building underground. The fiber is currently rolled up on a pole just one pole past the new underground crossing. Can we get with Frontier to be sure they use the new underground conduits for the fiber installation? They would need to unfasten it from the current pole and drop back to the previous pole. The existing voice and data lines will also be moved. Doug at Valley Head Library is trying to get this done as soon as possible, but he said it could be as long as mid November before it is all completed. - Cris Spradling - LIB COMM. - 9/13/12*
BB42A28 | RANDOLPH | Randolph County 9-1-1 | FR | PSAP | FTX1436AJTN | 1392 |  | 1/25/2012 |  | fiber and router needed |  | 2011-09-06 | Y | Y | 10633 | Y | 2011-09-13 | 2011-09-14 | Y | 1054 | 1054 |  | TBD | 2012-02-29 | N | No Build Required |  |  | 2012-02-29 | Complete | 2012-02-29 | Complete | 1/25/2012 | Ready | 2012-03-02
BB42A29 | RANDOLPH | Tygart Valley Regional Jail | FR | RJAIL | FTX1436A1TK | 652 |  |  |  | fiber and router needed | WVOT | 2011-10-17 | Y | Y | 19487.25 | Y | 2012-01-05 | 2012-04-09 | Y | 3425 | 3425 |  | TBD | 2012-05-03 | N | No Build Required |  |  | 2012-05-03 | Complete | 2012-05-03 | TBD |  | Waiting on Router
BB42A30 | RANDOLPH | Elkins / Randolph - Troop 3 State Police | FR | SP | FTX1439A248 | 1052 |  | 2011-12-29 |  | fiber and router needed | State Police | 2011-10-17 | Y | Y | 11715 | N |  | 2011-10-31 | Y | 640 | 640 |  | TBD | 2012-01-04 | Y | Complete | 2012-06-19 | 2012-04-26 | 2012-04-26 | Complete | 2012-04-26 | Complete | 2011-12-29 | Ready | 2012-05-04 | *FBO Update - Received Final Invoice before approval of dictated work. Final Costs reduced due to discrepancies. - 4/26/12*
BB42A31 | RANDOLPH | Davis Memorial Hospital | RO | TMED |  |  | Courier Delivery | 2012-07-11 |  | PER FTR ON 10/03/11, THIS CAI ALREADY HAS FIBER AT LOCATION. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-07-11 | Ready | 2012-07-13
BB42A32 | RANDOLPH | Valley Health Care, Mill Creek | FR | TMED | FTX1444AJ1R | 867 | 1ZX560410300467960 | 2011-09-20 |  | fiber and router needed | ? | 2011-08-15 | Y | Y | 7292.04 | N |  | 2011-09-14 | Y | 568 | 568 |  | TBD |  | N | No Build Required |  |  |  | TBD |  | Complete | 2011-09-20 | TBD
BB42A33 | RANDOLPH | Little Meadow Health Clinic | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB42A34 | RANDOLPH | Valley Health Care Vision Center | FR | TMED | FTX1444AJ0V | 872 | 1ZX560410300469397 | 2011-09-21 |  | fiber and router needed | ? | 2011-08-15 | Y | Y | SEE BB42A32 | N |  | 2011-09-14 | Y | 568 | 568 |  | TBD |  | N | No Build Required |  |  |  | TBD |  | Complete | 2011-09-21 | TBD
BB43A01 | RITCHIE | Ritchie County Courthouse | FR | CHOUSE | FTX1441A0QD |  |  |  |  | per FTR- site has Armstrong facilities/fiber; 2/2/2012: FTR PENDING LCR APPROVAL- WILL BUILD TO LOCATION | WVNET | 2011-08-15 | Y | Y | 1328466.85 | Y | 2011-08-18 |  | N | 0 | 0 | N/A | Complete | N/A | N | No Build Required |  | 2012-07-31 |  | TBD |  | TBD |  | TBD |  | Mark McKenzie/FTR: sent revised LCR with new GPS on 8/17/11; posted to SharePoint 8/18/11. * FBO Notified - Contractor notified WVOT and Frontier that FBO is required at this site. Frontier confirmed the contractor has the network side of build. 6/11/12* *FBO Hold - County Commissioner Sam Rogers has questioned whether location requires fiber. They currently have Armstrong Fiber and would like to know if what they have is sufficent for their facility. Will discuss in the Tiger team on 7/31/12 - Nick Patel - 7/30/12* *Update - Fiber will be built past this site since their is existing fiber at this location. Tiger Team - 8/14/12*
BB43A02 | RITCHIE | CREED COLLINS ELEMENTARY SCHOOL | FR | K12 | FTX1442AKEF | 252 |  | 2011-08-05 |  | fiber and router needed | K-12 | 2011-04-04 | Y | Y | 5412.06 | N* |  | 2011-05-19 | Y | 611 | 611 | 2011-04-25 | Complete | 2011-04-21 | N | No Build Required |  |  | 2011-04-25 | Complete | 2011-04-25 | Complete | 2011-08-05 | Ready | 2012-01-05 | **LCR WAS LISTED ON MIKE TORDORVICH'S MEMO TO APPROVE 26 LCRs ON 4/15/2011**
BB43A03 | RITCHIE | ELLENBORO ELEMENTARY SCHOOL | FR | K12 | FTX1442A2BT | 253 |  | 2011-08-05 |  | fiber and router needed | K-12 | 2011-06-07 | Y | Y | 19283.71 | N |  | 2011-10-18 | Y | 1803 | 1803 | 2012-03-01 | Complete | 2012-07-10 | N | No Build Required |  |  | 2012-07-10 | Complete | 2012-07-10 | Complete | 2011-08-05 | Ready | 2012-08-03
BB43A04 | RITCHIE | HARRISVILLE ELEMENTARY SCHOOL | FR | K12 | FTX1442A1XP | 254 |  | 2011-08-05 |  | fiber and router needed | K-12 | 2011-08-15 | Y | Y | 21717.81 | N |  | 2011-10-18 | Y | 1752 | 1752 | 2012-03-01 | 2012-03-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2011-08-05 | TBD |  | * FBO Notified - Contractor notified WVOT and Frontier that FBO is required at this site. Frontier confirmed the work is required and agreed to move forward with the FBO. 4/30/12*
BB43A05 | RITCHIE | RITCHIE COUNTY HIGH SCHOOL | FR | K12 | FTX1442A1T2 | 255 |  | 2011-08-05 |  | PER FTR: SITE ALREADY HAS FIBER. PER GIT DECISION, FTR WILL BUILD FIBER TO THIS CAI AND BB43A06 | K-12 | 2011-06-11 | Y | Y | $ 56,796.32 (36795.67) | Y | 2/7/2012; 3/13/2012 | 2/24/2012; 3/23/2012 | Y | 7902 | 7902 | 2012-03-01 | Complete | 2012-06-30 | Y | Complete | 2012-07-31 | 2012-07-11 |  | TBD |  | Complete | 2011-08-05 | TBD |  | per FTR; site was originally slated not to receive fiber build. Per GIT decision, FTR will build fiber to BB43A05/BB43A06 (dual location). LCR final approval notice was issued on 2/24/2012, but new revision of LCR was rec'd on 3/13/2012 due to exhausted IOF facilities. Cost and Fiber Footage have both increased on latest revision. "* FBO Notified - Contractor notified WVOT and Frontier that FBO is required at this site. Frontier confirmed the work is required and agreed to move forward with the FBO - 5/29/12* *FBO Issue - Principal stated that Frontier installed PVC on the outside to the entrance of the building. Based on the Principals decision we will either cancel job or rip out PVC and install Steel Conduit. - Rick Singer - Gudenkauf - 7/3/12*"
BB43A06 | RITCHIE | RITCHIE COUNTY MIDDLE SCHOOL | FR | K12 | FTX1442A1ZF | 256 |  | 2011-08-05 |  | SEE NOTE ABOVE | K-12 | 2011-06-11 | Y | Y | SEE BB43A05 | Y | 2/7/2012; 3/13/2012 | 2/24/2012;3/23/2012 | Y | 0 | 0 | 2012-03-01 | Complete | 2012-06-30 | N | No Build Required |  |  |  | TBD |  | Complete | 2011-08-05 | TBD |  | see notes above (BB43A05)
BB43A07 | RITCHIE | SMITHVILLE ELEMENTARY SCHOOL | FR | K12 | FTX1442A1HK | 257 |  | 2011-08-05 |  | fiber and router needed | K-12 | 2011-06-11 | Y | Y | 401165.6 |  |  | 2011-10-18 | Y | 77367 | 77367 | 2012-03-01 | 2012-03-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2011-08-05 | TBD
BB43A08 | RITCHIE | Pennsboro Public Library | FR | LIB | FTX1439A14U | 758 |  | 2012-03-12 |  | fiber and router needed | WVNET | 2011-05-16 | Y | Y | 7776 | Y | 2011-06-15 | 2011-07-05 | Y | 1175 | 1175 | 2011-12-01 | Complete | 2011-11-07 | Y | Complete | 2012-03-29 | 2012-04-16 | 2012-04-25 | Complete | 2012-04-25 | Complete | 2012-03-12 | Ready | 2012-04-27
BB43A09 | RITCHIE | Ritchie County Public Library | RO | LIB | FTX1439AJY6 | 759 |  | 2012-03-12 |  | per FTR; site already has fiber- router only | WVNET | 2011-06-07 | Y | Y | 5760.71 | N |  | 2011-06-29 | Y | 500 | 500 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-03-12 | Ready | 2012-04-05
BB43A10 | RITCHIE | Central Communications | FR | PSAP | FTX1436AJTV | 1374 |  | 1/23/2012 |  | fiber and router needed |  | 2011-05-16 | Y | Y | 5679 | Y | 2011-06-15 | 2011-07-05 | Y | 550 | 550 | 2011-09-29 | Complete | 2011-09-23 | N | No Build Required |  |  | 2011-09-29 | Complete | 2011-09-29 | Complete | 1/23/2012 | Ready | 2012-03-02
BB43A11 | RITCHIE | Harrisville Ritchie - Troop 4 State Police | FR | SP | FTX1439A23L | 1036 |  | 2011-12-14 |  | fiber and router needed | State Police | 2011-06-11 | Y | Y | 60880.37 | N |  | 2011-10-18 | Y | 5316 | 5316 | 2012-03-01 | Complete | 2012-04-30 | Y | Complete | 2012-08-08 | 2012-07-03 |  | TBD |  | Complete | 2011-12-14 | TBD |  | * FBO Notified - Contractor notified WVOT and Frontier that FBO is required at this site. Frontier confirmed the work is required and agreed to move forward with the FBO. 4/30/12*
BB44A01 | ROANE | Roane County Courthouse | RO | CHOUSE | FTX1441A0QC |  |  |  |  | per Ed Kelemen, this site has Suddenlink Fiber; Router Only PER FTR; BTOP Fiber has been completed to the Demarc | WVNET | 2011-06-14 | Y | Y | 14441.28 | N |  | 2011-07-05 | Y | 800 | 800 | 2012-03-01 | Complete | 2012-06-05 | N | No Build Required |  |  | 2012-06-05 | Complete | N/A | TBD |  | Waiting on Router | N/A | *Fiber Update - BTOP Fiber was in processing. Suddenlink informed our team that there is fiber existing after we had already completed the build. - 6/15/12*
BB44A02 | ROANE | GEARY ELEMENTARY SCHOOL | FR | K12 | FTX1442AKE8 | 239 |  | 2012-03-23 |  | fiber and router needed | K-12 | 2011-09-07 | Y | Y | 113995.08 | N |  | 2011-10-06 | Y | 22995 | 22995 | 2012-03-01 | Complete | 2012-03-05 | N | No Build Required |  |  | 2012-03-05 | Complete | 2012-03-05 | Complete | 2012-03-23 | Ready | 2012-03-29
BB44A03 | ROANE | REEDY ELEMENTARY SCHOOL | FR | K12 | FTX1442A1TN | 240 |  | 2012-03-02 |  | fiber and router needed | K-12 | 2011-08-19 | Y | Y | 20547.87 | N |  | 2011-10-06 | Y | 3400 | 3400 | 2012-03-01 | 2012-03-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2012-03-02 | TBD
BB44A04 | ROANE | ROANE COUNTY HIGH SCHOOL | FR | K12 | FTX1442A1YR | 241 |  | 2012-03-09 |  | fiber and router needed | K-12 | 2011-09-02 | Y | Y | 13926.92 | N |  | 2011-09-08 | Y | 1550 | 1550 | 2011-10-24 | Complete | 2011-10-20 | N | No Build Required |  |  | 2011-10-24 | Complete | 2011-10-24 | Complete | 2012-03-09 | Ready | 2012-03-29
BB44A05 | ROANE | SPENCER MIDDLE SCHOOL | FR | K12 | FTX1442A1YA | 242 |  | 2012-03-09 |  | fiber and router needed | K-12 | 2011-06-14 | Y | Y | 7957.06 | N |  | 2011-07-05 | Y | 1200 | 1200 | 2011-08-15 | Complete | 2011-08-15 | N | No Build Required |  |  | 2011-08-15 | Complete | 2011-08-15 | Complete | 2012-03-09 | Ready | 2012-03-29
BB44A06 | ROANE | Spencer Elementary Primary Center | FR | K12 | FTX1442A1HH | 243 |  | 2012-03-23 |  | fiber and router needed | K-12 | 2011-06-14 | Y | Y | 13909.55 | N |  | 2011-10-06 | Y | 3453 | 3453 | 2011-12-01 | Complete | 2011-11-20 | Y | Scheduled | 2012-08-01 |  |  | TBD |  | Complete | 2012-03-23 | TBD |  | *FBO Update - Wrong Final Invoice Given - Rick Singer - New one will be submitted - New invoice for only $3000.00* *FBO Hold - Work completed using existing conduit. Before Frontier could complete Lumos installed Fiber into the existing conduit. Lance has reviewed site and has reccommended we re-do the FBO work with new conduit. - 6/29/12 - Nick Patel* *FBO Update - FBO will be redone due to no access in the existing conduit. Tiger Team - 7/3/12* *FBO Update - Rick Singer stated there is plenty of space in conduit in this location. Pictures will be sent to me for confirmation - Forward to Mark McKenzie - 8/10/12* *FBO Update - Building owner will not allow installation into the ground. Contractor submitted new Invoice - 8/21/12* *FBO Hold - Pending Lance Review - 8/28/12* *FBO Update - Lance Approved work (Little High) - 9/12/12
BB44A07 | ROANE | WALTON ELEMENTARY/MIDDLE SCHOOL | FR | K12 | FTX1442A2CU | 244 |  | 2012-03-23 |  | fiber and router needed | K-12 | 2011-11-06 | Y | Y | 19099.95 | N |  | 2011-11-09 | Y | 3700 | 3700 | 2012-03-01 | Complete | 2012-01-30 | Y | Complete | 2012-05-30 | 2012-04-02 | 2012-05-01 | Complete | 2012-05-01 | Complete | 2012-03-23 | Ready | 2012-05-04
BB44A08 | ROANE | Roane County Public Library | FR | LIB | FTX1439AJW7 | 747 |  | 2012-02-17 |  | fiber and router needed | WVNET | 2011-06-14 | Y | Y | 12777.84 | N |  | 2011-07-05 | Y | 1050 | 1050 | 2012-03-01 | Complete | 2012-06-05 | N | No Build Required |  |  | 2012-06-05 | Complete | 2012-06-05 | Complete | 2012-02-17 | Ready | 2012-06-08
BB44A09 | ROANE | Walton Public Library | FR | LIB | FTX1439A166 | 757 |  | 2012-03-09 |  | fiber and router needed | WVNET | 2011-06-24 | Y | Y | 11445.1 | N |  | 2011-10-06 | Y | 801 | 801 | 2011-12-01 | Complete | 2011-11-22 | Y | Complete | 2012-06-04 | 2012-04-02 | 2012-05-03 | Complete | 2012-05-03 | Complete | 2012-03-09 | Ready | 2012-05-10
BB44A10 | ROANE | Geary Library & Medical Care | FR | LIB | FTX1439AK04 | 746 |  | 2012-02-15 |  | fiber and router needed | WVNET | 2011-09-07 | Y | Y | 12220.91 | N |  | 2011-09-14 | Y | 588 | 588 | 2012-03-01 | Complete | 2012-03-22 | N | No Build Required |  |  | 2012-03-22 | Complete | 2012-03-22 | Complete | 2012-02-15 | Ready | 2012-03-23
BB44A11 | ROANE | 911 Center | FR | PSAP | FTX1436AJUB | 1365 |  | 2012-01-31 |  | fiber and router needed |  | 2011-06-15 | Y | Y | 4876 | N |  | 2011-10-06 | Y | 550 | 550 | 2012-03-01 | Complete | 2012-06-05 | N | No Build Required |  |  | 2012-06-05 | Complete | 2012-06-05 | Complete | 2012-01-31 | Ready | 2012-06-08
BB44A12 | ROANE | Spencer Roane - Troop 4 State Police | FR | SP | FTX1439A240 | 1046 |  | 2012-01-25 |  | fiber and router needed | State Police | 2011-06-24 | Y | Y | 11046.54 | N |  | 2011-10-06 | Y | 450 | 450 | 2012-03-01 | 2012-03-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2012-01-25 | TBD
BB44A13 | ROANE | Roane County Family Health Care, Inc. | FR | TMED | FTX1444AJ1F | 875 | 1ZX560410300469324 | 2011-09-27 |  | fiber and router needed | ? | 2011-06-14 | Y | Y | 12550.08 | N |  | 2011-07-05 | Y | 3350 | 3350 | 2011-10-03 | Complete | 2011-10-03 | N | No Build Required |  |  | 2011-10-03 | Complete | 2011-10-03 | Complete | 2011-09-27 | Ready | 2012-01-05
BB44A14 | ROANE | Roane General Hospital | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB45A01 | SUMMERS | Summers County Courthouse | FR | CHOUSE | FTX1441A0PJ |  |  |  |  | fiber and router needed | WVNET | 2011-11-01 | Y | Y | 26781.31 | N |  | 2012-03-23 | Y | 2859 | 2859 | 2012-11-01 | 2012-11-01 |  | N | No Build Required |  |  |  | TBD |  | TBD |  | TBD
BB45A02 | SUMMERS | HINTON AREA ELEMENTARY SCHOOL | RO | K12 | FTX1439AH1F | 51 |  | 2011-08-16 |  |  | K-12 |  | N | N/A |  |  |  |  | N/A |  | 0 | 2012-11-01 | Complete |  | N | No Build Required |  |  |  | Complete | N/A | Complete | 2011-08-16 | Ready | 2012-01-27
BB45A03 | SUMMERS | JUMPING BRANCH ELEMENTARY SCHOOL | RO | K12 | FTX1438A2C7 | 52 |  | 2011-11-23 |  |  | K-12 |  | N | N/A |  |  |  |  | N/A |  | 0 | 2012-11-01 | Complete |  | N | No Build Required |  |  |  | Complete | N/A | Complete | 2011-11-23 | Ready | 2012-01-27
BB45A04 | SUMMERS | SUMMERS COUNTY HIGH SCHOOL | RO | K12 | FTX1439AH0T | 53 |  | 2011-10-11 |  |  | K-12 |  | N | N/A |  |  |  |  | N/A |  | 0 | 2012-11-01 | Complete |  | N | No Build Required |  |  |  | Complete | N/A | Complete | 2011-10-11 | Ready | 2012-01-27
BB45A05 | SUMMERS | SUMMERS MIDDLE SCHOOL | RO | K12 | FTX1438A2CP | 54 |  | 2011-11-23 |  |  | K-12 |  | N | N/A |  |  |  |  | N/A |  | 0 | 2012-11-01 | Complete |  | N | No Build Required |  |  |  | Complete | N/A | Complete | 2011-11-23 | Ready | 2012-01-27
BB45A06 | SUMMERS | TALCOTT ELEMENTARY SCHOOL | RO | K12 | FTX1439AH0X | 55 |  | 2011-10-07 |  |  | K-12 |  | N | N/A |  |  |  |  | N/A |  | 0 | 2012-11-01 | Complete |  | N | No Build Required |  |  |  | Complete | N/A | Complete | 2011-10-07 | Ready | 2012-01-27
BB45A07 | SUMMERS | Summers County Public Library | FR | LIB | FTX1439AJW3 | 782 |  | 2012-05-18 |  | fiber and router needed | WVNET | 2011-10-31 | Y | Y | 10601.69 | N |  | 2011-11-07 | Y | 1085 | 1085 | 2012-11-01 | 2012-11-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2012-05-18 | TBD
BB45A08 | SUMMERS | Summers County E-911 | FR | PSAP | FTX1436AJTH | 1355 |  | 2012-02-22 |  | fiber and router needed |  | 2011-10-28 | Y | Y | 10089.97 | N |  | 2012-03-23 | Y | 625 | 625 | 2012-11-01 | 2012-11-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2012-02-22 | TBD
BB45A09 | SUMMERS | Hinton Summers - Troop 6 State Police | FR | SP | FTX1439A26C | 1087 |  | 2012-01-20 |  | fiber and router needed | State Police | 2011-11-01 | Y | Y | 9701.19 | N |  | 2012-03-23 | Y | 420 | 420 | 2012-11-01 | Complete | 2012-05-18 | Y | Scheduled | 2012-07-14 |  | 2012-08-29 | Complete | 2012-08-29 | Complete | 2012-01-20 | Ready | 2012-08-31
BB46A01 | TAYLOR | Taylor County Courthouse | FR | CHOUSE | FTX1441AHZN | 555 | Delivered and Installed by Tech | 2012-03-07 |  | fiber and router needed | WVNET | 2011-04-15 | Y | Y | 30959 | N |  | 2011-05-21 | Y | 4150 | 4150 | 2012-02-01 | 2012-02-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2012-03-07 | TBD
BB46A02 | TAYLOR | Pruntytown Correctional Center | FR | CORR | FTX1444AHKW | 636 | 1ZX560410300523185 | 2012-06-11 |  | fiber and router needed | WVOT | 2011-05-06 | Y | Y | 18344.14 | N |  | 2011-09-14 | Y | 2459 | 2459 | 2011-05-04 | Complete | 2011-04-30 | N | No Build Required |  |  | 2011-05-04 | Complete | 2011-05-04 | Complete | 2012-06-11 | Ready |  | **LCR WAS LISTED ON MIKE TORDORVICH'S MEMO TO APPROVE 26 LCRs ON 4/15/2011** *Router Update - Router installed - 7/13/12*
BB46A03 | TAYLOR | *GRAFTON HIGH SCHOOL & TAYLOR TECH CENTER | RO | K12 | FTX1442AKF1 | 401 |  | 2011-05-17 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-05-17 | Ready | 2012-01-05
BB46A04 | TAYLOR | ANNA JARVIS ELEMENTARY SCHOOL | RO | K12 | FTX1443AK5U | 402 |  | 2011-05-13 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-05-13 | Ready | 2012-01-05
BB46A05 | TAYLOR | FLEMINGTON ELEMENTARY SCHOOL | FR | K12 | FTX1442A2C0 | 403 |  | 2012-09-04 |  | fiber and router needed | K-12 | 2011-04-15 | Y | Y | 39538 | N |  | 2011-12-08 | Y | 5300 | 5300 | 2012-03-01 | Complete | 2012-02-29 | Y | Complete | 2012-06-01 | 2012-04-30 | 2012-05-10 | Complete | 2012-05-10 | Complete | 2012-09-04 | Ready | 2012-09-28 | 12/22/11: LCR WAS APPROVED ON 12/8/11 AND LCR FINAL APPROVAL NOTICE WAS SENT TO CAI/FTR. WVOT WILL NOT BE RESENDING A LCR FINAL APPROVAL NOTICE. * FBO Notified - Contractor notified WVOT and Frontier that FBO is required at this site. Frontier confirmed the work is required and agreed to move forward with the FBO. 2/2/12*
BB46A06 | TAYLOR | TAYLOR COUNTY MIDDLE SCHOOL | RO | K12 | FTX1442A2D4 | 404 |  | 2011-05-13 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-05-13 | Ready | 2012-01-05
BB46A07 | TAYLOR | WEST TAYLOR ELEMENTARY SCHOOL | RO | K12 | FTX1442A2CH | 405 |  | 2011-05-18 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-05-18 | Ready | 2012-01-05
BB46A08 | TAYLOR | Taylor County Public Library | FR | LIB | FTX1439A13U | 809 |  | 2012-06-29 |  | fiber and router needed | WVNET | 2011-04-15 | Y | Y | 6714 | N |  | 2011-09-14 | Y | 900 | 900 | 2012-02-01 | Complete | 2012-01-11 | N | No Build Required |  |  | 2012-01-11 | Complete | 2012-01-11 | Complete | 2012-06-29 | Ready | 2012-08-03
BB46A09 | TAYLOR | Grafton Taylor - Troop 1 | FR | SP | FTX1439A25T | 1080 |  | 2011-12-14 |  | fiber and router needed | State Police | 2011-04-15 | Y | Y | 7460 | N |  | 2011-09-14 | Y | 1000 | 1000 | 2011-12-01 | Complete | 2011-11-09 | Y | Complete | 2012-07-03 | 2012-04-30 | 2012-05-29 | Complete | 2012-05-29 | Complete | 2011-12-14 | Ready | 2012-06-08
BB47A01 | TUCKER | Tucker County Courthouse | FR | CHOUSE | FTX1441A0PK |  |  |  |  | fiber and router needed | WVNET | 2011-07-18 | Y | Y | 11456 | N |  | 2011-07-25 | Y | 310 | 310 | 2012-07-01 | Complete | 2012-04-16 | N | No Build Required |  |  | 2012-04-13 | Complete | 2012-04-13 | TBD |  | Waiting on Router
BB47A02 | TUCKER | DAVIS-THOMAS ELEMENTARY/MIDDLE SCHOOL | FR | K12 | FTX1442AKEU | 406 |  | 2012-01-17 |  | fiber and router needed | K-12 | 2011-07-18 | Y | Y | 17211.04 | N |  | 2011-07-25 | Y | 2165 | 2165 | 2012-07-01 | Complete | 2012-04-04 | N | No Build Required |  |  | 2012-04-04 | Complete | 2012-04-04 | Complete | 2012-01-17 | Ready | 2012-04-13
BB47A03 | TUCKER | TUCKER COUNTY HIGH SCHOOL | FR | K12 | FTX1442A2D0 | 407 |  | 2012-01-17 |  | fiber and router needed | K-12 | 2011-07-18 | Y | Y | 277219.64 | N |  | 2011-07-25 | Y | 53192 | 53192 | 2012-07-01 | Complete | 2012-04-07 | N | No Build Required |  |  | 2012-04-07 | Complete | 2012-04-07 | Complete | 2012-01-17 | Ready | 2012-04-13
BB47A04 | TUCKER | TUCKER COUNTY SD BOARD OFFICE (PK) | FR | K12 | FTX1442AKEQ | 408 |  | 2012-01-18 |  | fiber and router needed | K-12 | 2011-07-18 | Y | Y | 61039.69 | N |  | 2011-07-25 | Y | 3108 | 3108 | 2012-07-01 | Complete | 2012-04-16 | N | No Build Required |  |  | 2012-04-16 | Complete | 2012-04-16 | Complete | 2012-01-18 | Ready | 2012-04-19
BB47A05 | TUCKER | TUCKER VALLEY ELEMENTARY MIDDLE SCHOOL | FR | K12 | FTX1442A2DV | 409 |  | 2012-01-18 |  | fiber and router needed | K-12 | 2011-07-18 | Y | Y | 31572.76 | N |  | 2011-07-25 | Y | 49791 | 49791 | 2012-07-01 | Complete | 2012-04-16 | N | No Build Required |  |  | 2012-04-16 | Complete | 2012-04-16 | Complete | 2012-01-18 | Ready | 2012-04-19
BB47A06 | TUCKER | WVIEP - DAVIS CENTER (Kenneth "Honey" Rubenstein Ctr) DJS | FR | K12 | FTX1442A2BU | 410 |  | 2012-04-20 |  | fiber and router needed | K-12 | 2011-07-18 | Y | Y | 19574.64 | N |  | 2011-07-25 | Y | 2525 | 2525 | 2012-07-01 | Complete | 2012-03-31 | N | No Build Required |  |  | 2012-03-31 | Complete | 2012-03-31 | Complete | 2012-04-20 | Ready | 2012-09-28
BB47A07 | TUCKER | Five Rivers Public Library | FR | LIB | FTX1439AJWJ | 786 |  | 2012-05-17 |  | fiber and router needed | WVNET | 2011-07-18 | Y | Y | 11463.61 | N |  | 2011-07-25 | Y | 187 | 187 | 2012-07-01 | Complete | 2012-04-13 | N | No Build Required |  |  | 2012-04-13 | Complete | 2012-04-13 | Complete | 2012-05-17 | Ready | 2012-06-08
BB47A08 | TUCKER | Mountaintop Public Library | FR | LIB | FTX1439A16N | 806 |  | 2012-06-19 |  | fiber and router needed | WVNET | 2011-07-18 | Y | Y | 12392.85 | N |  | 2011-07-25 | Y | 755 | 755 | 2012-07-01 | Complete | 2012-04-04 | N | No Build Required |  |  | 2012-04-04 | Complete | 2012-04-04 | Complete | 2012-06-19 | Ready | 2012-08-03
BB47A09 | TUCKER | Tucker County 9-1-1 | FR | PSAP | FTX1436AJU0 | 1367 |  | 2012-01-24 |  | fiber and router needed |  | 2011-07-18 | Y | Y | 11249.43 | N |  | 2011-07-25 | Y | 259 | 259 | 2012-07-01 | Complete | 2012-04-16 | N | No Build Required |  |  | 2012-04-16 | Complete | 2012-04-16 | Complete | 2012-01-24 | Ready | 2012-04-19
BB47A10 | TUCKER | Parsons Tucker - Troop 3 State Police | FR | SP | FTX1439A25K | 1079 |  | 2011-12-14 |  | fiber and router needed | State Police | 2011-07-18 | Y | Y | 13104.39 | N |  | 2011-07-25 | Y | 1217 | 1217 | 2012-07-01 | Complete | 2012-04-16 | Y | Scheduled | 2012-07-18 |  |  | TBD |  | Complete | 2011-12-14 | TBD |  | *FBO Update - Nichols Construction will be re-evaluating the this site based on pictures of the location they may be able to go aieral with the Fiber entrance. - Tom Orr - Nichols Con - 7/3/12*
BB48A01 | TYLER | Tyler County Courthouse | FR | CHOUSE | FTX1441A0QB | 577 | Delivered and Installed by Tech | 2012-08-02 |  | fiber and router needed | WVNET | 2011-11-09 | Y | Y | 13917.04 | N |  | 2011-11-16 | Y | 1600 | 1600 | 2012-01-01 | Complete | 2011-12-20 | N | No Build Required |  |  | 2011-12-20 | Complete | 2011-12-20 | Complete | 2012-08-02 | Ready | 2012-08-10
BB48A02 | TYLER | *TYLER CONSOLIDATED MIDDLE/HIGH SCHOOL & BOE (Shared with board office--cannot determine actual counts) | FR | K12 | FTX1442A1TH | 245 |  | 2012-04-22 |  | fiber and router needed | K-12 | 2011-11-09 | Y | Y | 18574.99 | N |  | 2011-11-16 | Y | 3050 | 3050 | 2012-01-01 | Complete | 2011-12-06 | N | No Build Required |  |  | 2011-12-06 | Complete | 2011-12-06 | Complete | 2012-04-22 | Ready | 2012-05-18
BB48A03 | TYLER | BOREMAN ELEMENTARY SCHOOL | FR | K12 | FTX1442A1ZQ | 246 |  |  |  | fiber and router needed | K-12 | 2011-11-30 | Y | Y | 27250.16 | N |  | 2012-04-09 | Y | 1429 | 1429 | 2012-03-01 | Complete | 2012-05-16 | Y | Complete | 2012-08-21 | 2012-09-20 |  | TBD |  | TBD |  | TBD |  | *FBO Hold - Pending EA Review - 8/13/12* *FBO Update - This FBO was approved on the original LCR back on 3/6/12. It is the same buried route the agencies approved. No additional EA work is required.- Teresa Schuller - 8/13/12* *FBO Hold - John D. Request that Lance Review this location - 8/13/12* *FBO Update - Lance Approved Work - 8/23/12*
BB48A04 | TYLER | SISTERSVILLE ELEMENTARY SCHOOL | FR | K12 | FTX1442A1HS | 247 |  | 2012-02-10 |  | fiber and router needed | K-12 | 2011-11-17 | Y | Y | 23078.43 | N |  | 2012-04-09 | Y | 3750 | 3750 | 2012-03-01 | Complete | 2012-05-18 | Y | Complete | 2012-08-21 | 2012-09-06 | 2012-09-24 | Complete | 2012-09-24 | Complete | 2012-02-10 | Ready | 2012-09-28 | *FBO Hold - Pending EA Approval - Nick Patel - 7/26/12* *FBO Hold - EA Approved - John D requested Lance review on this location - 8/10/12* *FBO Update - Lance Approves scope of work - 8/13/12* *FBO Update - John D Approved - 8/13/12*
BB48A05 | TYLER | Tyler County Public Library | FR | LIB | FTX1439A186 | 731 |  | 2012-01-23 |  | fiber and router needed | WVNET | 2011-11-18 | Y | Y | 8505.34 | N |  | 2012-04-09 | Y | 960 | 960 | 2012-03-01 | Complete | 2012-05-23 | Y | TBD |  |  |  | TBD |  | Complete | 2012-01-23 | TBD |  | *FBO Hold - Upon visiting this site we were informed that they will be breaking ground on a building addition adjacent to the original building. The location of the new building is in direct conflict with our path. ( aerial or buried ) Roseanne Eastham told me it would be in our best interest to delay this job because the new d-mark and equipment will be relocated to the new structure and their current equipment is temporarily on a shelf. We can provide you a picture of the lot location vs fiber coil if you need it. Here is Rosanne’s number if you need it. 304-7584304 - Rick Singer - Gudenkauf - 6/28/12* *FBO Update - Notified LIB Commission - they will investigate and return call with more information. They were unaware of any office move - Barbara England - 6/29/12* *FBO Update -New addition to begin construction this fall and be completed by Feb 2013. The new addition will sit between the existing building and the pole where the fiber is coiled. If you want to leave it on the pole, that should be fine. - Cris Spradling -7/16/12*
BB48A06 | TYLER | Sistersville Public Library | FR | LIB | FTX1439AJVV | 730 |  | 2012-01-23 |  | fiber and router needed | WVNET | 2011-11-06 | Y | Y | 13098.02 | N |  | 2011-12-22 | Y | 1100 | 1100 | 2012-03-01 | Complete | 2012-01-23 | Y | Complete | 2012-06-06 | 2012-04-02 | 2012-04-23 | Complete | 2012-04-23 | Complete | 2012-01-23 | Ready | 2012-04-27
BB48A07 | TYLER | Paden City Public Library Tyler pt | REM | LIB |  |  |  |  | E | DUPLICATE SITE: SEE BB52A12 | WVNET |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed |  | N/A | Removed | N/A |  | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB48A08 | TYLER | Dispatch Center | RO | PSAP | FTX1436AJUE | 1372 |  | 1/18/2012 |  | per FTR; site already has fiber- router only |  |  | N | N/A |  |  |  |  | N/A |  | 0 |  | Complete |  |  | No Build Required |  |  |  | Complete | N/A | Complete | 1/18/2012 | Ready
BB48A09 | TYLER | Paden City Tyler - Troop 1 State Police | FR | SP | FTX1439A26N | 1094 |  | 2011-12-19 |  | fiber and router needed | State Police | 2011-10-04 | Y | Y | 34744.95 | N |  | 2012-03-07 | Y | 4050 | 4050 | 2012-02-01 | Complete | 2012-05-25 | Y | Complete | 2012-07-16 | 2012-07-30 | 2012-08-08 | Complete | 2012-08-08 | Complete | 2011-12-19 | Ready | 2012-08-10 | *FBO Hold - FBR Approved - Pending E.A. Approval - 6/29/12* FBO Update - E.A. Approved - Signoff complete. - 6/28/12
BB49A01 | UPSHUR | Upshur County Courthouse | FR | CHOUSE | FTX1441A0QE | 550 | Delivered and Installed by Tech | 2012-06-27 |  | fiber and router needed | WVNET | 2011-11-09 | Y | Y | 33557.24 | N |  | 2012-05-02 | Y | 2786 | 2786 | 2012-07-01 | Complete | 2012-06-07 | N | No Build Required |  |  | 2012-06-07 | Complete | 2012-06-07 | Complete | 2012-06-27 | Ready | 2012-08-03
BB49A02 | UPSHUR | BUCKHANNON UPSHUR HIGH SCHOOL | FR | K12 | FTX1442A2SA | 412 |  | 2012-05-22 |  | fiber and router needed | K-12 | 2011-11-16 | Y | Y | 25738.26 | N |  | 2012-05-02 | Y | 1980 | 1980 | 2012-07-01 | Complete | 2012-08-10 | Y | Complete | 2012-10-10 | 2012-08-22 | 2012-09-26 | Complete | 2012-09-26 | Complete | 2012-05-22 | Ready | 2012-09-28 | * FBO Notified - Contractor notified WVOT and Frontier that FBO is required at this site. Frontier confirmed the contractor has the network side of build. 6/18/12* *FBO Hold - Pending Lance Assessment and EA - Nick Patel - 7/26/12* *FBO Update - Lance Verified work and approves - 7/27/12* *FBO Update - EA pre-approved. EA Approved as long as contractors stay on the same path as dictated on the EA Map - Teresa Schuller - 7/30/12*
BB49A03 | UPSHUR | BUCKHANNON UPSHUR INTERMEDIATE SCHOOL | FR | K12 | FTX1442AKER | 413 |  |  |  | fiber and router needed | K-12 | 2011-11-06 | Y | Y | 26809.83 | N |  | 2012-05-02 | Y | 3644 | 3644 | 2012-07-01 | 2012-07-01 |  | N | No Build Required |  |  | 2012-06-27 | Complete | 2012-06-27 | TBD |  | Waiting on Router |  | BUCKHANNON ACADEMY ELEMENTARY SCHOOL
BB49A04 | UPSHUR | BUCKHANNON UPSHUR MIDDLE SCHOOL | FR | K12 | FTX1442AKF4 | 414 |  | 2012-09-11 |  | fiber and router needed | K-12 | 2011-05-06 | Y | Y | 5930.7 | N |  | 2011-05-26 | Y | 795 | 795 | 2012-04-01 | Complete | 2011-04-21 | Y | Complete | 2012-07-10 | 2012-07-03 | 2012-07-13 | Complete | 2012-07-13 | Complete | 2012-09-11 | Ready | 2012-09-28 | **LCR WAS LISTED ON MIKE TORDORVICH'S MEMO TO APPROVE 26 LCRs ON 4/15/2011**
BB49A05 | UPSHUR | FRED W EBERLE TECHNICAL CENTER | FR | K12 | FTX1442AKE5 | 415 |  | 2011-08-23 |  | fiber and router needed | K-12 | 2011-05-06 | Y | Y | 2685.6 | N |  | 2011-05-26 | Y | 360 | 360 | 2012-04-01 | Complete | 2011-05-04 | Y | Complete | 2012-06-15 | 2012-04-20 | 2012-05-09 | Complete | 2012-05-09 | Complete | 2011-08-23 | Ready | 2012-05-10 | **LCR WAS LISTED ON MIKE TORDORVICH'S MEMO TO APPROVE 26 LCRs ON 4/15/2011**
BB49A06 | UPSHUR | FRENCH CREEK ELEMENTARY SCHOOL | FR | K12 | FTX1442A1XE | 416 |  | 2012-05-14 |  | fiber and router needed | K-12 | 2011-11-04 | Y | Y | 95137.93 | N |  |  | N |  | TBD | 2012-07-01 | 2012-07-01 |  | N | No Build Required |  |  | 2012-08-22 | Complete | 2012-08-22 | Complete | 2012-05-14 | Ready | 2012-08-24
BB49A07 | UPSHUR | HODGESVILLE ELEMENTARY SCHOOL | FR | K12 | FTX1442A1XH | 417 |  | 2012-05-17 |  | fiber and router needed | K-12 | 2011-11-02 | Y | Y | 43575.12 | N |  | 2012-05-02 | Y | 6360 | 6360 | 2012-07-01 | Complete | 2012-08-10 | Y | Scheduled | 2012-08-16 |  |  | TBD |  | Complete | 2012-05-17 | TBD |  | *FBO Hold - Pending EA Approval - Nick Patel - 7/26/12* *FBO Update - EA Approved - Teresa Schuller - 8/8/12* *FBO Hold - John D requested Lance Review - 8/9/12* *FBO Update - Pending Contractor Justification of work - 8/10/12* *FBO Update - Lance Approved work - 8/23/12*
BB49A08 | UPSHUR | ROCK CAVE ELEMENTARY SCHOOL | FR | K12 | FTX1442A2CD | 418 |  | 2012-05-14 |  | fiber and router needed | K-12 | 2011-11-08 | Y | Y | 39834.02 | N |  | 2012-05-02 | Y | 4608 | 4608 | 2012-07-01 | Complete | 2012-09-04 | Y | Scheduled | 2012-10-02 |  |  | TBD |  | Complete | 2012-05-14 | TBD
BB49A09 | UPSHUR | TENNERTON ELEMENTARY SCHOOL | FR | K12 | FTX1442A1T9 | 420 |  | 2012-05-15 |  | fiber and router needed | K-12 | 2011-11-02 | Y | Y | 11391.45 | N |  | 2012-05-02 | Y | 2118 | 2118 | 2012-07-01 | Complete | 2012-03-15 | Y | Scheduled | 2012-06-12 |  | 2012-09-17 | Complete | 2012-09-17 | Complete | 2012-05-15 | Ready | 2012-09-21 | * FBO Notified - Contractor notified WVOT and Frontier that FBO is required at this site. Frontier confirmed the work is required and agreed to move forward with the FBO. 2/28/12* *FBO On Hold - On Hold until LCR is Approved. - 2/29/12* *FBO Update - LCR is still on Hold for EA - Teresa Schuller - 3/14/12* *FBO Hold - Location will require EA Approval - Lance has assesd information and we have requested more information. 6/29/12* *FBO Update - EA Approved - 7/18/12* *FBO Update - Pending Contractor Justification of work - 8/13/12* *FBO Update - Lance Approved - 8/23/12*
BB49A10 | UPSHUR | UNION ELEMENTARY SCHOOL | FR | K12 | FTX1442A1XG | 421 |  | 2012-05-17 |  | fiber and router needed | K-12 | 2011-10-10 | Y | Y | 22419.03 | N |  | 2012-05-02 | Y | 3800 | 3800 | 2012-07-01 | Complete | 2012-08-10 | Y | Complete | 2012-09-03 | 2012-08-28 |  | TBD |  | Complete | 2012-05-17 | TBD |  | *FBO Hold - Pending EA Approval - Nick Patel - 7/26/12* *FBO Update - EA Approved. Pending John's Approval- Teresa Schuller - 7/31/12* *FBO Hold Update - John D. Request Lance Review - 8/6/12* *FBO Hold Update - Lance Approved - Pending John D. Approval - 8/6/12*
BB49A11 | UPSHUR | WASHINGTON DISTRICT ELEMENTARY SCHOOL | FR | K12 | FTX1442A1TC | 422 |  | 2012-05-15 |  | fiber and router needed | K-12 | 2011-11-08 | Y | Y | 266051.4 | Y | 2012-01-24 |  | N |  | TBD | 2012-07-01 | 2012-07-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2012-05-15 | TBD
BB49A12 | UPSHUR | Charles W. Gibson Public Library | FR | LIB | FTX1439A16J | 804 |  | 2012-06-14 |  | fiber and router needed | WVNET | 2011-11-02 | Y | Y | 16792.63 | N |  | 2011-11-09 | Y | 2545 | 2545 | 2012-05-01 | Complete | 2012-03-02 | Y | Complete | 2012-06-29 | 2012-04-20 | 2012-06-27 | Complete | 2012-06-27 | Complete | 2012-06-14 | Ready | 2012-08-03 | *FBO Update - Backboard Placed for location - $50 charge will be added to final invoice for the placement. Michelle - Gudenkauf - 4/17/12*
BB49A13 | UPSHUR | Upshur County Public Library | FR | LIB | FTX1439AJW9 | 771 |  | 2012-06-14 |  | fiber and router needed | WVNET | 2011-11-02 | Y | Y | 9370.02 | N |  | 2011-11-09 | Y | 410 | 410 | 2012-05-01 | Complete | 2012-03-02 | Y | Complete | 2012-06-27 | 2012-04-20 | 2012-06-28 | Complete | 2012-06-28 | Complete | 2012-06-14 | Ready | 2012-09-21
BB49A14 | UPSHUR | James Curry Public Library | FR | LIB | FTX1439A15R | 837 |  | 2012-09-25 |  | fiber and router needed | WVNET | 2011-11-04 | Y | Y | 68615.17 | N |  |  | N |  | TBD | 2012-07-01 | Complete | 2012-08-10 | Y | Complete | 2012-08-14 | 2012-09-06 |  | TBD |  | Complete | 2012-09-25 | TBD |  | * FBO Notified - Contractor notified WVOT and Frontier that FBO is required at this site. Frontier confirmed the work is required and agreed to move forward with the FBO. 2/28/12* *FBO Hold - Pending EA Approval - Nick Patel - 7/26/12* *FBO Update - EA Approved. Pending John's Approval- Teresa Schuller - 7/31/12* *FBO Hold Update - John D. Request Lance Review - 8/6/12* *FBO Hold - Lance requested we get more information on FBO. Pernding justification for amount of estimate from contractors. - 8/7/12* *FBO Update - Lance Approved Work - Pending John D Approval - 8/21/12*
BB49A15 | UPSHUR | Region 7–Planning and Development Council (Barbour, Braxton Gilmer Lewis, Randolph, Tucker, Upshur) | FR | PDEV | FTX1436A1TR | 1027 | 1ZX560410300480338 | 2011-11-17 |  | fiber and router needed | ? | 2011-11-04 | Y | Y | 19530.88 | N |  | 2012-05-02 | Y | 1749 | 1749 | 2012-07-01 | 2012-07-01 |  | Y | Complete |  | 2012-07-16 |  | TBD |  | Complete | 2011-11-17 | TBD |  | *FBO Cancelled - I spoke with Steve Foster today concerning the conduit placement on this job and was informed that they already have a conduit (w/pull line) in place and it will not be necessary for us to place a new route from the pole to the 2nd story office as per the print. Thanks, Rick Singer - Gudenkauf - 7/16/12*
BB49A16 | UPSHUR | Upshur County Communications | FR | PSAP | FTX1436A1RF | 1388 |  | 1/24/2012 |  | fiber and router needed |  | 2012-01-30 | Y | Y | 30390.64 | N |  | 2012-02-08 | Y | 3734 | 3734 | 2012-07-01 | Complete | 2012-06-07 | N | No Build Required |  |  | 2012-06-07 | Complete | 2012-06-07 | Complete | 1/24/2012 | Ready | 2012-06-08
BB49A17 | UPSHUR | Buckhannon Upshur - Troop 3 State Police | FR | SP | FTX1439A295 | 1106 |  | 2011-12-28 |  | fiber and router needed | State Police | 2011-11-04 | Y | Y | 25738.26 | N |  | 2012-05-02 | Y | 520 | 520 | 2012-08-01 | Complete | 2012-08-10 | Y | Complete | 2012-08-09 | 2012-08-22 |  | TBD |  | Complete | 2011-12-28 | TBD |  | * FBO Notified - Contractor notified WVOT and Frontier that FBO is required at this site. Frontier confirmed the contractor has the network side of build. 6/18/12* *FBO Hold - Pending EA Approval - Nick Patel - 7/26/12* *FBO Update - EA Approved. Pending John's Approval- Teresa Schuller - 7/31/12* *FBO Hold Update - John D. Request Lance Review - 8/6/12* *FBO Update - Lance Review Approved - John D. Approved - 8/6/12*
BB49A18 | UPSHUR | BCI Buckhannon Upshur County State Police | FR | SP | FTX1439A26L | 1092 |  | 2011-12-29 |  | fiber and router needed | State Police | 2012-01-04 | Y | Y | 14863.68 | Y | 2012-01-24 | 2012-05-02 | Y | 1788 | 1788 | 2012-08-01 | Complete | 2012-08-10 | Y | Complete | 2012-08-02 | 2012-08-28 | 2012-09-26 | Complete | 2012-09-26 | Complete | 2011-12-29 | Ready | 2012-09-28 | *FBO Hold - Location Requires EA Approval - Nick Patel - 6/29/12* *FBO Hold - Pending EA Approval - Nick Patel - 7/26/12* *FBO Update - EA Approved - 7/27/12*
BB49A19 | UPSHUR | Clyde Mitchell, M.D., office | REM | TMED | [5 empty] | fiber and router needed | ? | 2011-11-04 | Y | Y | 15279.27 | N |  | 2012-05-02 | Y | 1699 | 1699 | 2012-08-01 | 2012-08-01 |  | N | Removed |  |  |  | Removed | N/A | N/A | N/A | Removed
BB49A20 | UPSHUR | St. Joseph’s Hospital | REM | TMED | [5 empty] | per FTR; site already has fiber- router only | ? |  | N | N/A |  |  |  |  | N/A |  | 0 |  | Complete |  |  | Removed |  |  |  | Removed | N/A | N/A | N/A | Removed |  | *Router Update - Brian Williams - Technical Director declined router to this location. Wishes to speak to a member of the GIT about the project. - Nick Patel - 5/12/12*
BB49A21 | UPSHUR | St-Josephs-Hospital, Hospital Campus | REM | TMED | [5 empty] | per FTR; site already has fiber- router only | ? |  | N | N/A |  |  |  |  | N/A |  | 0 |  | Complete |  |  | Removed |  |  |  | Removed | N/A | N/A | N/A | Removed |  | *Router Update - Brian Williams - Technical Director declined router to this location. Wishes to speak to a member of the GIT about the project. - Nick Patel - 5/12/12*
BB49A22 | UPSHUR | Tri-County Care Xpress | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB49A23 | UPSHUR | Tri-County Health Clinic | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB50A01 | WAYNE | Wayne County Courthouse | FR | CHOUSE | FTX1441A0PT |  |  |  |  | fiber and router needed | WVNET | 2011-11-08 | Y | Y |  | N |  | 2011-11-10 | Y | 1338 | 1338 | 2012-06-01 | 2012-06-01 |  | N | TBD |  |  |  | TBD |  | TBD |  | TBD
BB50A02 | WAYNE | Wayne County Youth Reporting | FR | DJS | FTX1444AJ1E | 481 |  |  |  | fiber and router needed | WVOT | 2011-10-03 | Y | Y | 8738.8 | Y | 2012-02-01 | 2012-03-07 | Y | 410 | 410 | 2012-10-01 | 2012-10-01 |  | Y | TBD |  |  |  | TBD |  | TBD |  | TBD |  | Can we get with Frontier to be sure they use the new underground conduits for the fiber installation? They would need to unfasten it from the current pole and drop back to the previous pole. The existing voice and data lines will also be moved. Doug at Valley Head Library is trying to get this done as soon as possible, but he said it could be as long as mid November before it is all completed.
BB50A03 | WAYNE | BUFFALO ELEMENTARY SCHOOL | RO | K12 | FTX1443A23H | 79 |  | 2011-06-15 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-06-15 | Ready | 2012-01-05
BB50A04 | WAYNE | BUFFALO MIDDLE SCHOOL | RO | K12 | FTX1437AJHN | 80 |  | 2011-06-15 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-06-15 | Ready | 2012-01-05
BB50A05 | WAYNE | CEREDO ELEMENTARY SCHOOL | RO | K12 | FTX1437AJHY | 81 |  | 2011-07-06 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-07-06 | Ready | 2012-01-05
BB50A06 | WAYNE | CEREDO KENOVA MIDDLE SCHOOL | RO | K12 | FTX1437A1PK | 82 |  | 2011-07-06 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-07-06 | Ready | 2012-01-05
BB50A07 | WAYNE | CRUM ELEMENTARY SCHOOL | RO | K12 | FTX1437A1NX | 83 |  | 2011-07-05 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-07-05 | Ready | 2012-01-05
BB50A08 | WAYNE | CRUM MIDDLE SCHOOL | RO | K12 | FTX1437A1R1 | 84 |  | 2011-07-05 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-07-05 | Ready | 2012-01-05
BB50A09 | WAYNE | DUNLOW ELEMENTARY SCHOOL | FR | K12 | FTX1443AK5Q | 85 |  | 2012-02-03 |  | fiber and router needed | K-12 | 2011-10-03 | Y | Y | 35790.61 | N |  | 2012-03-07 | Y | 3618 | 3618 | 2012-10-01 | Complete | 2012-05-30 | Y | TBD |  |  |  | TBD |  | Complete | 2012-02-03 | TBD |  | *FBO Notified - Contractor notified WVOT and Frontier that FBO is required at this site. Frontier confirmed the work is required and agreed to move forward with the FBO - 5/31/12* *FBO Hold - Pending Lance Review - 9/4/12*
BB50A10 | WAYNE | EAST LYNN ELEMENTARY SCHOOL | RO | K12 | FTX1443AK5M | 86 |  | 2011-07-07 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-07-07 | Ready | 2012-01-05
BB50A11 | WAYNE | FORT GAY ELEMENTARY SCHOOL | RO | K12 | FTX1437A1Q4 | 87 |  | 2011-07-19 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-07-19 | Ready | 2012-01-05
BB50A12 | WAYNE | FORT GAY MIDDLE SCHOOL | RO | K12 | FTX1437A1Q5 | 88 |  | 2011-07-08 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-07-08 | Ready | 2012-01-05
BB50A13 | WAYNE | GENOA ELEMENTARY SCHOOL | RO | K12 | FTX1437AJJE | 89 |  | 2011-07-08 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-07-08 | Ready | 2012-01-05
BB50A14 | WAYNE | KENOVA ELEMENTARY SCHOOL | FR | K12 | FTX1437A1P1 | 90 |  | 2011-08-17 |  | fiber and router needed | K-12 | 2011-07-05 | Y | Y | 57494.25 | N |  | 2011-07-06 | Y | 1745 | 1745 | 2011-08-22 | Complete | 2011-08-12 | N | TBD |  |  | 2011-08-22 | Complete | 2011-08-22 | Complete | 2011-08-17 | Ready | 2012-01-05
BB50A15 | WAYNE | LAVALETTE ELEMENTARY SCHOOL | RO | K12 | FTX1437A1P2 | 91 |  | 2011-06-07 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-06-07 | Ready | 2012-01-05
BB50A16 | WAYNE | PRICHARD ELEMENTARY SCHOOL | RO | K12 | FTX1443AK51 | 92 |  | 2011-07-08 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-07-08 | Ready | 2012-02-02
BB50A17 | WAYNE | SPRING VALLEY HIGH SCHOOL | RO | K12 | FTX1443AK5B | 93 |  | 2011-06-07 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-06-07 | Ready | 2012-01-05
BB50A18 | WAYNE | TOLSIA HIGH SCHOOL | RO | K12 | FTX1443A23P | 94 |  | 2011-07-08 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-07-08 | Ready | 2012-01-05
BB50A19 | WAYNE | VINSON MIDDLE SCHOOL | RO | K12 | FTX1443AK43 | 95 |  | 2011-07-06 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-07-06 | Ready | 2012-01-05
BB50A20 | WAYNE | WAYNE ELEMENTARY | RO | K12 | FTX1443AK3S | 96 |  | 2011-07-06 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-07-06 | Ready | 2012-01-05
BB50A21 | WAYNE | WAYNE HIGH SCHOOL | RO | K12 | FTX1443A23V | 97 |  | 2011-07-06 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-07-06 | Ready | 2012-01-05
BB50A22 | WAYNE | WAYNE MIDDLE SCHOOL | RO | K12 | FTX1443AK5K | 98 |  | 2011-07-06 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-07-06 | Ready | 2012-01-05
BB50A23 | WAYNE | WAYNE PRE-K | FR | K12 | FTX1443AK3W | 99 |  | 2011-07-07 |  | fiber and router needed | K-12 | 2011-10-03 | Y | Y | 11518.46 | N |  | 2012-03-07 | Y | 1104 | 1104 | 2012-10-01 | 2012-10-01 | N | N | No Build Required |  |  |  | TBD |  | Complete | 2011-07-07 | TBD |  | * FBO Notified - Contractor notified WVOT and Frontier that FBO is required at this site. Frontier confirmed the contractor has the network side of build. 8/20/12*
BB50A24 | WAYNE | Fort Gay Public Library | FR | LIB | FTX1439A18L | 752 |  | 2012-04-05 |  | fiber and router needed | WVNET | 2011-08-29 | Y | Y | 114029.32 | Y | 2011-08-31 | 2012-03-07 | Y | 2909 | 2909 | 2012-10-01 | 2012-10-01 |  | Y | Scheduled | 2012-07-09 |  |  | TBD |  | Complete | 2012-04-05 | TBD |  | *FBO Notified - Contractor notified WVOT and Frontier that FBO is required at this site. Frontier confirmed the work is required and agreed to move forward with the FBO - 5/31/12*
BB50A25 | WAYNE | Wayne County Public Library | FR | LIB | FTX1439A15U | 762 |  | 2012-04-04 |  | fiber and router needed | WVNET | 2011-08-29 | Y | Y | 48036.35 | Y | 2/1/2012; 2/2/2012 | 2012-03-07 | Y | 1264 | 1264 | 2012-10-01 | Complete | 2012-04-25 | N | No Build Required |  |  | 2012-04-25 | Complete | 2012-04-25 | Complete | 2012-04-04 | Ready | 2012-04-27
BB50A26 | WAYNE | Wayne Public Library | FR | LIB | FTX1439A18F | 761 |  | 2012-04-24 |  | fiber and router needed | WVNET | 2011-10-03 | Y | Y | 7270.25 | N |  | 2012-03-07 | Y | 400 | 400 | 2012-10-01 | Complete | 2012-05-30 | Y | TBD |  |  |  | TBD |  | Complete | 2012-04-24 | TBD
BB50A27 | WAYNE | Wayne County 9-1-1 | FR | PSAP | FTX1436AJTL | 1380 |  | 2012-01-30 |  | fiber and router needed |  | 2011-10-03 | Y | Y | 43832.98 | Y | 2012-02-01 | 2012-03-07 | Y | 3298 | 3298 | 2012-10-01 | Complete | 2012-05-30 | Y | TBD |  |  |  | TBD |  | Complete | 2012-01-30 | TBD
BB50A28 | WAYNE | Wayne Wayne - Troop 5 State Police | FR | SP | FTX1439AKL7 | 1107 |  | 2012-01-20 |  | fiber and router needed | State Police | 2011-10-03 | Y | Y | 50130.81 | Y | 2012-02-01 | 2012-03-07 | Y | 5821 | 5821 | 2012-10-01 | 2012-10-01 | N | N | No Build Required |  |  |  | TBD |  | Complete | 2012-01-20 | TBD
BB50A29 | WAYNE | Valley Health - Tolsia High Health Center | RO | TMED | FTX1443A290 | 908 | 1ZX560410300485931 | 2012-02-16 |  | per FTR; site already has fiber- router only | ? |  | N | N/A |  |  |  |  | N/A |  | 0 |  | Complete |  |  | No Build Required |  |  |  | Complete | N/A | Complete | 2012-02-16 | Ready | 2012-02-16
BB50A30 | WAYNE | Valley Health - Fort Gay | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB50A31 | WAYNE | Valley Health - Wayne at Wayne High School | RO | TMED | FTX1436AKRJ | 897 | 1ZX560410300484441 | 2012-02-16 |  | per FTR; site already has fiber- router only | ? |  | N | N/A |  |  |  |  | N/A |  | 0 |  | Complete |  |  | No Build Required |  |  |  | Complete | N/A | Complete | 2012-02-16 | Ready | 2012-02-16
BB50A32 | WAYNE | Valley Health - Wayne | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB50A33 | WAYNE | Valley Health - Wayne WIC | FR | TMED | [5 empty] | fiber and router needed | ? | 2011-11-18 | Y | Y | 7001.9 | N |  | 2011-12-08 | Y | 704 | 704 | 2012-10-01 | Complete | 2012-05-30 | Y | TBD |  |  |  | TBD |  | TBD |  | TBD
BB51A01 | WEBSTER | Webster County Courthouse | FR | CHOUSE | FTX1441A0QP |  |  |  |  | fiber and router needed | WVNET | 2011-10-31 | Y | Y | 5952 | N |  | 2011-11-07 | Y | 674 | 674 | 2012-05-01 | Complete | 2012-04-12 | Y | TBD |  |  |  | TBD |  | TBD |  | TBD
BB51A02 | WEBSTER | *GLADE ELEMENTARY & MIDDLE SCHOOLS | RO | K12 | FTX1438A2CE | 229 |  | 2011-10-17 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-10-17 | Ready | 2012-01-05
BB51A03 | WEBSTER | DIANA ELEMENTARY SCHOOL | RO | K12 | FTX1442A2BZ | 230 |  | 2012-04-02 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2012-04-02 | Ready | 2012-04-16
BB51A04 | WEBSTER | HACKER VALLEY ELEMENTARY SCHOOL | RO | K12 | FTX1442A1HJ | 231 |  | 2011-10-05 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-10-05 | Ready | 2012-01-05
BB51A05 | WEBSTER | WEBSTER COUNTY HIGH SCHOOL | RO | K12 | FTX1442A1ZH | 232 |  | 2011-10-05 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-10-05 | Ready | 2012-01-05
BB51A06 | WEBSTER | WEBSTER SPRINGS ELEMENTARY SCHOOL | RO | K12 | FTX1442A1TL | 233 |  | 2011-09-27 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-09-27 | Ready | 2012-01-05
BB51A07 | WEBSTER | Cowen Public Library | FR | LIB | FTX1439A13Y | 796 |  | 2012-06-04 |  | fiber and router needed | WVNET | 2011-10-31 | Y | Y | 4465 | N |  | 2012-02-15 | Y | 490 | 490 | 2012-08-01 | Complete | 2012-06-10 | Y | Complete | 2012-07-11 | 2012-07-25 |  | TBD |  | Complete | 2012-06-04 | TBD
BB51A08 | WEBSTER | Webster-Addison Public Library | FR | LIB | FTX1439AK01 | 795 |  | 2012-06-03 |  | fiber and router needed | WVNET | 2011-10-31 | Y | Y | 3009 | N |  | 2012-01-05 | Y | 259 | 259 | 2012-08-01 | 2012-08-01 |  | Y | Scheduled | 2012-08-03 |  |  | TBD |  | Complete | 2012-06-03 | TBD |  | * FBO Notified - Contractor notified WVOT and Frontier that FBO is required at this site. Frontier confirmed the work is required and agreed to move forward with the FBO - 5/29/12*
BB51A09 | WEBSTER | Emergency Ops Center | FR | PSAP | FTX1436AJTK | 1383 |  | 2012-01-31 |  | fiber and router needed |  | 2011-10-31 | Y | Y | 2816 | N |  | 2011-11-07 | Y | 277 | 277 | 2012-05-01 | Complete | 2012-04-05 | Y | Complete | 2012-05-09 | 2012-07-25 |  | TBD |  | Complete | 2012-01-31 | TBD
BB51A10 | WEBSTER | Webster Springs - Webster - Troop 3 State Police | FR | SP | FTX1439A24N | 1063 |  | 2012-01-19 |  | fiber and router needed | State Police | 2011-10-31 | Y | Y | 3956 | N |  | 2011-11-07 | Y | 451 | 451 | 2012-05-01 | Complete | 2012-09-17 | N | No Build Required |  |  | 2012-09-17 | Complete | 2012-09-17 | Complete | 2012-01-19 | Ready | 2012-09-21
BB51A11 | WEBSTER | Camden on Gauley Medical Center | FR | TMED | FTX1436A1TS | 888 | 1ZX560410300480347 | 2011-11-29 |  | fiber and router needed | ? | 2011-11-01 | Y | Y | $264,578 ($247.908.00) | Y | 12/7/2011; 12/21/2011 | 2012-02-15 | Y | 33197 | 33197 | 2012-08-01 | 2012-08-01 |  | N | No Build Required |  |  |  | TBD |  | Complete | 2011-11-29 | TBD
BB51A12 | WEBSTER | Webster County Memorial Hospital | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB51A13 | WEBSTER | Webster Memorial Hospital | FR | TMED | FTX1436A1T3 | 887 | 1ZX560410300480436 | 2011-11-21 |  | fiber and router needed | ? | 2011-10-31 | Y | Y | 30353 | N |  | 2011-11-07 | Y | 3961 | 3961 | 2012-05-01 | Complete | 2012-03-16 | Y | Complete | 2012-05-09 | 2012-05-14 |  | TBD |  | Complete | 2011-11-21 | TBD
BB52A01 | WETZEL | Wetzel County Courthouse | FR | CHOUSE | FTX1441A0QV |  |  |  |  | fiber and router needed | WVNET | 2011-10-04 | Y | Y | 22660 | Y | 2012-01-17 | 2012-03-07 | Y | 3050 | 3050 | 2012-03-01 | Complete | 2012-04-04 | Y | Complete | 2012-09-21 | 2012-08-14 | 2012-08-31 | Complete | 2012-08-31 | TBD |  | Waiting on Router
BB52A02 | WETZEL | HUNDRED HIGH SCHOOL | FR | K12 | FTX1443A23G | 282 |  | 2011-06-24 |  | fiber and router needed | K-12 | 2011-10-04 | Y | Y | 39163.25 | N |  | 2011-10-18 | Y | 4650 | 4650 | 2012-02-01 | Complete | 2012-03-15 | N | No Build Required |  |  | 2012-03-30 | Complete | 2012-03-30 | Complete | 2011-06-24 | Ready | 2012-04-05
BB52A03 | WETZEL | LONG DRAIN SCHOOL | FR | K12 | FTX1443AK4H | 283 |  | 2011-07-14 |  | fiber and router needed | K-12 | 2011-10-04 | Y | Y | 7334.24 | Y | 10/17/2011; 10/24/11 | 2011-10-31 | Y | 900 | 900 | 2012-03-01 | Complete | 2012-02-13 | N | No Build Required |  |  | 2012-02-13 | Complete | 2012-02-13 | Complete | 2011-07-14 | Ready | 2012-02-17
BB52A04 | WETZEL | MAGNOLIA HIGH SCHOOL | FR | K12 | FTX1443AK53 | 284 |  | 2011-07-18 |  | fiber and router needed | K-12 | 2011-10-04 | Y | Y | $ 39,630.00 ($30,765.03) | Y | 10/17/2011; 1/17/2012; 1/19/2012; 4/26/2012 | 3/7/2012; 5/10/12 | Y | 6495 | 6495 | 2012-03-01 | Complete | 2012-09-13 | Y | Complete | 2012-06-25 | 2012-09-06 | 2012-09-13 | Complete | 2012-09-13 | Complete | 2011-07-18 | Ready | 2012-09-21 | * FBO Notified - Contractor notified WVOT and Frontier that FBO is required at this site. Frontier confirmed the work is required and agreed to move forward with the FBO - 5/29/12* *FBO Hold - Pending Lance Review - 6/29/12* *FBO Update - Pending Contractor Justification of work - 7/26/12* *FBO Update - Lance Approved work - 8/23/12*
BB52A05 | WETZEL | NEW MARTINSVILLE SCHOOL | FR | K12 | FTX1443A241 | 285 |  | 2011-08-04 |  | fiber and router needed | K-12 | 2011-10-04 | Y | Y | 18337.63 | Y | 10/17/2011; 1/17/2012; 1/19/2012 | 2012-03-07 | Y | 1750 | 1750 | 2011-12-01 | Complete | 2011-11-19 | Y | Complete |  | 2012-04-17 | 2012-04-18 | Complete | 2012-04-18 | Complete | 2011-08-04 | Ready | 2012-04-19 | *FBO On Hold - Until LCR approved - 1/12/12* *FBO Update - LCR Approved 3/7/12* *FBO No Longer Required - FBO Completed by the location - Rick Singer - 3/17/12* *FBO Update - Mark McKenzie Confirmed - 4/17/12*
BB52A06 | WETZEL | PADEN CITY ELEMENTARY SCHOOL | FR | K12 | FTX1443AK4X | 286 |  | 2011-07-18 |  | fiber and router needed | K-12 | 2011-11-06 | Y | Y | 16632.49 | N |  | 2011-11-09 | Y | 4500 | 4500 | 2012-01-01 | Complete | 2011-12-02 | Y | Complete | 2012-02-07 | 2012-02-21 | 2012-03-12 | Complete | 2012-03-12 | Complete | 2011-07-18 | Ready | 2012-03-16
BB52A07 | WETZEL | PADEN CITY HIGH SCHOOL | FR | K12 | FTX1443AK5S | 287 |  | 2011-07-18 |  | fiber and router needed | K-12 | 2011-11-02 | Y | Y | 11689.74 | N |  | 2011-11-09 | Y | 1463 | 1463 | 2012-01-01 | Complete | 2011-12-02 | Y | Complete | 2012-07-13 | 2012-04-20 | 2012-04-26 | Complete | 2012-04-26 | Complete | 2011-07-18 | Ready | 2012-05-04 | *FBO Not Required - Locations have already completed the FBO to complete by owner to Demarc. - 1/3/12* *FBO Hold - FBO was done to the wrong room. - Frontier - Rob Hugart - 3/30/12* *FBO Update - Spoke to on site Contact - Mrs. Hallzie - Stated the Demarc is currently in the correct location. however they will be moving their server to a new location in June 2012. They want the Demarc in the new location.* *FBO Update - Informed Contractors (Gudenkauf) to go out to site and complete the location as dictated. No extended Demarc. - John Dunlap - 4/2/12* FBO - Update - Instructed Gudenkauf to return out to location and complete the work at the current Demarc. No Extended Demarcs. - Nick Patel - 4/6/12*
BB52A08 | WETZEL | SHORT LINE SCHOOL | FR | K12 | FTX1443A23S | 288 |  | 2011-07-18 |  | fiber and router needed | K-12 | 2011-10-04 | Y | Y | 8145.45 | Y | 2011-10-17 | 2011-10-31 | Y | 1450 | 1450 | 2012-03-01 | Complete | 2011-12-29 | Y | Complete |  | 2011-12-29 | 2012-02-13 | Complete | 2012-02-13 | Complete | 2011-07-18 | Ready | 2012-02-17 | *FBO Not Required. Board of Education completed FBO Work on their own - Completed on 12/29/11 - 01/23/12*
BB52A09 | WETZEL | VALLEY HIGH SCHOOL | FR | K12 | FTX1442A2DR | 289 |  | 2011-07-14 |  | fiber and router needed | K-12 | 2011-10-04 | Y | Y | 13570 | N |  | 2011-10-18 | Y | 1700 | 1700 | 2012-03-01 | Complete | 2012-02-07 | N | No Build Required |  |  | 2012-02-09 | Complete | 2012-02-09 | Complete | 2011-07-14 | Ready | 2012-02-10
BB52A10 | WETZEL | WETZEL CO. CTR. FOR FAMILIES & CHILDREN | FR | K12 | FTX1442AKF6 | 290 |  | 2011-07-29 |  | fiber and router needed | K-12 | 2011-10-04 | Y | Y | $ 23,410.53 ($15036.53) | Y | 1/17/2012; 4/19/2012 | 3/7/2012; 5/2/2012 | Y | 1147 | 1147 | 2012-03-01 | Complete | 2012-06-21 | N | No Build Required |  |  | 2012-06-21 | Complete | 2012-06-21 | Complete | 2011-07-29 | Ready | 2012-06-22 | *FBO - Cancelled due to location completing FBO on own - 01/05/12*
BB52A11 | WETZEL | New Martinsville Public Library | FR | LIB | FTX1439A15K | 726 |  | 2012-01-24 |  | fiber and router needed | WVNET | 2011-10-04 | Y | Y | 20470.39 | N |  | 2012-03-15 | Y | 1500 | 1500 | 2011-12-01 | Complete | 2011-11-16 | Y | Complete | 2012-07-09 | 2012-04-30 | 2012-04-27 | Complete | 2012-04-27 | Complete | 2012-01-24 | Ready | 2012-05-04 | *FBO On Hold - Until LCR approved - 1/12/12* *FBO Update - LCR was Missing - Has been re-submitted - 3.14.12 - Nick Patel* *FBO Update - LCR has been approved and Contractor has received update information - Nick Patel - 3/28/12* FBO Update - Estimate was off by $50.00 due to backboard placement.
BB52A12 | WETZEL | Paden City Public Library | FR | LIB | FTX1439A18K | 728 |  | 2012-01-23 |  | same as BB48A07 | WVNET | 2011-11-02 | Y | Y | 7473.94 | N |  | 2012-01-05 | Y | 799 | 799 | 2012-03-01 | Complete | 2012-02-29 | Y | Complete | 2012-07-02 | 2012-04-20 | 2012-04-23 | Complete | 2012-04-23 | Complete | 2012-01-23 | Ready | 2012-04-27 | *FBO Update - Backboard Placed for location - $50 charge will be added to final invoice for the placement. Michelle - Gudenkauf - 4/17/12*
BB52A13 | WETZEL | Hundred Public Library | FR | LIB | FTX1439A18U | 725 |  | 2012-01-24 |  | fiber and router needed | WVNET | 2011-10-04 | Y | Y | 3999.3 | Y | 2011-10-17 | 2011-10-31 | Y | 405 | 405 | 2012-02-01 | Complete | 2012-03-02 | Y | Complete | 2012-02-23 | 2012-02-27 | 2012-03-30 | Complete | 2012-03-30 | Complete | 2012-01-24 | Ready | 2012-04-05 | * FBO Notified - Contractor notified WVOT and Frontier that FBO is required at this site. Frontier confirmed the work is required and agreed to move forward with the FBO. 2/2/12* *FBO Revised - Revised Date of Completion to 2/23/12*
BB52A14 | WETZEL | Pine Grove Public Library | FR | LIB | FTX1439A15C | 729 |  | 2012-01-24 |  | fiber and router needed | WVNET | 2012-02-02 | Y | Y | 5521 | N |  | 2012-02-08 | Y | 350 | 350 | 2012-03-01 | Complete | 2012-03-30 | Y | Complete | 2012-05-04 | 2012-03-23 | 2012-03-30 | Complete | 2012-03-30 | Complete | 2012-01-24 | Ready | 2012-04-05 | * FBO Notified - Contractor notified WVOT and Frontier that FBO is required at this site. Frontier confirmed the work is required and agreed to move forward with the FBO. 2/21/12*
BB52A15 | WETZEL | Wetzel County 911 | FR | PSAP | FTX1436AJTT | 1371 |  | 2012-01-18 |  | fiber and router needed |  | 2011-10-04 | Y | Y | 12737.63 | N |  | 2011-10-18 | Y | 1750 | 1750 | 2011-12-01 | Complete | 2011-11-11 | N | No Build Required |  |  | 2012-03-02 | Complete | 2012-03-02 | Complete | 2012-01-18 | Ready | 2012-03-02
BB52A16 | WETZEL | Hundred Wetzel - Troop 1 State Police | FR | SP | FTX1439A24V | 1066 |  | 2011-12-28 |  | fiber and router needed | State Police | 2011-10-04 | Y | Y | 10005.12 | N |  | 2011-10-18 | Y | 1085 | 1085 | 2012-02-01 | Complete | 2012-03-01 | Y | Complete | 2012-03-29 | 2012-03-14 | 2012-03-30 | Complete | 2012-03-30 | Complete | 2011-12-28 | Ready | 2012-04-05
BB52A17 | WETZEL | Community Health Center of North-Eastern Wetzel County | REM | TMED |  |  |  |  | D | PER FTR; THIS CAI WAS APART OF TMED GRANT AWARDED TO FTR. REMOVE FROM LIST. | ? |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Removed | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A | N/A | N/A | Removed | N/A
BB53A01 | WIRT | Wirt County Courthouse | FR | CHOUSE | FTX1441A0QF | 592 | Delivered and Installed by Tech | 2012-06-22 |  | fiber and router needed | WVNET | 2011-06-07 | Y | Y | 8361.3 | N |  | 2011-06-30 | Y | 250 | 250 | 2011-08-15 | Complete | 2011-08-02 | N | No Build Required |  |  | 2011-08-15 | Complete | 2011-08-15 | Complete | 2012-06-22 | Ready | 2012-08-10
BB53A02 | WIRT | Dora Bee Woodyard Memorial Library | FR | LIB | FTX1439AJWA | 675 |  | 2011-10-06 |  | fiber and router needed | WVNET | 2011-05-23 | Y | Y | 7820 | Y | 2011-06-13 | 2011-07-05 | Y | 500 | 500 | 2011-08-15 | Complete | 2011-08-15 | N | No Build Required |  |  | 2011-08-15 | Complete | 2011-08-15 | Complete | 2011-10-06 | Ready | 2012-01-05
BB53A03 | WIRT | Elizabeth Wirt - Troop 4 State Police | FR | SP | FTX1439A254 | 1072 |  | 2012-01-25 |  | fiber and router needed | State Police | 2011-05-23 | Y | Y | 14215 | Y | 2011-06-13 | 2011-07-05 | Y | 1500 | 1500 | 2011-08-15 | Complete | 2011-08-15 | N | No Build Required |  |  | 2011-08-15 | Complete | 2011-08-15 | Complete | 2012-01-25 | Ready | 2012-02-02 | 12/16/11: MARK MCKENZIE SENT A REVISED LCR WITH ESTIMATED COST CHANGED TO $13,265.00, STATING REASON FOR PRICE DIFFERENCE SHOULD READ "CONSTRUCTION HOURS LESS THAN EXPECTED".
BB54A01 | WOOD | Wood County Courthouse | FR | CHOUSE | FTX1441A0PX |  |  |  |  | fiber and router needed | WVNET | 2011-06-07 | Y | Y | 7053.07 | N |  | 2011-06-29 | Y | 1068 | 1068 | 2011-12-01 | Complete | 2011-11-05 | N | No Build Required |  |  | 2011-11-05 | Complete | 2011-11-05 | TBD |  | Waiting on Router |  | FTX1441A0PX was changed to FTX1444AHKC due to a transfer in a router between WVOT and CHOUSE.
BB54A02 | WOOD | Parkersburg Parole Office | REM | CORR | FTX1444AHL1 | 637 |  |  |  | fiber and router needed | WVOT | 2011-06-07 | Y | Y | 21825.2 | N |  | 2011-06-29 | Y | 4893 | 4893 | 2012-03-01 | Complete | 2011-10-17 | Y | Removed |  | 2012-03-06 |  | Removed | N/A | N/A | N/A | Removed |  | *LCR Update - FBO Hold -Location is closing - Will be informing us with the new address soon - Mike Coleman - Nick Patel - 3/5/12* *LCR Update - FBO No Longer required - Location is going to be close and integrated into BB54A03 - Parkersburg Work Release Center. BB54A02 Will be Removed from Project build. - John Dunlap - 3/6/12* *Router Update - Router will be reassociated to another site. Will contact Mike Coleman - Corrections - for a new site allocation. The new site will be at least Improved Services - Nick Patel - 3/6/12*
BB54A03 | WOOD | Parkersburg Work Release Center | FR | CORR | FTX1444AHKM | 638 | 1ZX560410300523229 | 2012-05-17 |  | fiber and router needed | WVOT | 2011-06-07 | Y | Y | 42131.97 | N |  | 2011-06-29 | Y | 10983 | 10983 | 2011-10-18 | Complete | 2011-10-17 | N | No Build Required |  |  | 2011-10-18 | Complete | 2011-10-18 | Complete | 2012-05-17 | Ready
BB54A04 | WOOD | Wood County Youth Reporting | FR | DJS | FTX1443A29R | 482 |  |  |  | fiber and router needed | WVOT | 2011-06-07 | Y | Y | 15196.3 | N |  | 2011-09-14 | Y | 3730 | 3730 | 2012-03-01 | Complete | 2011-10-19 | Y | Complete | 2012-05-02 | 2012-04-02 | 2012-04-16 | Complete | 2012-04-16 | TBD |  | Waiting on Router
BB54A05 | WOOD | ADULT EDUCATION CENTER | RO | K12 | FTX1442A1ZC | 248 |  | 2012-02-09 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 |  | Complete |  | N/A | No Build Required | N/A | N/A |  | Complete | N/A | Complete | 2012-02-09 | Ready | 2012-02-09
BB54A06 | WOOD | WVIEP - LORRIE YEAGER JUVENILE CENTER DJS | FR | K12 | FTX1442A1XB | 250 |  | 2012-05-09 |  | fiber and router needed | K-12 | 2011-06-07 | Y | Y | 7424.16 | N |  | 2011-06-29 | Y | 2817 | 2817 | 2011-08-18 | Complete | 2011-08-18 | N | No Build Required |  |  | 2011-08-18 | Complete | 2011-08-18 | Complete | 2012-05-09 | Ready | 2012-05-18
BB54A07 | WOOD | WVIEP - PRESSLEY RIDGE At White Oak Village | FR | K12 | FTX1442A1XC | 251 |  | 2012-05-09 |  | fiber and router needed | K-12 | 2011-06-08 | Y | Y | 81402.41 | N |  | 2011-09-14 | Y | 10197 | 10197 | 2012-03-01 | Complete | 2012-02-29 | N | No Build Required |  |  | 2012-02-29 | Complete | 2012-02-29 | Complete | 2012-05-09 | Ready | 2012-05-18
BB54A08 | WOOD | Parkersburg/Wood Co. Public Library | FR | LIB | FTX1439A175 | 672 |  | 2011-08-18 |  | fiber and router needed | WVNET | 2011-06-07 | Y | Y | 6160.17 | N |  | 2011-06-29 | Y | 1188 | 1188 | 2012-02-01 | Complete | 2012-01-23 | N | No Build Required |  |  | 2012-01-23 | Complete | 2012-01-23 | Complete | 2011-08-18 | Ready | 2012-01-26
BB54A09 | WOOD | South Parkersburg Public Library | FR | LIB | FTX1439A14A | 756 |  | 2012-03-06 |  | fiber and router needed | WVNET | 2011-05-27 | Y | Y | 8496.48 | Y | 2011-06-13 | 2011-09-14 | Y | 858 | 858 | 2012-03-01 | Complete | 2011-10-20 | Y | Complete | 2012-05-08 | 2012-04-02 | 2012-04-13 | Complete | 2012-04-13 | Complete | 2012-03-06 | Ready | 2012-04-19
BB54A10 | WOOD | Waverly Public Library | FR | LIB | FTX1439AJVN | 716 |  | 2012-01-03 |  | fiber and router needed | WVNET | 2011-06-08 | Y | Y | 45114.09 | N |  | 2011-06-29 | Y | 14723 | 14723 | 2012-03-01 | Complete | 2011-08-31 | Y | Complete | 2012-05-07 | 2012-04-02 | 2012-04-12 | Complete | 2012-04-12 | Complete | 2012-01-03 | Ready | 2012-04-19
BB54A11 | WOOD | Vienna Public Library | FR | LIB | FTX1439A161 | 670 |  | 2011-08-09 |  | fiber and router needed | WVNET | 2011-06-08 | Y | Y | 3512.14 | N |  | 2011-06-29 | Y | 325 | 325 | 2011-09-26 | Complete | 2011-09-26 | N | No Build Required |  |  | 2011-09-26 | Complete | 2011-09-26 | Complete | 2011-08-09 | Ready | 2012-01-05
BB54A12 | WOOD | Williamstown Public Library | FR | LIB | FTX1439A15V | 68 |  | 2011-07-05 |  | fiber and router needed | WVNET | 2011-05-27 | Y | Y | 8509.28 | Y | 2011-06-13 | 2011-07-05 | Y | 2991 | 2991 | 2012-03-01 | Complete | 2011-08-15 | Y | Complete | 2012-05-03 | 2012-04-02 | 2012-04-16 | Complete | 2012-04-16 | Complete | 2011-07-05 | Ready | 2012-04-19
BB54A13 | WOOD | Region 5–Mid-Ohio Valley Regional Council (Calhoun, Jackson, Pleasants, Ritchie, Roane, Tyler, Wirt, Wood) | FR | PDEV | FTX1436A2BC | 1021 | 1ZX560410300469351 | 2011-10-05 |  | fiber and router needed | ? | 2011-06-08 | Y | Y | 5440.31 | N |  | 2011-06-29 | Y | 724 | 724 | 2012-03-01 | Complete | 2011-08-15 | Y | TBD |  |  |  | TBD |  | Complete | 2011-10-05 | TBD |  | *FBO Hold - Building owner is going to work out access issues with their facility. Paul Hoblitzell - 304-481-0332, 304-422-3519 - 3/5/12* *FBO Update - Spoke with Paul Hoblitzell - Building owner that has access to the demarc - Stated that Jim Mylott does not wish to have fiber pulled to their location due to the State department pushing them too hard on the issue. - 3/21/12* *FBO Update - Information has been relayed to the Tiger Team that Jim Mylott of Region 5 no longer wishes to receive Fiber from the BTOP Project. Has been noted in the Minutes of the meeting. Further action will be discussed by the GIT. - Nick Patel - 3/27/12*
BB54A14 | WOOD | Central Telcom Center | FR | PSAP | FTX1436AJTS | 1373 |  | 1/17/2012 |  | fiber and router needed |  | 2011-06-07 | Y | Y | 10944.03 | N |  | 2011-09-14 | Y | 4270 | 4270 | 2011-10-20 | Complete | 2011-10-20 | N | No Build Required |  |  | 2011-10-20 | Complete | 2011-10-20 | Complete | 1/17/2012 | Ready | 2012-02-02
BB54A15 | WOOD | Parkersburg Wood - Troop 4 State Police | FR | SP | FTX1439AKL8 | 1108 |  | 2012-01-25 |  | fiber and router needed | State Police | 2011-06-08 | Y | Y | 74982.17 | N |  | 2011-09-14 | Y | 19258 | 19258 | 2012-03-01 | Complete | 2012-01-19 | N | No Build Required |  |  | 2012-01-19 | Complete | 2012-01-19 | Complete | 2012-01-25 | Ready | 2012-02-02
BB54A16 | WOOD | BCI Parkersburg Wood County State Police | FR | SP | FTX1439A25H | 1077 |  | 2012-01-25 |  | fiber and router needed | State Police | 2011-06-07 | Y | Y | 7222.95 | N |  | 2011-06-29 | Y | 1770 | 1770 | 2011-09-29 | Complete | 2011-09-28 | N | No Build Required |  |  | 2011-09-29 | Complete | 2011-09-29 | Complete | 2012-01-25 | Ready | 2012-02-02
BB55A01 | WYOMING | Wyoming County Courthouse | FR | CHOUSE | FTX1441AHZV |  |  |  |  | fiber and router needed | WVNET | 2011-11-30 | Y | Y | 15724.74 | N |  | 2011-12-08 | Y | 1390 | 1390 | 2012-10-01 | Complete | 2012-04-09 | Y | TBD |  |  |  | TBD |  | TBD |  | TBD
BB55A02 | WYOMING | BAILEYSVILLE ELEMENTARY SCHOOL | RO | K12 | FTX1438A2DV | 56 |  | 2011-11-29 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-11-29 | Ready | 2012-01-05
BB55A03 | WYOMING | BERLIN MCKINNEY ELEMENTARY | RO | K12 | FTX1439AH07 | 57 |  | 2011-12-19 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-12-19 | Ready | 2012-01-05
BB55A04 | WYOMING | GLEN FORK GRADE SCHOOL | RO | K12 | FTX1439AH1D | 58 |  | 2011-11-30 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-11-30 | Ready | 2012-01-05
BB55A05 | WYOMING | HERNDON CONSOLIDATED SCHOOL | RO | K12 | FTX1439AH1H | 59 |  | 2011-11-28 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-11-28 | Ready | 2012-01-05
BB55A06 | WYOMING | HUFF CONSOLIDATED ELEMENTARY SCHOOL | RO | K12 | FTX1439AH05 | 60 |  | 2011-11-29 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-11-29 | Ready | 2012-01-05
BB55A07 | WYOMING | MULLENS ELEMENTARY SCHOOL | RO | K12 | FTX1439AH1K | 61 |  | 2011-11-28 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-11-28 | Ready | 2012-01-05
BB55A08 | WYOMING | MULLENS MIDDLE SCHOOL | RO | K12 | FTX1438A2CR | 62 |  | 2011-11-28 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-11-28 | Ready | 2012-01-05
BB55A09 | WYOMING | OCEANA MIDDLE SCHOOL | RO | K12 | FTX1438A2CU | 63 |  | 2011-12-19 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-12-19 | Ready | 2012-01-05
BB55A10 | WYOMING | PINEVILLE MIDDLE SCHOOL | RO | K12 | FTX1439AH0M | 64 |  | 2011-11-29 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-11-29 | Ready | 2012-01-05
BB55A11 | WYOMING | PINEVILLE Elementary PRIMARY SCHOOL | RO | K12 | FTX1439AH01 | 65 |  | 2011-12-09 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-12-09 | Ready | 2012-01-05
BB55A12 | WYOMING | ROAD BRANCH GRADE SCHOOL | RO | K12 | FTX1438A2DT | 66 |  | 2011-11-30 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-11-30 | Ready | 2012-01-05
BB55A13 | WYOMING | WESTSIDE HIGH SCHOOL | RO | K12 | FTX1438A2BY | 67 |  | 2011-11-30 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-11-30 | Ready | 2012-01-05
BB55A14 | WYOMING | WYOMING COUNTY EAST HIGH SCHOOL | RO | K12 | FTX1439AH1G | 68 |  | 2011-11-28 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-11-28 | Ready | 2012-01-05
BB55A15 | WYOMING | WYOMING VOC-TECH CENTER | RO | K12 | FTX1439AH0L | 69 |  | 2011-11-18 |  | per FTR; site already has fiber- router only | K-12 |  | N | N/A |  |  |  |  | N/A | 0 | 0 | N/A | Complete | N/A | N/A | No Build Required | N/A | N/A | N/A | Complete | N/A | Complete | 2011-11-18 | Ready | 2012-01-05
BB55A16 | WYOMING | Hanover Public Library | FR | LIB | FTX1439A192 | 710 |  | 2011-12-13 |  | fiber and router needed | WVNET | 2011-10-03 | Y | Y | $ 8,922.77 ($3,997.26) | Y | 2012-04-27 | 2012-03-07 | Y | 1560 | 1560 | 2012-10-01 | Complete | 2012-05-17 | Y | Scheduled | 2012-06-14 |  | 2012-09-19 | Complete | 2012-09-19 | Complete | 2011-12-13 | Ready | 2012-09-21
BB55A17 | WYOMING | Mullens Area Public Library | FR | LIB | FTX1439A159 | 686 |  | 2011-10-28 |  | fiber and router needed | WVNET | 2011-11-21 | Y | Y | 12530.6 | N |  | 2012-03-09 | Y | 475 | 475 | 2012-10-01 | Complete | 2012-04-26 | Y | Scheduled | 2012-07-09 |  |  | TBD |  | Complete | 2011-10-28 | TBD
BB55A18 | WYOMING | Oceana Public Library | FR | LIB | FTX1439AJYE | 708 |  | 2011-12-15 |  | fiber and router needed | WVNET | 2011-12-01 | Y | Y | 16048.64 | N |  | 2011-12-08 | Y | 2092 | 2092 | 2012-10-01 | Complete | 2012-02-03 | Y | Complete | 2012-05-02 | 2012-07-03 |  | TBD |  | Complete | 2011-12-15 | TBD |  | *FBO On Hold - Until LCR is Approved - 2/10/12* *FBO Update - No Longer On Hold. 3/14/12*
BB55A19 | WYOMING | Wyoming County Public Library | FR | LIB | FTX1439A15L | 709 |  | 2011-12-15 |  | fiber and router needed | WVNET | 2011-12-07 | Y | Y | 5594.12 | N |  | 2011-12-13 | Y | 662 | 662 | 2012-10-01 | Complete | 2012-04-12 | Y | Complete | 2012-05-23 | 2012-07-03 |  | TBD |  | Complete | 2011-12-15 | TBD
BB55A20 | WYOMING | WERC 9-1-1 | FR | PSAP | FTX1436AJUN | 1351 |  | 2012-01-28 |  | fiber and router needed |  | 2011-12-01 | Y | Y | 7424.31 | N |  | 2011-12-13 | Y | 590 | 590 | 2012-10-01 | Complete | 2012-04-09 | Y | TBD |  |  |  | TBD |  | Complete | 2012-01-28 | TBD
BB55A21 | WYOMING | Jesse Wyoming - Troop 6 State Police | FR | SP | FTX1439A26T | 1099 |  | 2012-01-18 |  | fiber and router needed | State Police | 2011-12-01 | Y | Y | 7379.28 | N |  | 2011-12-08 | Y | 888 | 888 | 2012-10-01 | Complete | 2012-02-24 | Y | Complete | 2012-05-02 | 2012-07-03 |  | TBD |  | Complete | 2012-01-18 | TBD |  | *FBO On Hold - On hold until LCR is Approved - 03.1.12* *FBO Update - No Longer On Hold. 3/14/12*
BB55A22 | WYOMING | Oceana Medical Center Hygeia Facilities Foundation, Inc. | FR | TMED | FTX1436A2B8 | 859 | 1ZX560410300456712 | 2011-07-25 |  | fiber and router needed | ? | 2011-12-01 | Y | Y | 15539.47 | N |  | 2012-03-23 | Y | 1532 | 1532 | 2012-10-01 | Complete | 2012-04-26 | Y | Complete | 2012-06-14 | 2012-07-03 |  | TBD |  | Complete | 2011-07-25 | TBD
Formulas:
SCHEDULE FOR FIBER COMPLETION = IF([D]="",IF([ENGINEERING REQUIRED]="N","Complete",IF([Schedule for Fiber Completion]="N/A","Complete",IF([Schedule for Fiber Completion]="","TBD",IF(ISNUMBER([Fiber Footage Completed]),"Complete",[Schedule for Fiber Completion])))),"Removed")