## Sheet1
Agency | Date Sent to GEO | Funds Form Flow Request # | General Description of Expense | Budget Category | Admin & Legal (1.) | Land & Structures (2.) | Architectural and Engineering (4.) | Other Archictural and Engr (5.) | Site Work (7.) | Construction (9.) |  |  |  | Equipment (10.) | Miscellaneous (11.) (Office Supplies, Computers, Travel, Per diem etc) | Invoice Total | Total Drawdown to Date | % Spent
Total Grant Federal Funding | 159823296 |  |  | 1.Admn&Legal 2.Land,Struc 3.Relocation 4.Arch&Eng 5.OthrArch&Eng 6.InspectionFee 7.Site Work 8.Demolition 9.Const 10. Equip 11. Misc | 3830000 | 538200 | 13270236 | 5407800 | 700000 | 78722630 |  |  |  | 56736719 | 617711
Including Match Funding | [9 empty] | Cables |  | Towers | Other
[10 empty] | Fiber Build - Special Const | Fiber Build - Green Bank /NRAO | New Microwave Towers | Microwave const; switching, etc
DHHR/OEMS | 2011-02-22 | OEMS0006 | AUE Engineers 12/1-31/10; Jan 1/15/11 | 4 |  |  | 184480.16 | [8 empty] | 184480.16 | 184480.16 | 0.146%
DHHR/OEMS | 2011-03-11 | OEMS0007 | Engineering Services/installation services; Tower Steel-Cleveland Mtn, Cottle Knob | 4,9 |  |  | 260477.87 |  |  |  |  | 260000 |  |  |  | 520477.87 | 704958.03 | 0.5581%
DHHR/OEMS | 2011-03-11 | OEMS0008 | Generators-Sharps Knob;Williamson;Kenna; Glenville;FiveForks | 10 | [9 empty] | 92995.4 |  | 92995.4 | 797953.43 | 0.6317%
DHHR/OEMS | 2011-03-11 | OEMS0009 | Generators-Long Ridge;Cottle Knob;Cleveland;Weirton; Snowshoe | 10 | [9 empty] | 92995.4 |  | 92995.4 | 890948.83 | 0.7053%
DHHR/OEMS | 2011-03-11 | OEMS0010 | Generators-Greenbrier;Spencer sites | 10 | [9 empty] | 37198.16 |  | 37198.16 | 928146.99 | 0.7347%
DHHR/OEMS | 2011-05-19 | OEMS0011 | Engineering Services/installation services; Tower Steel-Five Forks, Weirton | 4,9 |  |  | 317601.72 |  |  |  |  | 213000 |  |  |  | 530601.72 | 1458748.71 | 1.155%
DHHR/OEMS | 2011-05-31 | OEMS0012 | Engineering Services/installation services; Tower Steel-Greenbrier MTN, Glenville, Williamson, Long Ridge | 9 | [7 empty] | 448000 |  |  |  | 448000 | 1906748.71 | 1.509%
DHHR/OEMS | 2011-05-31 | OEMS0013 | Communications BLDG - Kenna, Long Ridge, Cleveland MTN, Weirton, Snoeshow MTN, Greenbrier MTN | 2 |  | 173520 | [9 empty] | 173520 | 2080268.71 | 1.647%
DHHR/OEMS | 2011-05-31 | OEMS0014 | Communications BLDG - Spencer, Five Forks, Glenville | 2 |  | 86760 | [9 empty] | 86760 | 2167028.71 | 1.715%
DHHR/OEMS | 2011-08-18 | OEMS0015 | Engineering Services | 4 |  |  | 136565.87 | [8 empty] | 136565.87 | 2303594.58 | 1.824%
DHHR/OEMS | 2011-08-18 | OEMS0016 | Towers and Freight | 9 | [7 empty] | 152798.7 |  |  |  | 152798.7 | 2456393.28 | 1.945%
DHHR/OEMS | 2011-08-18 | OEMS0017 | Engineering Services | 4 |  |  | 131554.04 | [8 empty] | 131554.04 | 2587947.32 | 2.049%
DHHR/OEMS | 2011-09-14 | OEMS0020 | Tower Steel | 9 | [7 empty] | 334000 |  |  |  | 334000 | 2921947.32 | 2.313%
DHHR/OEMS | 2011-09-14 | OEMS0019 | Project MGMT | 2,4 |  | 28920 | 518655.5 | [8 empty] | 547575.5 | 3469522.82 | 2.747%
DHHR/OEMS | 2011-09-14 | OEMS0018 | Engineering Services | 2,4,10 |  | 46770.64 | 104857.98 | [6 empty] | 8463.4 |  | 160092.02 | 3629614.84 | 2.873%
DHHR/OEMS | 2011-10-03 | OEMS0021 | Tower buildout | 2,9 |  | 9045 | [5 empty] | 306000 |  |  |  | 315045 | 3944659.84 | 3.123%
DHHR/OEMS | 2011-11-18 | OEMS0022 | Engineering, Construction, MISC. | 2,9,10 |  | 8670.64 | [5 empty] | 5385 |  | 1798483.66 |  | 1812539.3 | 5757199.14 | 4.558%
DHHR/OEMS | 2011-11-18 | OEMS0023 | Engineering, Construction, MISC. | 4,9,10 |  |  | 224009.61 |  |  |  |  | 2190 |  | 8463.4 |  | 234663.01 | 5991862.15 | 4.743%
DHHR/OEMS | 2011-11-18 | OEMS0024 | Engineering, Equipment | 4,10 |  |  | 363529.31 | [6 empty] | 16926.8 |  | 380456.11 | 6372318.26 | 5.044%
DHHR/OEMS | 2011-12-19 | OEMS0025 | Project MGMT, MISC | 4,10 |  |  | 301050.7 | [6 empty] | 2383042.87 |  | 2684093.57 | 9056411.83 | 7.169%
DHHR/OEMS | 2011-12-19 | OEMS0026 | Testing and Project MGMT | 4,10 |  |  | 227642.15 | [6 empty] | 269550.44 |  | 497192.59 | 9553604.42 | 7.563%
DHHR/OEMS | 2011-12-19 | OEMS0027 | Testing and Project MGMT | 10 | [9 empty] | 1618533.59 |  | 1618533.59 | 11172138.01 | 8.844%
DHHR/OEMS | 2012-02-02 | OEMS0029 | Project MGMT | 4 |  |  | 207687.01 | [8 empty] | 207687.01 | 11379825.02 | 9.008%
DHHR/OEMS | 2012-02-02 | OEMS0031 | Project MGMT and Support | 2,4,10 |  | 4093.48 | 39834.13 | [7 empty] | 8463.4 | 52391.01 | 11432216.03 | 9.05%
DHHR/OEMS | 2012-02-02 | OEMS0032 | Project MGMT and Support | 4,10 |  |  | 109592.01 | [6 empty] | 9600 | 4000 | 123192.01 | 11555408.04 | 9.147%
DHHR/OEMS | 2012-02-13 | OEMS0030 | Freight, Microwave Equipment, Engineering | 2,4,9,10 |  | 4273 | 146270 |  |  |  |  | 14456.95 |  | 316952.64 |  | 481952.59 | 12037360.63 | 9.529%
DHHR/OEMS | 2012-02-16 | OEMS0033 | Freight | 9 | [7 empty] | 17234.4 |  |  |  | 17234.4 | 12054595.03 | 9.543%
DHHR/OEMS | 2012-02-23 | OEMS0028 | Engineering | 2,4 |  | -8670.64 | 829287.84 | [6 empty] | 429235 |  | 1249852.2 | 13304447.23 | 10.53%
DHHR/OEMS | 2012-02-28 | OEMS0034 | Equipment and Engineering | 4,10,9 |  |  | 173946.13 |  |  |  |  | -103000 |  | 2987392.7 |  | 3058338.83 | 16362786.06 | 12.95%
DHHR/OEMS | 2012-02-28 | OEMS0035 | Equipment and Engineering | 10,4 |  |  | 428171.76 | [6 empty] | 390325.6 |  | 818497.36 | 17181283.42 | 13.6%
DHHR/OEMS | 2012-03-08 | OEMS0036 | Engineering and Misc | 4 |  |  | 115174.14 | [8 empty] | 115174.14 | 17296457.56 | 13.69%
DHHR/OEMS | 2012-03-08 | OEMS0037 | Equipment and Engineering | 4,10 |  |  | 286607.04 | [6 empty] | 456152.8 |  | 742759.84 | 18039217.4 | 14.28%
DHHR/OEMS | 2012-03-08 | OEMS0038 | Engineering | 10 | [9 empty] | 46610 |  | 46610 | 18085827.4 | 14.32%
DHHR/OEMS | 2012-03-16 | OEMS0040 | Equipment | 10 | [9 empty] | 3129203.5 |  | 3129203.5 | 21215030.9 | 16.79%
DHHR/OEMS | 2012-03-20 | OEMS0039 | Equipment and Construction | 9,10 | [7 empty] | 10240 |  | 429943.49 |  | 440183.49 | 21655214.39 | 17.14%
DHHR/OEMS | 2012-04-03 | OEMS0041 | Tower Accessories | 9 | [7 empty] | 18400 |  |  |  | 18400 | 21673614.39 | 17.16%
DHHR/OEMS | 2012-04-19 | OEMS0044 | Storage Tank | 10 | [9 empty] | 8463.4 |  | 8463.4 | 21682077.79 | 17.16%
DHHR/OEMS | 2012-05-10 | OEMS0043 | Engineering | 10 | [9 empty] | 22384.1 |  | 22384.1 | 21704461.89 | 17.18%
DHHR/OEMS | 2012-05-10 | OEMS0042 | Engineering | 4 |  |  | 423377.14 | [8 empty] | 423377.14 | 22127839.03 | 17.52%
DHHR/OEMS | 2012-06-05 | OEMS0045 | Engineering and Freight | 4,9 |  |  | 201210.64 |  |  |  |  | 95000 |  |  |  | 296210.64 | 22424049.67 | 17.75%
DHHR/OEMS | 2012-06-19 | OEMS0046 | Microwave Equipment | 10 | [9 empty] | 308404.25 |  | 308404.25 | 22732453.92 | 18%
DHHR/OEMS | 2012-06-19 | OEMS0047 | Engineering | 4 |  |  | 419358.21 | [8 empty] | 419358.21 | 23151812.13 | 18.33%
DHHR/OEMS | 2012-06-19 | OEMS0048 | Engineering | 4,5 |  |  | 31243.86 | 73499.8 | [7 empty] | 104743.66 | 23256555.79 | 18.41%
DHHR/OEMS | 2012-06-19 | OEMS0049 | Engineering | 4,5 |  |  | 22919.98 | 64042.22 | [7 empty] | 86962.2 | 23343517.99 | 18.48%
DHHR/OEMS | 2012-06-19 | OEMS0050 | Engineering | 4,5 |  |  | 19353.9 | 46453.66 | [7 empty] | 65807.56 | 23409325.55 | 18.53%
DHHR/OEMS | 2012-06-19 | OEMS0051 | Engineering | 4,5 |  |  | 49495.51 | 15717.02 | [7 empty] | 65212.53 | 23474538.08 | 18.58%
DHHR/OEMS | 2012-06-19 | OEMS0052 | Engineering | 4 |  |  | 24876.52 | [8 empty] | 24876.52 | 23499414.6 | 18.6%
DHHR/OEMS | 2012-07-11 | OEMS0054 | Engineering | 4 |  |  | 98962 | [8 empty] | 98962 | 23598376.6 | 18.68%
DHHR/OEMS | 2012-07-11 | OEMS0055 | Tower Accessories | 10 | [9 empty] | 100850 |  | 100850 | 23699226.6 | 18.76%
DHHR/OEMS | 2012-07-11 | OEMS0056 | Engineering and Testing | 4 |  |  | 314366.91 | [8 empty] | 314366.91 | 24013593.51 | 19.01%
DHHR/OEMS | 2012-07-20 | OEMS0057 | Engineering and Environmental | 4,5 |  |  | 21432.89 | 133081.3 | [7 empty] | 154514.19 | 24168107.7 | 19.13%
DHHR/OEMS | 2012-07-24 | OEMS0058 | Engineering and Environmental | 4,5 |  |  | 16935.81 | 15950 | [7 empty] | 32885.81 | 24200993.51 | 19.16%
DHHR/OEMS | 2012-08-08 | OEMS0059 | Microwave Equipment | 10 | [9 empty] | 457079.4 |  | 457079.4 | 24658072.91 | 19.52%
DHHR/OEMS | 2012-08-08 | OEMS0060 | Microwave Equipment | 10 | [9 empty] | 642545.41 |  | 642545.41 | 25300618.32 | 20.03%
DHHR/OEMS | 2012-08-08 | OEMS0061 | Engineering | 4 |  |  | 89727.2 | [8 empty] | 89727.2 | 25390345.52 | 20.1%
DHHR/OEMS | 2012-08-27 | OEMS0062 | Engineering | 4 |  |  | 129732 | [8 empty] | 129732 | 25520077.52 | 20.2%
DHHR/OEMS | 2012-08-27 | OEMS0064 | Microwave Equipment | 10 | [9 empty] | 1746509.7 |  | 1746509.7 | 27266587.22 | 21.58%
DHHR/OEMS | 2012-08-28 | OEMS0063 | Microwave Equipment | 10 | [9 empty] | 2389728 |  | 2389728 | 29656315.22 | 23.48%
DHHR/OEMS | 2012-08-28 | OEMS0065 | Microwave Equipment | 10 | [9 empty] | 122598.93 |  | 122598.93 | 29778914.15 | 23.57%
DHHR/OEMS | 2012-09-14 | OEMS0069 | Freight | 9 | [7 empty] | 17400 |  |  |  | 17400 | 29796314.15 | 23.59%
DHHR/OEMS | 2012-09-14 | OEMS0068 | Fuel Tanks | 10 | [9 empty] | 16926.8 |  | 16926.8 | 29813240.95 | 23.6%
DHHR/OEMS | 2012-09-14 | OEMS0067 | Engineering | 4 |  |  | 54355.84 | [8 empty] | 54355.84 | 29867596.79 | 23.64%
DHHR/OEMS | 2012-09-14 | OEMS0066 | Engineering | 4 |  |  | 351156.79 | [8 empty] | 351156.79 | 30218753.58 | 23.92%
DHHR/OEMS | 2012-10-05 | OEMS0071 | Engineering | 4 |  |  | 60662.72 | [8 empty] | 60662.72 | 30279416.3 | 23.97%
DHHR/OEMS | 2012-10-05 | OEMS0070 | Fibrebond BLDG | 2 |  | 74201.6 | [9 empty] | 74201.6 | 30353617.9 | 24.03%
DHHR/OEMS | 2012-10-19 | OEMS0073 | Engineering | 4 |  |  | 23382.79 | [8 empty] | 23382.79 | 30377000.69 | 24.05%
DHHR/OEMS | 2012-10-19 | OEMS0074 | Freight and Engineering | 4,9 |  |  | 84900 |  |  |  |  | 15153.27 |  |  |  | 100053.27 | 30477053.96 | 24.13%
DHHR/OEMS | 2012-11-08 | OEMS0083 | Engineering and Microwave Equipment | 4,10 |  |  | 140944.5 | [6 empty] | 283383.18 |  | 424327.68 | 30901381.64 | 24.46%
DHHR/OEMS | 2012-11-08 | OEMS0082 | Tower Accessories | 9 | [7 empty] | 94400 |  |  |  | 94400 | 30995781.64 | 24.54%
DHHR/OEMS | 2012-11-08 | OEMS0075 | Engineering | 4 |  |  | 18066.34 | [8 empty] | 18066.34 | 31013847.98 | 24.55%
DHHR/OEMS | 2012-11-20 | OEMS0072 | Freight | 2 |  | 14505 | [9 empty] | 14505 | 31028352.98 | 24.56%
DHHR/OEMS | 2012-11-20 | OEMS0084 | Engineering | 4 |  |  | 40415.4 | [8 empty] | 40415.4 | 31068768.38 | 24.59%
DHHR/OEMS | 2012-12-13 | OEMS0086 | Engineering | 4 |  |  | 116513.02 | [8 empty] | 116513.02 | 31185281.4 | 24.69%
DHHR/OEMS | 2012-12-18 | OEMS0088 | Engineering | 4 |  |  | 203594.23 | [8 empty] | 203594.23 | 31388875.63 | 24.85%
DHHR/OEMS | 2012-12-18 | OEMS0089 | Microwave Equipment | 10 | [9 empty] | 752196.9 |  | 752196.9 | 32141072.53 | 25.44%
DHHR/OEMS | 2012-12-21 | OEMS0090 | Microwave Equipment | 10 | [9 empty] | 13741.04 |  | 13741.04 | 32154813.57 | 25.45%
DHHR/OEMS | 2012-12-21 | OEMS0092 | Tower Steel | 9 | [7 empty] | 84100 |  |  |  | 84100 | 32238913.57 | 25.52%
DHHR/OEMS | 2012-12-21 | OEMS0093 | Tower Steel | 9 | [7 empty] | 84100 |  |  |  | 84100 | 32323013.57 | 25.59%
DHHR/OEMS | 2012-12-21 | OEMS0094 | Tower Steel | 9 | [7 empty] | 84100 |  |  |  | 84100 | 32407113.57 | 25.65%
DHHR/OEMS | 2013-01-11 | OEMS0096 | Engineering | 4 |  |  | 144096.79 | [8 empty] | 144096.79 | 32551210.36 | 25.77%
DHHR/OEMS | 2013-01-11 | OEMS0097 | Engineering | 4 |  |  | 25613.75 | [8 empty] | 25613.75 | 32576824.11 | 25.79%
DHHR/OEMS | 2013-01-11 | OEMS0098 | Tower Steel | 9 | [7 empty] | 221300 |  |  |  | 221300 | 32798124.11 | 25.96%
DHHR/OEMS | 2013-02-08 | OEMS0095 | Storage Tank | 10 | [9 empty] | 8463.4 |  | 8463.4 | 32806587.51 | 25.97%
DHHR/OEMS | 2013-02-08 | OEMS0099 | Engineering | 4 |  |  | 175193.5 | [8 empty] | 175193.5 | 32981781.01 | 26.11%
DHHR/OEMS | 2013-02-08 | OEMS0100 | Storage Tank | 10 | [9 empty] | 8463.4 |  | 8463.4 | 32990244.41 | 26.12%
DHHR/OEMS | 2013-02-08 | OEMS0101 | Engineering | 4 |  |  | 11877 | [8 empty] | 11877 | 33002121.41 | 26.13%
DHHR/OEMS | 2013-02-11 | OEMS0102 | DHHR Fuel | 11 | [10 empty] | 3222.64 | 3222.64 | 33005344.05 | 26.13%
DHHR/OEMS | 2013-02-11 | OEMS0103 | Engineering | 4 |  |  | 71490 | [8 empty] | 71490 | 33076834.05 | 26.18%
DHHR/OEMS | 2013-02-11 | OEMS0104 | Engineering | 4 |  |  | 272888.52 | [8 empty] | 272888.52 | 33349722.57 | 26.4%
DHHR/OEMS | 2013-02-21 | OEMS0091 | Vehicle Rental and Travel | 11 | [10 empty] | 8136.76 | 8136.76 | 33357859.33 | 26.41%
DHHR/OEMS | 2013-03-12 | OEMS0105 | Storage Tank | 10 | [9 empty] | 8463.4 |  | 8463.4 | 33366322.73 | 26.41%
DHHR/OEMS | 2013-03-12 | OEMS0106 | Engineering | 4 |  |  | 184520.9 | [8 empty] | 184520.9 | 33550843.63 | 26.56%
DHHR/OEMS | 2013-03-12 | OEMS0107 | Engineering | 4 |  |  | 74714.1 | [8 empty] | 74714.1 | 33625557.73 | 26.62%
DHHR/OEMS | 2013-03-12 | OEMS0108 | Engineering | 4 |  |  | 5765.51 | [8 empty] | 5765.51 | 33631323.24 | 26.62%
DHHR/OEMS | 2013-03-12 | OEMS0109 | Engineering | 4,5 |  | 11170 |  | 17599.12 | [7 empty] | 28769.12 | 33660092.36 | 26.65%
DHHR/OEMS | 2013-04-09 | OEMS0053 | Payroll | 1 | 8976.28 | [10 empty] | 8976.28 | 33669068.64 | 26.65%
DHHR/OEMS | 2013-04-09 | OEMS0076 | Payroll | 1 | 18815.86 | [10 empty] | 18815.86 | 33687884.5 | 26.67%
DHHR/OEMS | 2013-04-09 | OEMS0077 | Payroll | 1 | 25266.17 | [10 empty] | 25266.17 | 33713150.67 | 26.69%
DHHR/OEMS | 2013-04-09 | OEMS0079 | Payroll | 1 | 33057.57 | [10 empty] | 33057.57 | 33746208.24 | 26.71%
DHHR/OEMS | 2013-04-09 | OEMS0080 | Payroll | 1 | 32268.68 | [10 empty] | 32268.68 | 33778476.92 | 26.74%
DHHR/OEMS | 2013-04-09 | OEMS0081 | Payroll | 1 | 27261.09 | [10 empty] | 27261.09 | 33805738.01 | 26.76%
DHHR/OEMS | 2013-04-09 | OEMS0085 | Payroll | 1 | 27505.84 | [10 empty] | 27505.84 | 33833243.85 | 26.78%
DHHR/OEMS | 2013-04-09 | OEMS0110 | Payroll | 1 | 27533.24 | [10 empty] | 27533.24 | 33860777.09 | 26.8%
DHHR/OEMS | 2013-04-09 | OEMS0111 | Payroll | 1 | 27666.29 | [10 empty] | 27666.29 | 33888443.38 | 26.83%
DHHR/OEMS | 2013-04-11 | OEMS0078 | Payroll | 1 | 24739.49 | [10 empty] | 24739.49 | 33913182.87 | 26.85%
DHHR/OEMS | 2013-04-11 | OEMS0112 | Payroll | 1 | 25944.41 | [10 empty] | 25944.41 | 33939127.28 | 26.87%
DHHR/OEMS | 2013-07-05 | OEMS0113 | Payroll | 1 | 25207.8 | [10 empty] | 25207.8 | 33964335.08 | 26.89%
DHHR/OEMS | 2013-07-05 | OEMS0115 | Payroll | 1 | 25269.62 | [10 empty] | 25269.62 | 33989604.7 | 26.91%
DHHR/OEMS | 2013-07-05 | OEMS0116 | Payroll | 1 | 24124.33 | [10 empty] | 24124.33 | 34013729.03 | 26.93%
DHHR/OEMS | 2013-07-05 | OEMS0117 | Payroll | 1 | 24676.95 | [10 empty] | 24676.95 | 34038405.98 | 26.95%
DHHR/OEMS | 2013-08-07 | OEMS0118 | Payroll | 1 | 14318.43 | [10 empty] | 14318.43 | 34052724.41 | 26.96%
DHHR/OEMS | 2013-08-27 | OEMS0114 | Engineering and Misc | 4,11 |  |  | 292219.11 | [7 empty] | 12456.26 | 304675.37 | 34357399.78 | 27.2%
DHHR/OEMS | 2013-10-28 | OEMS0119 | Freight Charges | 2,4,9 |  | 101144.32 |  | 38450.68 |  |  |  | 17400 |  |  |  | 156995 | 34514394.78 | 27.32%
DHHR/STEMS | 2010-08-13 | STEMS-0001 | AUE Eng Services July 9, 2010 | 4 |  |  | 99058.1 | [8 empty] | 99058.1 | 34613452.88 | 27.4%
DHHR/STEMS | 2010-09-29 | STEMS-0002 | AUE Eng - Eng Services July 2010; Aug 2010 | 4 |  |  | 107432.5 | [8 empty] | 107432.5 | 34720885.38 | 27.49%
DHHR/STEMS | 2010-11-03 | STEMS-0003 | AUE Eng-Eng Services Sept 1-30,11 | 4 |  |  | 92780.6 | [8 empty] | 92780.6 | 34813665.98 | 27.56%
DHHR/STEMS | 2010-11-16 | STEMS-0004 | AUE Eng - Eng Services Oct 1-15/10; Aviat Eng Site Survey/Eng Oct 18,2011 | 4 |  |  | 374102 | [8 empty] | 374102 | 35187767.98 | 27.86%
DHHR/STEMS | 2010-12-21 | STEMS-0005 | AUE Eng - Oct 16-31/10; Nov 1-30/11 | 4 |  |  | 212727.87 | [8 empty] | 212727.87 | 35400495.85 | 28.02%
[17 empty] | 35400495.85 | 28.02%
[17 empty] | 35400495.85 | 28.02%
LCC | 2011-06-15 | LCC001 | Site Work and Tower Construction | 9,7 |  |  |  |  | 221317 |  |  | 265632.5 |  |  |  | 486949.5 | 35887445.35 | 28.41%
LCC | 2011-07-14 | LCC002 | Site Work and Tower Construction | 7,9 |  |  |  |  | 103935 |  |  | 55332.5 |  |  |  | 159267.5 | 36046712.85 | 28.54%
LCC | 2011-07-21 | LCC003 | Site Work | 7 |  |  |  |  | 52115 | [6 empty] | 52115 | 36098827.85 | 28.58%
LCC | 2011-07-25 | LCC004 | Site Work | 7 |  |  |  |  | 187896.6 | [6 empty] | 187896.6 | 36286724.45 | 28.73%
LCC | 2011-08-09 | LCC005 | Site Work and Tower buildout | 7,9 |  |  |  |  | 124920 |  |  | 3600 |  |  |  | 128520 | 36415244.45 | 28.83%
LCC | 2011-08-29 | LCC006 | Site Work | 7 |  |  |  |  | 330494.3 | [6 empty] | 330494.3 | 36745738.75 | 29.09%
LCC | 2011-09-13 | LCC007 | Site Work and Tower Construction | 7,9 |  |  |  |  | 129935.9 |  |  | 149560 |  |  |  | 279495.9 | 37025234.65 | 29.31%
LCC | 2011-11-17 | LCC008 | Tower Construction | 9 | [7 empty] | 279391.2 |  |  |  | 279391.2 | 37304625.85 | 29.53%
LCC | 2011-11-18 | LCC009 | Site Work and Tower Construction | 9,7 |  |  |  |  | 24573.1 |  |  | 89905 |  |  |  | 114478.1 | 37419103.95 | 29.62%
LCC | 2011-12-08 | LCC010 | Tower Construction | 9 | [7 empty] | 117277.5 |  |  |  | 117277.5 | 37536381.45 | 29.71%
LCC | 2011-12-08 | LCC011 | Tower Construction | 9 | [7 empty] | 144585 |  |  |  | 144585 | 37680966.45 | 29.83%
LCC | 2011-12-08 | LCC012 | Tower Construction | 9 | [7 empty] | 146183.5 |  |  |  | 146183.5 | 37827149.95 | 29.94%
LCC | 2011-12-15 | LCC013 | Tower Construction | 9 | [7 empty] | 27286.25 |  |  |  | 27286.25 | 37854436.2 | 29.97%
LCC | 2012-02-01 | LCC014 | Site Work and Tower Construction | 7,9 |  |  |  |  | 340 |  |  | 17800 |  |  |  | 18140 | 37872576.2 | 29.98%
LCC | 2012-02-01 | LCC015 | Site Work and Tower Construction | 7,9 |  |  |  |  | 5940 |  |  | 11905 |  |  |  | 17845 | 37890421.2 | 29.99%
LCC | 2012-02-01 | LCC016 | Tower Construction | 9 | [7 empty] | 24330 |  |  |  | 24330 | 37914751.2 | 30.01%
LCC | 2012-03-08 | LCC017-LCC020 | Tower Construction | 9 | [7 empty] | 58846.5 |  |  |  | 58846.5 | 37973597.7 | 30.06%
LCC | 2012-03-08 | LCC021-LCC027 | Tower Construction | 9 | [7 empty] | 102758.75 |  |  |  | 102758.75 | 38076356.45 | 30.14%
LCC | 2012-03-08 | LCC028-LCC029 | Tower Construction | 9 | [7 empty] | 8386.25 |  |  |  | 8386.25 | 38084742.7 | 30.15%
LCC | 2012-03-08 | LCC030-LCC034 | Tower Construction | 9 | [7 empty] | 40810 |  |  |  | 40810 | 38125552.7 | 30.18%
LCC | 2012-03-16 | LCC035-LCC036 | Tower Construction | 9 | [7 empty] | 6262.5 |  |  |  | 6262.5 | 38131815.2 | 30.19%
LCC | 2012-03-16 | LCC037 | Tower Construction | 9 | [7 empty] | 114700 |  |  |  | 114700 | 38246515.2 | 30.28%
LCC | 2012-05-01 | LCC038 | Tower Construction | 9 | [7 empty] | 42900 |  |  |  | 42900 | 38289415.2 | 30.31%
LCC | 2012-05-29 | LCC039 | Site Work | 7 |  |  |  |  | 87182.5 | [6 empty] | 87182.5 | 38376597.7 | 30.38%
LCC | 2012-05-29 | LCC040 | Site Work | 7 |  |  |  |  | 95136.45 | [6 empty] | 95136.45 | 38471734.15 | 30.45%
LCC | 2012-05-29 | LCC041 | Tower Construction | 9 | [7 empty] | 18540 |  |  |  | 18540 | 38490274.15 | 30.47%
LCC | 2012-05-29 | LCC042 | Tower Construction | 9 | [7 empty] | 24740 |  |  |  | 24740 | 38515014.15 | 30.49%
LCC | 2012-05-29 | LCC043 | Site Work and Tower Construction | 7,9 |  |  |  |  | 112100 |  |  | 4464 |  |  |  | 116564 | 38631578.15 | 30.58%
LCC | 2012-05-29 | LCC044 | Tower Construction | 9 | [7 empty] | 8776 |  |  |  | 8776 | 38640354.15 | 30.59%
LCC | 2012-06-19 | LCC045 | Tower Construction | 9 | [7 empty] | 103200 |  |  |  | 103200 | 38743554.15 | 30.67%
LCC | 2012-07-19 | LCC046 | Site Work | 7 |  |  |  |  | 59500 | [6 empty] | 59500 | 38803054.15 | 30.72%
LCC | 2012-07-19 | LCC047 | Tower Construction | 9 | [7 empty] | 14840 |  |  |  | 14840 | 38817894.15 | 30.73%
LCC | 2012-07-19 | LCC048 | Tower Construction | 9 | [7 empty] | 93240 |  |  |  | 93240 | 38911134.15 | 30.8%
LCC | 2012-07-19 | LCC049 | Tower Construction | 9 | [7 empty] | 15332 |  |  |  | 15332 | 38926466.15 | 30.81%
LCC | 2012-07-19 | LCC050 | Site Work | 7 |  |  |  |  | 22990 | [6 empty] | 22990 | 38949456.15 | 30.83%
LCC | 2012-07-19 | LCC051 | Tower Construction | 9 | [7 empty] | 51380 |  |  |  | 51380 | 39000836.15 | 30.87%
LCC | 2012-07-19 | LCC052 | Tower Construction | 9 | [7 empty] | 20400 |  |  |  | 20400 | 39021236.15 | 30.89%
LCC | 2012-07-19 | LCC053 | Tower Construction | 9 | [7 empty] | 28600 |  |  |  | 28600 | 39049836.15 | 30.91%
LCC | 2012-07-19 | LCC054 | Tower Construction | 9 | [7 empty] | 26310 |  |  |  | 26310 | 39076146.15 | 30.93%
LCC | 2012-08-08 | LCC055 | Site Work and Tower Construction | 7,9 |  |  |  |  | 39900 |  |  | 57405 |  |  |  | 97305 | 39173451.15 | 31.01%
LCC | 2012-08-21 | LCC0056 | Tower Construction | 9 | [7 empty] | 77040 |  |  |  | 77040 | 39250491.15 | 31.07%
LCC | 2012-09-14 | LCC0057 | Tower Construction | 9 | [7 empty] | 2400 |  |  |  | 2400 | 39252891.15 | 31.07%
LCC | 2012-09-14 | LCC0058 | Tower Construction | 9 | [7 empty] | 10225 |  |  |  | 10225 | 39263116.15 | 31.08%
LCC | 2012-09-14 | LCC0060 | Site Work | 7 |  |  |  |  | 27140 | [6 empty] | 27140 | 39290256.15 | 31.1%
LCC | 2012-09-14 | LCC0061 | Tower Construction | 9 | [7 empty] | 7975 |  |  |  | 7975 | 39298231.15 | 31.11%
LCC | 2012-09-14 | LCC0062 | Tower Construction | 9 | [7 empty] | 5312.5 |  |  |  | 5312.5 | 39303543.65 | 31.11%
LCC | 2012-09-14 | LCC0063 | Tower Construction | 9 | [7 empty] | 7079 |  |  |  | 7079 | 39310622.65 | 31.12%
LCC | 2012-09-14 | LCC0064 | Tower Construction | 9 | [7 empty] | 842.5 |  |  |  | 842.5 | 39311465.15 | 31.12%
LCC | 2012-09-14 | LCC0065 | Tower Construction | 9 | [7 empty] | 5705 |  |  |  | 5705 | 39317170.15 | 31.12%
LCC | 2012-09-14 | LCC0066 | Tower Construction | 9 | [7 empty] | 9365 |  |  |  | 9365 | 39326535.15 | 31.13%
LCC | 2012-09-14 | LCC0067 | Tower Construction | 9 | [7 empty] | 2700 |  |  |  | 2700 | 39329235.15 | 31.13%
LCC | 2012-09-14 | LCC0068 | Tower Construction | 9 | [7 empty] | 8037.75 |  |  |  | 8037.75 | 39337272.9 | 31.14%
LCC | 2012-09-14 | LCC0069 | Tower Construction | 9 | [7 empty] | 7400 |  |  |  | 7400 | 39344672.9 | 31.15%
LCC | 2012-09-14 | LCC0070 | Tower Construction | 9 | [7 empty] | 18146 |  |  |  | 18146 | 39362818.9 | 31.16%
LCC | 2012-09-14 | LCC0071 | Tower Construction | 9 | [7 empty] | 13233.5 |  |  |  | 13233.5 | 39376052.4 | 31.17%
LCC | 2012-09-14 | LCC0072 | Tower Construction | 9 | [7 empty] | 22554.5 |  |  |  | 22554.5 | 39398606.9 | 31.19%
LCC | 2012-09-14 | LCC0073 | Tower Construction | 9 | [7 empty] | 15720 |  |  |  | 15720 | 39414326.9 | 31.2%
LCC | 2012-09-14 | LCC0074 | Tower Construction | 9 | [7 empty] | 10358 |  |  |  | 10358 | 39424684.9 | 31.21%
LCC | 2012-09-14 | LCC0075 | Tower Construction | 9 | [7 empty] | 4121.25 |  |  |  | 4121.25 | 39428806.15 | 31.21%
LCC | 2012-09-14 | LCC0076 | Tower Construction | 9 | [7 empty] | 5873.75 |  |  |  | 5873.75 | 39434679.9 | 31.22%
LCC | 2012-09-14 | LCC0077 | Tower Construction | 9 | [7 empty] | 14425 |  |  |  | 14425 | 39449104.9 | 31.23%
LCC | 2012-09-14 | LCC0078 | Tower Construction | 9 | [7 empty] | 1300 |  |  |  | 1300 | 39450404.9 | 31.23%
LCC | 2012-09-14 | LCC0079 | Tower Construction | 9 | [7 empty] | 4823.75 |  |  |  | 4823.75 | 39455228.65 | 31.23%
LCC | 2012-09-14 | LCC0080 | Tower Construction | 9 | [7 empty] | 18195 |  |  |  | 18195 | 39473423.65 | 31.25%
LCC | 2012-09-14 | LCC0081 | Tower Construction | 9 | [7 empty] | 2720 |  |  |  | 2720 | 39476143.65 | 31.25%
LCC | 2012-09-14 | LCC0082 | Tower Construction | 9 | [7 empty] | 4268.75 |  |  |  | 4268.75 | 39480412.4 | 31.25%
LCC | 2012-09-14 | LCC0083 | Tower Construction | 9 | [7 empty] | 1895 |  |  |  | 1895 | 39482307.4 | 31.25%
LCC | 2012-09-14 | LCC0084 | Tower Construction | 9 | [7 empty] | 12117.5 |  |  |  | 12117.5 | 39494424.9 | 31.26%
LCC | 2012-09-14 | LCC0085 | Tower Construction | 9 | [7 empty] | 8410 |  |  |  | 8410 | 39502834.9 | 31.27%
LCC | 2012-09-14 | LCC0086 | Tower Construction | 9 | [7 empty] | 12814.75 |  |  |  | 12814.75 | 39515649.65 | 31.28%
LCC | 2012-09-14 | LCC0087 | Tower Construction | 9 | [7 empty] | 11540 |  |  |  | 11540 | 39527189.65 | 31.29%
LCC | 2012-09-14 | LCC0088 | Tower Construction | 9 | [7 empty] | 14460 |  |  |  | 14460 | 39541649.65 | 31.3%
LCC | 2012-09-14 | LCC0089 | Tower Construction | 9 | [7 empty] | 10623.75 |  |  |  | 10623.75 | 39552273.4 | 31.31%
LCC | 2012-09-14 | LCC0090 | Tower Construction | 9 | [7 empty] | 2445 |  |  |  | 2445 | 39554718.4 | 31.31%
LCC | 2012-09-14 | LCC0091 | Tower Construction | 9 | [7 empty] | 10365 |  |  |  | 10365 | 39565083.4 | 31.32%
LCC | 2012-09-14 | LCC0092 | Tower Construction | 9 | [7 empty] | 4770 |  |  |  | 4770 | 39569853.4 | 31.32%
LCC | 2012-09-14 | LCC0093 | Tower Construction | 9 | [7 empty] | 13110 |  |  |  | 13110 | 39582963.4 | 31.33%
LCC | 2012-09-14 | LCC0094 | Tower Construction | 9 | [7 empty] | 6345 |  |  |  | 6345 | 39589308.4 | 31.34%
LCC | 2012-10-05 | LCC0095 | Tower Construction | 9 | [7 empty] | 11430 |  |  |  | 11430 | 39600738.4 | 31.35%
LCC | 2012-10-05 | LCC0096 | Tower Construction | 9 | [7 empty] | 7320 |  |  |  | 7320 | 39608058.4 | 31.35%
LCC | 2012-10-14 | LCC0097 | Tower Construction | 9 | [7 empty] | 78325 |  |  |  | 78325 | 39686383.4 | 31.42%
LCC | 2012-10-14 | LCC0098 | Tower Construction | 9 | [7 empty] | 125300 |  |  |  | 125300 | 39811683.4 | 31.52%
LCC | 2012-10-15 | LCC0059 | Site Work | 7 |  |  |  |  | 28240 | [6 empty] | 28240 | 39839923.4 | 31.54%
LCC | 2012-12-04 | LCC0099 | Tower Construction | 9 | [7 empty] | 32545 |  |  |  | 32545 | 39872468.4 | 31.56%
LCC | 2012-12-04 | LCC0100 | Tower Construction | 9 | [7 empty] | 77275 |  |  |  | 77275 | 39949743.4 | 31.63%
LCC | 2012-12-04 | LCC0101 | Tower Construction | 9 | [7 empty] | 7890 |  |  |  | 7890 | 39957633.4 | 31.63%
LCC | 2012-12-04 | LCC0102 | Tower Construction | 9 | [7 empty] | 26515 |  |  |  | 26515 | 39984148.4 | 31.65%
LCC | 2012-12-04 | LCC0103 | Tower Construction | 9 | [7 empty] | 62625 |  |  |  | 62625 | 40046773.4 | 31.7%
LCC | 2012-12-04 | LCC0104 | Tower Construction | 9 | [7 empty] | 54335 |  |  |  | 54335 | 40101108.4 | 31.74%
LCC | 2012-12-04 | LCC0105 | Tower Construction | 9 | [7 empty] | 20932.5 |  |  |  | 20932.5 | 40122040.9 | 31.76%
LCC | 2012-12-04 | LCC0106 | Tower Construction | 9 | [7 empty] | 6655 |  |  |  | 6655 | 40128695.9 | 31.77%
LCC | 2012-12-04 | LCC0107 | Tower Construction | 9 | [7 empty] | 8292.5 |  |  |  | 8292.5 | 40136988.4 | 31.77%
LCC | 2012-12-04 | LCC0108 | Tower Construction | 9 | [7 empty] | 21302.5 |  |  |  | 21302.5 | 40158290.9 | 31.79%
LCC | 2013-01-07 | LCC0109 | Tower Construction | 9 | [7 empty] | 61335 |  |  |  | 61335 | 40219625.9 | 31.84%
LCC | 2013-01-07 | LCC0110 | Tower Construction | 9 | [7 empty] | 16919 |  |  |  | 16919 | 40236544.9 | 31.85%
LCC | 2013-01-07 | LCC0111 | Tower Construction | 9 | [7 empty] | 27382.5 |  |  |  | 27382.5 | 40263927.4 | 31.87%
LCC | 2013-01-07 | LCC0112 | Tower Construction | 9 | [7 empty] | 57932.5 |  |  |  | 57932.5 | 40321859.9 | 31.92%
LCC | 2013-01-07 | LCC0113 | Tower Construction | 9 | [7 empty] | 33780 |  |  |  | 33780 | 40355639.9 | 31.95%
LCC | 2013-01-07 | LCC0114 | Tower Construction | 9 | [7 empty] | 8526.5 |  |  |  | 8526.5 | 40364166.4 | 31.95%
LCC | 2013-02-05 | LCC0115 | Tower Construction | 9 | [7 empty] | 47981.5 |  |  |  | 47981.5 | 40412147.9 | 31.99%
LCC | 2013-02-05 | LCC0116 | Tower Construction | 9 | [7 empty] | 25527.5 |  |  |  | 25527.5 | 40437675.4 | 32.01%
LCC | 2013-02-05 | LCC0117 | Tower Construction | 9 | [7 empty] | 47768.75 |  |  |  | 47768.75 | 40485444.15 | 32.05%
LCC | 2013-02-05 | LCC0118 | Tower Construction | 9 | [7 empty] | 27750 |  |  |  | 27750 | 40513194.15 | 32.07%
LCC | 2013-04-09 | LCC0119 | Tower Construction | 9 | [7 empty] | 51494.75 |  |  |  | 51494.75 | 40564688.9 | 32.11%
LCC | 2013-04-09 | LCC0120 | Tower Construction | 9 | [7 empty] | 77950 |  |  |  | 77950 | 40642638.9 | 32.17%
LCC | 2013-04-09 | LCC0121 | Tower Construction | 9 | [7 empty] | 36795 |  |  |  | 36795 | 40679433.9 | 32.2%
LCC | 2013-04-11 | LCC0122 | Site Work | 7 |  |  |  |  | 61775 | [6 empty] | 61775 | 40741208.9 | 32.25%
LCC | 2013-04-30 | LCC0123 | Tower Construction | 9 | [7 empty] | 35510 |  |  |  | 35510 | 40776718.9 | 32.28%
LCC | 2013-04-30 | LCC0124 | Tower Construction | 9 | [7 empty] | 20540 |  |  |  | 20540 | 40797258.9 | 32.3%
LCC | 2013-04-30 | LCC0125 | Tower Construction | 9 | [7 empty] | 50857.5 |  |  |  | 50857.5 | 40848116.4 | 32.34%
LCC | 2013-04-30 | LCC0126 | Tower Construction | 9 | [7 empty] | 45165 |  |  |  | 45165 | 40893281.4 | 32.37%
LCC | 2013-04-30 | LCC0127 | Tower Construction | 9 | [7 empty] | 10180 |  |  |  | 10180 | 40903461.4 | 32.38%
LCC | 2013-05-17 | LCC0128 | Site Work and Tower Construction | 7,9 |  |  |  |  | 25200 |  |  | 47057.5 |  |  |  | 72257.5 | 40975718.9 | 32.44%
LCC | 2013-05-17 | LCC0129 | Tower Construction | 9 | [7 empty] | 9932.5 |  |  |  | 9932.5 | 40985651.4 | 32.45%
LCC | 2013-05-17 | LCC0130 | Tower Construction | 9 | [7 empty] | 44932.5 |  |  |  | 44932.5 | 41030583.9 | 32.48%
LCC | 2013-05-17 | LCC0131 | Tower Construction | 9 | [7 empty] | 41630 |  |  |  | 41630 | 41072213.9 | 32.51%
LCC | 2013-05-17 | LCC0132 | Tower Construction | 9 | [7 empty] | 42487.5 |  |  |  | 42487.5 | 41114701.4 | 32.55%
LCC | 2013-05-17 | LCC0133 | Tower Construction | 9 | [7 empty] | 14913.75 |  |  |  | 14913.75 | 41129615.15 | 32.56%
LCC | 2013-05-17 | LCC0134 | Tower Construction | 9 | [7 empty] | 109982.5 |  |  |  | 109982.5 | 41239597.65 | 32.65%
LCC | 2013-05-17 | LCC0135 | Site Work | 7 |  |  |  |  | 44000 | [6 empty] | 44000 | 41283597.65 | 32.68%
LCC | 2013-05-17 | LCC0136 | Site Work | 7 |  |  |  |  | 95300 | [6 empty] | 95300 | 41378897.65 | 32.76%
LCC | 2013-05-17 | LCC0137 | Site Work | 7 |  |  |  |  | 3300 | [6 empty] | 3300 | 41382197.65 | 32.76%
LCC | 2013-05-17 | LCC0138 | Tower Construction | 9 | [7 empty] | 8900 |  |  |  | 8900 | 41391097.65 | 32.77%
LCC | 2013-05-17 | LCC0139 | Tower Construction | 9 | [7 empty] | 6525 |  |  |  | 6525 | 41397622.65 | 32.77%
LCC | 2013-05-17 | LCC0140 | Tower Construction | 9 | [7 empty] | 2400 |  |  |  | 2400 | 41400022.65 | 32.77%
LCC | 2013-05-23 | LCC0141 | Tower Construction | 9 | [7 empty] | 32623 |  |  |  | 32623 | 41432645.65 | 32.8%
LCC | 2013-06-11 | LCC142 | Tower Construction | 9 | [7 empty] | 59540 |  |  |  | 59540 | 41492185.65 | 32.85%
LCC | 2013-06-11 | LCC143 | Tower Construction | 9 | [7 empty] | 9500 |  |  |  | 9500 | 41501685.65 | 32.85%
LCC | 2013-06-11 | LCC144 | Tower Construction | 9 | [7 empty] | 31518.5 |  |  |  | 31518.5 | 41533204.15 | 32.88%
LCC | 2013-06-11 | LCC145 | Tower Construction | 9 | [7 empty] | 36882.5 |  |  |  | 36882.5 | 41570086.65 | 32.91%
LCC | 2013-06-11 | LCC146 | Tower Construction | 9 | [7 empty] | 28220 |  |  |  | 28220 | 41598306.65 | 32.93%
LCC | 2013-06-11 | LCC147 | Tower Construction | 9 | [7 empty] | 47632.5 |  |  |  | 47632.5 | 41645939.15 | 32.97%
LCC | 2013-06-11 | LCC148 | Tower Construction | 9 | [7 empty] | 6937.5 |  |  |  | 6937.5 | 41652876.65 | 32.97%
LCC | 2013-06-11 | LCC149 | Tower Construction | 9 | [7 empty] | 18515 |  |  |  | 18515 | 41671391.65 | 32.99%
LCC | 2013-06-11 | LCC150 | Tower Construction | 9 | [7 empty] | 33775 |  |  |  | 33775 | 41705166.65 | 33.01%
LCC | 2013-06-11 | LCC151 | Tower Construction | 9 | [7 empty] | 59995 |  |  |  | 59995 | 41765161.65 | 33.06%
LCC | 2013-06-11 | LCC152 | Tower Construction | 9 | [7 empty] | 12813.75 |  |  |  | 12813.75 | 41777975.4 | 33.07%
LCC | 2013-06-11 | LCC153 | Tower Construction | 9 | [7 empty] | 1875 |  |  |  | 1875 | 41779850.4 | 33.07%
LCC | 2013-06-11 | LCC154 | Tower Construction | 9 | [7 empty] | 6261.25 |  |  |  | 6261.25 | 41786111.65 | 33.08%
LCC | 2013-06-11 | LCC155 | Tower Construction | 9 | [7 empty] | 29813.75 |  |  |  | 29813.75 | 41815925.4 | 33.1%
LCC | 2013-06-11 | LCC156 | Tower Construction | 9 | [7 empty] | 60195 |  |  |  | 60195 | 41876120.4 | 33.15%
LCC | 2013-06-11 | LCC157 | Tower Construction | 9 | [7 empty] | 30352.5 |  |  |  | 30352.5 | 41906472.9 | 33.17%
LCC | 2013-07-24 | LCC158 | Tower Construction | 9 | [7 empty] | 8.75 |  |  |  | 8.75 | 41906481.65 | 33.17%
LCC | 2013-07-24 | LCC159 | Tower Construction | 9 | [7 empty] | 42161.25 |  |  |  | 42161.25 | 41948642.9 | 33.21%
LCC | 2013-07-24 | LCC160 | Tower Construction | 9 | [7 empty] | 10790 |  |  |  | 10790 | 41959432.9 | 33.22%
LCC | 2013-07-24 | LCC161 | Tower Construction | 9 | [7 empty] | 13265 |  |  |  | 13265 | 41972697.9 | 33.23%
LCC | 2013-07-24 | LCC162 | Tower Construction | 9 | [7 empty] | 53092.5 |  |  |  | 53092.5 | 42025790.4 | 33.27%
LCC | 2013-07-24 | LCC163 | Tower Construction | 9 | [7 empty] | 42945 |  |  |  | 42945 | 42068735.4 | 33.3%
LCC | 2013-07-24 | LCC164 | Tower Construction | 9 | [7 empty] | 32950 |  |  |  | 32950 | 42101685.4 | 33.33%
LCC | 2013-07-24 | LCC165 | Tower Construction | 9 | [7 empty] | 16720 |  |  |  | 16720 | 42118405.4 | 33.34%
LCC | 2013-08-21 | LCC167 | Site Work and Tower Construction | 7,9 |  |  |  |  | 6503.95 |  |  | 2400 |  |  |  | 8903.95 | 42127309.35 | 33.35%
LCC | 2013-08-21 | LCC168 | Site Work | 7 |  |  |  |  | 14725 | [6 empty] | 14725 | 42142034.35 | 33.36%
LCC | 2013-08-21 | LCC169 | Site Work and Tower Construction | 7,9 |  |  |  |  | 17100 |  |  | 92760 |  |  |  | 109860 | 42251894.35 | 33.45%
LCC | 2013-08-21 | LCC170 | Tower Construction | 9 | [7 empty] | 70845 |  |  |  | 70845 | 42322739.35 | 33.5%
LCC | 2013-08-21 | LCC171 | Site Work and Tower Construction | 7,9 |  |  |  |  | 6250 |  |  | 164140 |  |  |  | 170390 | 42493129.35 | 33.64%
LCC | 2013-08-22 | LCC166 | Site Work | 7 |  |  |  |  | 18818.75 | [6 empty] | 18818.75 | 42511948.1 | 33.65%
LCC | 2013-09-10 | LCC172 | Site Work and Tower Construction | 7,9 |  |  |  |  | 73800 |  |  | 157865 |  |  |  | 231665 | 42743613.1 | 33.84%
LCC | 2013-09-10 | LCC173 | Site Work and Tower Construction | 7,9 |  |  |  |  | 5500 |  |  | 85147 |  |  |  | 90647 | 42834260.1 | 33.91%
LCC | 2013-09-10 | LCC174 | Tower Construction | 9 | [7 empty] | 13000 |  |  |  | 13000 | 42847260.1 | 33.92%
LCC | 2013-09-10 | LCC175 | Site Work and Tower Construction | 7,9 |  |  |  |  | 12375 |  |  | 95680 |  |  |  | 108055 | 42955315.1 | 34%
LCC | 2013-11-19 | LCC176 | Site Work and Tower Construction | 9 | [7 empty] | 25100 |  |  |  | 25100 | 42980415.1 | 34.02%
LCC | 2013-11-19 | LCC177 | Site Work and Tower Construction | 9 | [7 empty] | 45326 |  |  |  | 45326 | 43025741.1 | 34.06%
LCC | 2013-11-19 | LCC178 | Site Work and Tower Construction | 9 | [7 empty] | 52216.9 |  |  |  | 52216.9 | 43077958 | 34.1%
LCC | 2013-11-19 | LCC180 | Site Work and Tower Construction | 7,9 |  |  |  |  | 22000 |  |  | 39560.5 |  |  |  | 61560.5 | 43139518.5 | 34.15%
LCC | 2013-11-21 | LCC0179 | Tower Construction | 9 | [7 empty] | 25900 |  |  |  | 25900 | 43165418.5 | 34.17%
[17 empty] | 43165418.5 | 34.17%
[17 empty] | 43165418.5 | 34.17%
MA | 2010-10-07 | MA-0001 | Personnel Services 7/16-9/30/10 and Travel Expenses | 1. & 11. | 10021.19 | [9 empty] | 486.42 | 10507.61 | 43175926.11 | 34.18%
MA | 2010-11-15 | MA-0002 | Personnel Services October 2010 | 1 | 5199.49 | [10 empty] | 5199.49 | 43181125.6 | 34.18%
MA | 2010-12-15 | MA-0003 | Personnel Services Nov 2010 mapping software; pens | 1. & 11. | 5008.43 | [9 empty] | 331.49 | 5339.92 | 43186465.52 | 34.19%
MA | 2011-01-06 | MA-0004 | Personnel Services December 2010; paper/news- letters | 1. &11. | 6946.13 | [9 empty] | 11.99 | 6958.12 | 43193423.64 | 34.19%
MA | 2011-02-22 | MA-0005 | Personnel Services January 2011; mapping software | 1. & 11. | 9326.4 | [9 empty] | 620.95 | 9947.35 | 43203370.99 | 34.2%
MA | 2011-03-16 | MA-0006 | Personnel Services February 2010 | 1 | 8185.12 | [10 empty] | 8185.12 | 43211556.11 | 34.21%
MA | 2011-04-22 | MA-0007 | Personnel Services March 2011 and purchase of BTOP Property Tags | 1. & 11. | 7942.91 | [9 empty] | 615 | 8557.91 | 43220114.02 | 34.21%
MA | 2011-06-10 | MA-0008 | Personnel Services April & Supplies | 1,11 | 8453.07 | [9 empty] | 199.99 | 8653.06 | 43228767.08 | 34.22%
MA | 2011-06-10 | MA-0009 | Personnel Services May & Supplies | 1,11 | 19709.97 | [9 empty] | 1001.99 | 20711.96 | 43249479.04 | 34.24%
MA | 2011-08-01 | MA-0010 | Personnel Services | 1 | 6478.67 | [10 empty] | 6478.67 | 43255957.71 | 34.24%
MA | 2011-09-07 | MA-0011 | Personnel Services | 1 | 13753.1 | [10 empty] | 13753.1 | 43269710.81 | 34.25%
MA | 2011-11-18 | MA-0012 | Payroll, Misc | 1,11 | 26775.21 | [9 empty] | 749.02 | 27524.23 | 43297235.04 | 34.27%
MA | 2011-12-14 | MA-0013 | Payroll | 1 | 17296.32 | [10 empty] | 17296.32 | 43314531.36 | 34.29%
MA | 2012-01-17 | MA-0014 | Payroll | 1,11 | 18654.99 |  | , | [7 empty] | 224.47 | 18879.46 | 43333410.82 | 34.3%
MA | 2012-02-06 | MA-0015 | Supplies & Payroll | 1,11 | 19321.49 | [9 empty] | 964.63 | 20286.12 | 43353696.94 | 34.32%
MA | 2012-03-08 | MA-0016 | Payroll | 1 | 18764.29 | [10 empty] | 18764.29 | 43372461.23 | 34.33%
MA | 2012-04-10 | MA-0017 | Payroll | 1,11 | 20919.45 | [9 empty] | 384.27 | 21303.72 | 43393764.95 | 34.35%
MA | 2012-05-07 | MA-0018 | Payroll | 1,11 | 24476.85 | [9 empty] | 2017.67 | 26494.52 | 43420259.47 | 34.37%
MA | 2012-07-11 | MA00019 | Payroll and Travel | 1,11 | 70622.43 | [9 empty] | 97 | 70719.43 | 43490978.9 | 34.43%
MA | 2012-07-18 | MA00020 | Payroll and Travel | 1,11 | 14227.73 | [9 empty] | 1462.83 | 15690.56 | 43506669.46 | 34.44%
MA | 2012-08-14 | MA00021 | Payroll, Workers Comp | 1 | 14568.5 | [10 empty] | 14568.5 | 43521237.96 | 34.45%
MA | 2012-09-10 | MA00022 | Payroll | 1 | 23164.38 | [10 empty] | 23164.38 | 43544402.34 | 34.47%
MA | 2012-11-20 | MA00024 | Payroll | 1,11 | 18965.58 | [9 empty] | 736.85 | 19702.43 | 43564104.77 | 34.49%
MA | 2012-12-13 | MA00023 | Payroll | 1 | 16083.46 | [10 empty] | 16083.46 | 43580188.23 | 34.5%
MA | 2012-12-21 | MA00025 | Payroll and Office Supplies | 1,11 | 21058.88 | [9 empty] | 47.99 | 21106.87 | 43601295.1 | 34.52%
MA | 2013-01-11 | MA00026 | Payroll, Workers Comp | 1 | 20934.2 | [10 empty] | 20934.2 | 43622229.3 | 34.53%
MA | 2013-02-21 | MA00027 | Payroll | 1 | 22213.38 | [10 empty] | 22213.38 | 43644442.68 | 34.55%
MA | 2013-03-12 | MA00028 | Admin Payroll | 1,11 | 22422.55 | [9 empty] | 2308.03 | 24730.58 | 43669173.26 | 34.57%
MA | 2013-05-03 | MA00029 | Payroll | 1,11 | 21880.86 | [9 empty] | 1057.94 | 22938.8 | 43692112.06 | 34.59%
MA | 2013-06-06 | MA00030 | Payroll | 1 | 21915.23 | [9 empty] | 3855.74 | 25770.97 | 43717883.03 | 34.61%
MA | 2013-06-11 | MA00031 | Payroll | 1 | 26282.73 | [9 empty] | 3768.69 | 30051.42 | 43747934.45 | 34.63%
MA | 2013-07-24 | MA00032 | Payroll | 1 | 29804.93 | [10 empty] | 29804.93 | 43777739.38 | 34.66%
MA | 2013-09-10 | MA00034 | Payroll and Travel | 1,11 | 22189.02 | [9 empty] | 1967.86 | 24156.88 | 43801896.26 | 34.67%
MA | 2013-10-16 | MA00035 | Payroll and Travel | 1,11 | 23192.68 | [9 empty] | 510.22 | 23702.9 | 43825599.16 | 34.69%
MA | 2013-11-21 | MA00036 | Payroll and Travel | 1,11 | 18042.4 | [9 empty] | 969.9 | 19012.3 | 43844611.46 | 34.71%
[17 empty] | 43844611.46 | 34.71%
[17 empty] | 43844611.46 | 34.71%
WVDE | 2013-10-17 | WVDE1 | Payroll and Travel | 1,11 | 31521.69 | [9 empty] | 1933.43 | 33455.12 | 43878066.58 | 34.73%
[17 empty] | 43878066.58 | 34.73%
[17 empty] | 43878066.58 | 34.73%
WVNET | 2013-10-10 | WVNET1 | Payroll, Equipment, Travel | 1,10,11 | 45990 | [8 empty] | 116.6 | 1990.06 | 48096.66 | 43926163.24 | 34.77%
[17 empty] | 43926163.24 | 34.77%
[17 empty] | 43926163.24 | 34.77%
WVOT | 2010-09-22 | OT-0001 | Personnel Services August 2010 | 4 |  |  | 9731.25 | [8 empty] | 9731.25 | 43935894.49 | 34.78%
WVOT | 2010-10-21 | OT-0002 | Personnel Services Sept 2010 | 4 |  |  | 4897.5 | [8 empty] | 4897.5 | 43940791.99 | 34.78%
WVOT | 2010-10-26 | OTBTOP-1 | CISCO Routers - 1st pmt of PO ISCL0002 | 10 | [9 empty] | 13858314.3 |  | 13858314.3 | 57799106.29 | 45.75%
WVOT | 2010-11-29 | OTBTOP-3 | CISCO Routers - 2nd pmt of PO ISCL0002 (final) | 10 | [9 empty] | 10191290.2 |  | 10191290.2 | 67990396.49 | 53.82%
WVOT | 2010-12-08 | OTBTOP-4 | Personnel Services October 2010 - | 4 |  |  | 6288.75 | [8 empty] | 6288.75 | 67996685.24 | 53.83%
WVOT | 2010-12-20 | OTBTOP-5 | Personnel Services November 2010 | 4,11 |  |  | 3990 | [7 empty] | 280.92 | 4270.92 | 68000956.16 | 53.83%
WVOT | 2011-01-27 | OTBTOP-7 | Personnel Services Dec 2010 | 4,11 |  |  | 6528.75 | [7 empty] | 225.11 | 6753.86 | 68007710.02 | 53.84%
WVOT | 2011-01-27 | OTBTOP-8 | Verizon - Engineering services for Sept & Oct 2010 | 4 |  |  | 249123 | [8 empty] | 249123 | 68256833.02 | 54.03%
WVOT | 2011-02-24 | OTBTOP-10 | Personnel Services January 2011 | 4,11 |  |  | 4256.25 | [7 empty] | 1288.9 | 5545.15 | 68262378.17 | 54.04%
WVOT | 2011-02-25 | OTBTOP-11 | Personnel Services January 2011/Verizon | 4 |  |  | 60637 | [8 empty] | 60637 | 68323015.17 | 54.09%
WVOT | 2011-03-21 | OTBTOP-12 | Inv#JF30120P01767 - partial purchase of core network infrastructure for Flatwoods & Clarksburg - See OTBTOP-2 | 10 | [9 empty] | 183581.94 |  | 183581.94 | 68506597.11 | 54.23%
WVOT | 2011-03-23 | OTBTOP-13 | Verizon Personnel Services February 2011 | 4 |  |  | 53722 | [8 empty] | 53722 | 68560319.11 | 54.27%
WVOT | 2011-03-28 | OTBTOP-14 | WVOT Personnel Services for February 2011 | 1,4 | 984 |  | 12431.25 | [8 empty] | 13415.25 | 68573734.36 | 54.28%
WVOT | 2011-04-27 | OTBTOP-15 | Verizon - Personnel Project Mngr & Proj Engineer March 2011 | 4 |  |  | 49508 | [8 empty] | 49508 | 68623242.36 | 54.32%
WVOT | 2011-05-03 | OTBTOP-16 | Microwave Radios; Patch Cables; OT Personnel Mar'11; Travel | 4,10,11 |  |  | 8167.13 | [6 empty] | 2251556.3 | 3919.25 | 2263642.68 | 70886885.04 | 56.12%
WVOT | 2011-06-03 | OTBTOP-18 | Verizon - personnel Project Mngr & Proj Engineer March/april 2011 | 4 |  |  | 86445 | [8 empty] | 86445 | 70973330.04 | 56.18%
WVOT | 2011-06-27 | OTBTOP-20 | Verizon - personnel Project Mngr & Proj Engineer May/June 2011 | 4 |  |  | 6566.25 | [8 empty] | 6566.25 | 70979896.29 | 56.19%
WVOT | 2011-06-27 | OTBTOP-19 | Verizon - personnel Project Mngr & Proj Engineer May/June 2011 | 4 |  |  | 74240 | [8 empty] | 74240 | 71054136.29 | 56.25%
WVOT | 2011-06-28 | OTBTOP-21 | Router Shipment | 11 | [10 empty] | 5018.3 | 5018.3 | 71059154.59 | 56.25%
WVOT | 2011-07-20 | OTBTOP-22 | Fiber optic buildout | 10,9 | [5 empty] | 11410 |  |  |  | 393224.38 |  | 404634.38 | 71463788.97 | 56.57%
WVOT | 2011-07-21 | OTBTOP-24 | Verizon - personnel Project Mngr & Proj Engineer May/June 2011 | 4 |  |  | 8407.34 | [8 empty] | 8407.34 | 71472196.31 | 56.58%
WVOT | 2011-07-27 | OTBTOP-17 | Verizon Personnel Services MAY 2011 | 4 |  |  | 9998.25 | [8 empty] | 9998.25 | 71482194.56 | 56.59%
WVOT | 2011-08-02 | OTBTOP-25 | Senior Personnel Services | 4 |  |  | 62931 | [8 empty] | 62931 | 71545125.56 | 56.64%
WVOT | 2011-08-29 | OTBTOP-26 | Project MGMT | 4 |  |  | 78619 | [8 empty] | 78619 | 71623744.56 | 56.7%
WVOT | 2011-08-29 | OTBTOP-27 | Computers and Access | 10 | [9 empty] | 12184.21 |  | 12184.21 | 71635928.77 | 56.71%
WVOT | 2011-08-29 | OTBTOP-28 | Project MGMT | 4 |  |  | 8917.5 | [8 empty] | 8917.5 | 71644846.27 | 56.72%
WVOT | 2011-10-11 | OTBTOP29 | Misc. Office Supplies | 10 | [9 empty] | 50987.43 |  | 50987.43 | 71695833.7 | 56.76%
WVOT | 2011-10-21 | OTBTOP30 | Project MGMT | 4 |  |  | 68223 | [8 empty] | 68223 | 71764056.7 | 56.81%
WVOT | 2011-10-21 | OTBTOP31 | Project MGMT | 4 |  |  | 20187.15 | [8 empty] | 20187.15 | 71784243.85 | 56.83%
WVOT | 2011-11-16 | OTBTOP32 | Contractor Payroll | 4 |  |  | 89812 | [8 empty] | 89812 | 71874055.85 | 56.9%
WVOT | 2011-11-18 | OTBTOP33 | Contractor Payroll | 4 |  |  | 13839.47 | [8 empty] | 13839.47 | 71887895.32 | 56.91%
WVOT | 2011-12-05 | OTBTOP34 | Contractor Payroll | 4 |  |  | 73245 | [8 empty] | 73245 | 71961140.32 | 56.97%
WVOT | 2011-12-20 | OTBTOP36 | Contractor Payroll | 4 |  |  | 70481 | [8 empty] | 70481 | 72031621.32 | 57.02%
WVOT | 2012-01-09 | OTBTOP37 | Misc. Office Supplies | 11 | [10 empty] | 3345.56 | 3345.56 | 72034966.88 | 57.02%
WVOT | 2012-01-10 | OTBTOP35 | PAYROLL | 4 |  |  | 8821.51 | [8 empty] | 8821.51 | 72043788.39 | 57.03%
WVOT | 2012-02-02 | OTBTOP40 | Payroll, MISC | 1,11 | 9367.5 | [9 empty] | 46.99 | 9414.49 | 72053202.88 | 57.04%
WVOT | 2012-02-03 | OTBTOP41 | Payroll | 4 |  |  | 64883.5 | [8 empty] | 64883.5 | 72118086.38 | 57.09%
WVOT | 2012-02-23 | OTBTOP42 | Contractor Payroll | 4,11 |  |  | 94302.5 | [7 empty] | 78.98 | 94381.48 | 72212467.86 | 57.16%
WVOT | 2012-02-23 | OTBTOP43 | Contractor Payroll | 1,4 | 351 |  | 61660 | [8 empty] | 62011 | 72274478.86 | 57.21%
WVOT | 2012-03-30 | OTBTOP45 | Contractor Payroll | 1 | 65897 | [10 empty] | 65897 | 72340375.86 | 57.27%
WVOT | 2012-04-03 | OTBTOP46 | Contractor Payroll | 4 |  |  | 6969.5 | [8 empty] | 6969.5 | 72347345.36 | 57.27%
WVOT | 2012-05-01 | OTBTOP47 | Contractor Payroll | 4 |  |  | 27992 | [8 empty] | 27992 | 72375337.36 | 57.29%
WVOT | 2012-06-05 | OTBTOP48 | Contractor Payroll | 1,4 | 19428.48 |  | 49278 | [8 empty] | 68706.48 | 72444043.84 | 57.35%
WVOT | 2012-07-11 | OTBTOP49 | Engineering and Legal Fees | 4 |  |  | 5758.25 | [8 empty] | 5758.25 | 72449802.09 | 57.35%
WVOT | 2012-07-11 | OTBTOP50 | Contractor Payroll | 1,4 | 6910.31 |  | 25737 | [8 empty] | 32647.31 | 72482449.4 | 57.38%
WVOT | 2012-09-04 | OTBTOP53 | Contractor Payroll | 1 | 4797 | [10 empty] | 4797 | 72487246.4 | 57.38%
WVOT | 2012-10-05 | OTBTOP51 | Contractor Payroll | 1,4 | 56729 |  | 47570 | [8 empty] | 104299 | 72591545.4 | 57.46%
WVOT | 2012-12-13 | OTBTOP55 | Contractor Payroll | 1,4 | 21130.8 |  | 46126.5 | [8 empty] | 67257.3 | 72658802.7 | 57.52%
WVOT | 2012-12-18 | OTBTOP56 | WVNET | 10 | [9 empty] | 3378151.36 |  | 3378151.36 | 76036954.06 | 60.19%
WVOT | 2013-02-11 | OTBTOP54 | Contractor Payroll | 1,4 | -42245.38 |  | 54292 | [8 empty] | 12046.62 | 76049000.68 | 60.2%
WVOT | 2013-02-11 | OTBTOP57 | Contractor Payroll | 1,4 | 6529.94 |  | 101050 | [8 empty] | 107579.94 | 76156580.62 | 60.29%
WVOT | 2013-02-11 | OTBTOP58 | Contractor Payroll | 1,4 | 54389.7 |  | 29475 | [8 empty] | 83864.7 | 76240445.32 | 60.35%
WVOT | 2013-02-11 | OTBTOP59 | Contractor Payroll | 1 | 127370 | [10 empty] | 127370 | 76367815.32 | 60.45%
WVOT | 2013-02-11 | OTBTOP60 | Contractor Payroll | 1,4 | 26579.25 |  | 10587.5 | [8 empty] | 37166.75 | 76404982.07 | 60.48%
WVOT | 2013-05-31 | RETURN | RETURN | RETURN | -10515.81 | [10 empty] | -10515.81 | 76394466.26 | 60.48%
WVOT | 2013-06-11 | OTBTOP63 | Contractor Payroll | 1 | 20025.8 | [10 empty] | 20025.8 | 76414492.06 | 60.49%
WVOT | 2013-06-12 | OTBTOP64 | Payroll | 1 | 61348 | [10 empty] | 61348 | 76475840.06 | 60.54%
WVOT | 2013-06-12 | OTBTOP65 | Payroll | 1 | 114475.05 | [10 empty] | 114475.05 | 76590315.11 | 60.63%
WVOT | 2013-06-26 | OTBTOP66 | Payroll | 1 | 13098.99 | [10 empty] | 13098.99 | 76603414.1 | 60.64%
WVOT | 2013-07-22 | OTBTOP68 | Payroll | 4 |  |  | 194302.5 | [8 empty] | 194302.5 | 76797716.6 | 60.79%
WVOT | 2013-08-08 | OTBTOP66C | Payroll | 4 | 13556.92 | [10 empty] | 13556.92 | 76811273.52 | 60.81%
WVOT | 2013-08-08 | OTBTOP67 | Payroll | 1,4 | 7123.56 |  | 35968 | [8 empty] | 43091.56 | 76854365.08 | 60.84%
WVOT | 2013-08-14 | OTBTOP69 | Payroll | 1,4 | 4916.93 |  | 88125 | [8 empty] | 93041.93 | 76947407.01 | 60.91%
WVOT | 2013-08-14 | OTBTOP70 | Payroll | 1,4 | 14941.69 |  | 51900 | [8 empty] | 66841.69 | 77014248.7 | 60.97%
WVOT | 2013-11-05 | OTBTOP71 | Payroll | 1 | 49695.13 | [10 empty] | 49695.13 | 77063943.83 | 61.01%
WVOT | 2013-11-05 | OTBTOP73 | Payroll | 1,4 | 14460 |  | 41175 | [8 empty] | 55635 | 77119578.83 | 61.05%
WVOT | 2013-11-15 | OTBTOP74 | Payroll | 1 | 26310 | [10 empty] | 26310 | 77145888.83 | 61.07%
WVOT | 2013-11-25 | OTBTOP75 | Payroll | 1 | 5527.86 | [10 empty] | 5527.86 | 77151416.69 | 61.07%
WVOT | 2013-11-25 | OTBTOP76 | Equipment | 10 | [9 empty] | 352244 |  | 352244 | 77503660.69 | 61.35%
WVOT | 2013-11-25 | OTBTOP77 | WVU Equipment | 10 | [9 empty] | 201777.56 |  | 201777.56 | 77705438.25 | 61.51%
WVOT | 2013-12-02 | OTBTOP72 | Payroll | 1,4 | 130789.95 |  | 16250 | [8 empty] | 147039.95 | 77852478.2 | 61.63%
[17 empty] | 77852478.2 | 61.63%
[17 empty] | 77852478.2 | 61.63%
WVOT/FTR | 2012-01-10 | OTBTOP37 | LCR Construction | 9 | [6 empty] | 93168 |  |  |  |  | 93168 | 77945646.2 | 61.7%
WVOT/FTR | 2012-01-10 | OTBTOP38 | LCR Construction | 9 | [6 empty] | 103576 |  |  |  |  | 103576 | 78049222.2 | 61.79%
WVOT/FTR | 2012-01-10 | OTBTOP39 | LCR Construction | 9 | [6 empty] | 44820 |  |  |  |  | 44820 | 78094042.2 | 61.82%
WVOT/FTR | 2012-02-23 | FRONTIER01 | Payroll | 5 |  |  |  | 85160.4 | [7 empty] | 85160.4 | 78179202.6 | 61.89%
WVOT/FTR | 2012-04-10 | FRONTIER02 | LCR Construction | 9 | [5 empty] | 70100.56 | [5 empty] | 70100.56 | 78249303.16 | 61.94%
WVOT/FTR | 2012-04-17 | FRONTIER03 | Audit Fees | 1 | 182500 | [10 empty] | 182500 | 78431803.16 | 62.09%
WVOT/FTR | 2012-06-05 | FRONTIER04 | LCR Construction | 9 | [6 empty] | 202028.61 |  |  |  |  | 202028.61 | 78633831.77 | 62.25%
WVOT/FTR | 2012-06-05 | FRONTIER05 | LCR Construction | 9 | [6 empty] | 160956.51 |  |  |  |  | 160956.51 | 78794788.28 | 62.38%
WVOT/FTR | 2012-06-05 | FRONTIER06 | LCR Construction | 9,11 | [6 empty] | 190177.41 |  |  |  | 981.67 | 191159.08 | 78985947.36 | 62.53%
WVOT/FTR | 2012-08-09 | FRONTIER07 | LCR Construction | 9 | [6 empty] | 50731.72 |  |  |  |  | 50731.72 | 79036679.08 | 62.57%
WVOT/FTR | 2012-08-09 | FRONTIER08 | LCR Construction | 9 | [6 empty] | 83274.09 |  |  |  |  | 83274.09 | 79119953.17 | 62.63%
WVOT/FTR | 2012-08-09 | FRONTIER09 | LCR Construction | 9 | [6 empty] | 128833.23 |  |  |  |  | 128833.23 | 79248786.4 | 62.73%
WVOT/FTR | 2012-08-09 | FRONTIER10 | LCR Construction | 9 | [6 empty] | 258952.62 |  |  |  |  | 258952.62 | 79507739.02 | 62.94%
WVOT/FTR | 2012-08-09 | FRONTIER11 | LCR Construction | 9 | [6 empty] | 416346.81 |  |  |  |  | 416346.81 | 79924085.83 | 63.27%
WVOT/FTR | 2012-08-09 | FRONTIER12 | LCR Construction | 9 | [6 empty] | 137273.55 |  |  |  |  | 137273.55 | 80061359.38 | 63.38%
WVOT/FTR | 2012-08-09 | FRONTIER13 | LCR Construction | 9 | [6 empty] | 376214.61 |  |  |  |  | 376214.61 | 80437573.99 | 63.68%
WVOT/FTR | 2012-08-09 | FRONTIER14 | LCR Construction | 9 | [6 empty] | 16277.99 |  |  |  |  | 16277.99 | 80453851.98 | 63.69%
WVOT/FTR | 2012-08-09 | FRONTIER15 | LCR Construction | 9 | [6 empty] | 394200.44 |  |  |  |  | 394200.44 | 80848052.42 | 64%
WVOT/FTR | 2012-08-09 | FRONTIER16 | LCR Construction | 9 | [6 empty] | 89717.72 |  |  |  |  | 89717.72 | 80937770.14 | 64.07%
WVOT/FTR | 2012-08-10 | FRONTIER17 | LCR Construction | 9 | [6 empty] | 214967.41 |  |  |  |  | 214967.41 | 81152737.55 | 64.24%
WVOT/FTR | 2012-08-10 | FRONTIER18 | LCR Construction | 9 | [6 empty] | 58384.78 |  |  |  |  | 58384.78 | 81211122.33 | 64.29%
WVOT/FTR | 2012-08-10 | FRONTIER19 | LCR Construction | 9 | [6 empty] | 99389.13 |  |  |  |  | 99389.13 | 81310511.46 | 64.37%
WVOT/FTR | 2012-08-10 | FRONTIER20 | LCR Construction | 9 | [6 empty] | 91146.85 |  |  |  |  | 91146.85 | 81401658.31 | 64.44%
WVOT/FTR | 2012-08-10 | FRONTIER21 | LCR Construction | 9 | [6 empty] | 177839.12 |  |  |  |  | 177839.12 | 81579497.43 | 64.58%
WVOT/FTR | 2012-08-10 | FRONTIER22 | LCR Construction | 9 | [6 empty] | 85434.94 |  |  |  |  | 85434.94 | 81664932.37 | 64.65%
WVOT/FTR | 2012-08-10 | FRONTIER23 | LCR Construction | 9 | [6 empty] | 156138.73 |  |  |  |  | 156138.73 | 81821071.1 | 64.77%
WVOT/FTR | 2012-08-10 | FRONTIER24 | LCR Construction | 9 | [6 empty] | 95471.85 |  |  |  |  | 95471.85 | 81916542.95 | 64.85%
WVOT/FTR | 2012-08-10 | FRONTIER25 | LCR Construction | 9 | [6 empty] | 134474.63 |  |  |  |  | 134474.63 | 82051017.58 | 64.95%
WVOT/FTR | 2012-08-10 | FRONTIER26 | LCR Construction | 9 | [6 empty] | 82077.48 |  |  |  |  | 82077.48 | 82133095.06 | 65.02%
WVOT/FTR | 2012-08-10 | FRONTIER27 | LCR Construction | 9 | [6 empty] | 77230.27 |  |  |  |  | 77230.27 | 82210325.33 | 65.08%
WVOT/FTR | 2012-08-10 | FRONTIER28 | LCR Construction | 9 | [6 empty] | 77772.46 |  |  |  |  | 77772.46 | 82288097.79 | 65.14%
WVOT/FTR | 2012-08-10 | FRONTIER29 | LCR Construction | 9 | [6 empty] | 117665.98 |  |  |  |  | 117665.98 | 82405763.77 | 65.23%
WVOT/FTR | 2012-08-10 | FRONTIER30 | LCR Construction | 9 | [6 empty] | 99145.59 |  |  |  |  | 99145.59 | 82504909.36 | 65.31%
WVOT/FTR | 2012-08-10 | FRONTIER31 | LCR Construction | 9 | [6 empty] | 158199.51 |  |  |  |  | 158199.51 | 82663108.87 | 65.44%
WVOT/FTR | 2012-08-10 | FRONTIER32 | LCR Construction | 9 | [6 empty] | 45050.53 |  |  |  |  | 45050.53 | 82708159.4 | 65.47%
WVOT/FTR | 2012-08-10 | FRONTIER34 | LCR Construction | [7 empty] | 552557.9 |  |  |  |  | 552557.9 | 83260717.3 | 65.91%
WVOT/FTR | 2012-09-04 | FRONTIER35 | LCR Construction | 9 | [6 empty] | 155755.42 |  |  |  |  | 155755.42 | 83416472.72 | 66.03%
WVOT/FTR | 2012-09-04 | FRONTIER36 | LCR Construction | 9 | [6 empty] | 211813.61 |  |  |  |  | 211813.61 | 83628286.33 | 66.2%
WVOT/FTR | 2012-09-04 | FRONTIER38 | LCR Construction | 9 | [6 empty] | 194088.95 |  |  |  |  | 194088.95 | 83822375.28 | 66.36%
WVOT/FTR | 2012-09-10 | FRONTIER37 | LCR Construction | 9 | [6 empty] | 211371.63 |  |  |  |  | 211371.63 | 84033746.91 | 66.52%
WVOT/FTR | 2012-12-21 | FRONTIER41 | LCR Construction | 9 | [6 empty] | 308916.12 |  |  |  |  | 308916.12 | 84342663.03 | 66.77%
WVOT/FTR | 2012-12-21 | FRONTIER42 | LCR Construction | 9 | [6 empty] | 798382.3 |  |  |  |  | 798382.3 | 85141045.33 | 67.4%
WVOT/FTR | 2012-12-21 | FRONTIER43 | LCR Construction | 9 | [6 empty] | 238677.32 |  |  |  |  | 238677.32 | 85379722.65 | 67.59%
WVOT/FTR | 2012-12-21 | FRONTIER44 | LCR Construction | 9 | [6 empty] | 135670 |  |  |  |  | 135670 | 85515392.65 | 67.7%
WVOT/FTR | 2012-12-21 | FRONTIER45 | LCR Construction | 9 | [6 empty] | 147723.02 |  |  |  |  | 147723.02 | 85663115.67 | 67.81%
WVOT/FTR | 2012-12-21 | FRONTIER46 | LCR Construction | 9 | [6 empty] | 231215.88 |  |  |  |  | 231215.88 | 85894331.55 | 68%
WVOT/FTR | 2012-12-21 | FRONTIER47 | LCR Construction | 9 | [6 empty] | 786234.85 |  |  |  |  | 786234.85 | 86680566.4 | 68.62%
WVOT/FTR | 2012-12-21 | FRONTIER48 | LCR Construction | 9 | [6 empty] | 433540.38 |  |  |  |  | 433540.38 | 87114106.78 | 68.96%
WVOT/FTR | 2013-01-04 | FRONTIER40 | LCR Construction | 9 | [6 empty] | 449575.15 |  |  |  |  | 449575.15 | 87563681.93 | 69.32%
WVOT/FTR | 2013-03-11 | FRONTIER49 | Project Management | 1 | 85160.4 | [10 empty] | 85160.4 | 87648842.33 | 69.38%
WVOT/FTR | 2013-05-31 | RETURN | RETURN | RETURN | [6 empty] | -127590.76 |  |  |  |  | -127590.76 | 87521251.57 | 69.28%
WVOT/FTR | 2013-06-11 | FRONTIER53 | LCR Construction | 9 | [6 empty] | 8635.78 |  |  |  |  | 8635.78 | 87529887.35 | 69.29%
WVOT/FTR | 2013-06-11 | FRONTIER54 | LCR Construction | 9 | [6 empty] | 337449.63 |  |  |  |  | 337449.63 | 87867336.98 | 69.56%
WVOT/FTR | 2013-06-11 | FRONTIER56 | LCR Construction | 9 | [6 empty] | 229983.24 |  |  |  |  | 229983.24 | 88097320.22 | 69.74%
WVOT/FTR | 2013-06-11 | FRONTIER59 | LCR Construction | 9 | [6 empty] | 18680.5 |  |  |  |  | 18680.5 | 88116000.72 | 69.75%
WVOT/FTR | 2013-06-11 | FRONTIER60 | LCR Construction | 9 | [6 empty] | 169890.59 |  |  |  |  | 169890.59 | 88285891.31 | 69.89%
WVOT/FTR | 2013-06-11 | FRONTIER61 | LCR Construction | 9 | [6 empty] | 173760.08 |  |  |  |  | 173760.08 | 88459651.39 | 70.03%
WVOT/FTR | 2013-06-11 | FRONTIER62 | LCR Construction | 9 | [6 empty] | 254830.32 |  |  |  |  | 254830.32 | 88714481.71 | 70.23%
WVOT/FTR | 2013-06-11 | FRONTIER63 | LCR Construction | 9 | [6 empty] | 116477.35 |  |  |  |  | 116477.35 | 88830959.06 | 70.32%
WVOT/FTR | 2013-06-11 | FRONTIER64 | LCR Construction | 9 | [6 empty] | 162542.39 |  |  |  |  | 162542.39 | 88993501.45 | 70.45%
WVOT/FTR | 2013-06-26 | FRONTIER52 | LCR Construction | 9 | [6 empty] | 430393.85 |  |  |  |  | 430393.85 | 89423895.3 | 70.79%
WVOT/FTR | 2013-06-26 | FRONTIER55 | LCR Construction | 9 | [6 empty] | 107380.77 |  |  |  |  | 107380.77 | 89531276.07 | 70.87%
WVOT/FTR | 2013-06-26 | FRONTIER57 | LCR Construction | 9 | [6 empty] | 143151.31 |  |  |  |  | 143151.31 | 89674427.38 | 70.99%
WVOT/FTR | 2013-06-26 | FRONTIER58 | LCR Construction | 9 | [6 empty] | 319621.4 |  |  |  |  | 319621.4 | 89994048.78 | 71.24%
WVOT/FTR | 2013-06-26 | FRONTIER67 | LCR Construction | 9 | [6 empty] | 44671.88 |  |  |  |  | 44671.88 | 90038720.66 | 71.28%
WVOT/FTR | 2013-06-26 | FRONTIER69 | LCR Construction | 9 | [6 empty] | 114686.19 |  |  |  |  | 114686.19 | 90153406.85 | 71.37%
WVOT/FTR | 2013-06-26 | FRONTIER70 | LCR Construction | 9 | [6 empty] | 11849.86 |  |  |  |  | 11849.86 | 90165256.71 | 71.38%
WVOT/FTR | 2013-06-26 | FRONTIER71 | LCR Construction | 9 | [6 empty] | 248992.53 |  |  |  |  | 248992.53 | 90414249.24 | 71.57%
WVOT/FTR | 2013-06-26 | FRONTIER72 | LCR Construction | 9 | [6 empty] | 151378.58 |  |  |  |  | 151378.58 | 90565627.82 | 71.69%
WVOT/FTR | 2013-06-27 | FRONTIER66 | LCR Construction | 9 | [6 empty] | 157373.39 |  |  |  |  | 157373.39 | 90723001.21 | 71.82%
WVOT/FTR | 2013-08-26 | FRONTIER75 | LCR Construction | 9 | [6 empty] | 447703.26 |  |  |  |  | 447703.26 | 91170704.47 | 72.17%
WVOT/FTR | 2013-08-26 | FRONTIER76 | LCR Construction | 9 | [6 empty] | 310786.35 |  |  |  |  | 310786.35 | 91481490.82 | 72.42%
WVOT/FTR | 2013-08-26 | FRONTIER77 | LCR Construction | 9 | [6 empty] | 362964.42 |  |  |  |  | 362964.42 | 91844455.24 | 72.71%
WVOT/FTR | 2013-10-10 | FRONTIER87 | LCR Construction | 9 | [6 empty] | 324741.61 |  |  |  |  | 324741.61 | 92169196.85 | 72.96%
WVOT/FTR | 2013-10-23 | FRONTIER80 | LCR Construction | 9 | [6 empty] | 390715.87 |  |  |  |  | 390715.87 | 92559912.72 | 73.27%
WVOT/FTR | 2013-10-23 | FRONTIER83 | LCR Construction | 9 | [6 empty] | 328668.63 |  |  |  |  | 328668.63 | 92888581.35 | 73.53%
WVOT/FTR | 2013-10-23 | FRONTIER84 | LCR Construction | 9 | [6 empty] | 382410.72 |  |  |  |  | 382410.72 | 93270992.07 | 73.84%
WVOT/FTR | 2013-10-23 | FRONTIER89 | LCR Construction | 9 | [6 empty] | 132225.58 |  |  |  |  | 132225.58 | 93403217.65 | 73.94%
WVOT/FTR | 2013-11-15 | FRONTIER82 | LCR Construction | 9 | [6 empty] | 583936.74 |  |  |  |  | 583936.74 | 93987154.39 | 74.4%
WVOT/FTR | 2013-11-15 | FRONTIER97 | LCR Construction | 9 | [6 empty] | 1805804.2 |  |  |  |  | 1805804.2 | 95792958.59 | 75.83%
WVOT/FTR | 2013-11-15 | FRONTIER98 | LCR Construction | 9 | [6 empty] | 152048.09 |  |  |  |  | 152048.09 | 95945006.68 | 75.95%
WVOT/FTR | 2013-11-20 | FRONTIER79 | LCR Construction | 9 | [6 empty] | 346057.56 |  |  |  |  | 346057.56 | 96291064.24 | 76.23%
WVOT/FTR | 2013-11-25 | FRONTIER78 | LCR Construction | 9 | [6 empty] | 313937.53 |  |  |  |  | 313937.53 | 96605001.77 | 76.47%
WVOT/FTR | 2013-12-02 | FRONTIER99 | LCR Construction | 9 | [6 empty] | 1089839.56 |  |  |  |  | 1089839.56 | 97694841.33 | 77.34%
WVOT/FTR | 2013-12-02 | FRONTIER101 | LCR Construction | 9 | [6 empty] | 366476.6 |  |  |  |  | 366476.6 | 98061317.93 | 77.63%
WVOT/FTR | 2013-12-10 | FRONTIER102 | LCR Construction | 9 | [6 empty] | 2179351.68 |  |  |  |  | 2179351.68 | 100240669.61 | 79.35%
WVOT/FTR | 2013-12-10 | FRONTIER103 | LCR Construction | 9 | [6 empty] | 1202515.25 |  |  |  |  | 1202515.25 | 101443184.86 | 80.3%
WVOT/FTR | 2013-12-10 | FRONTIER107 | LCR Construction | 9 | [6 empty] | 245968.57 |  |  |  |  | 245968.57 | 101689153.43 | 80.5%
[17 empty] | 101689153.43 | 80.5%
[17 empty] | 101689153.43 | 80.5%
GEO | 2013-11-25 | GEO-1 | MOU WORK | 1 | 1378 | [10 empty] | 1378 | 101690531.43 | 80.5%
[17 empty] | 101690531.43 | 80.5%
[17 empty] | 101690531.43 | 80.5%
WVU | 2013-03-12 | WVU 1 | Fiber Testing and Repair | 10 | [9 empty] | 4603.2 |  | 4603.2 | 101695134.63 | 80.5%
MATCH | MATCH | MATCH | MATCH | MATCH | 105000 | [6 empty] | 27192000 |  | 6203000
Sub-Totals |  |  |  |  | 2322956.83 | 554403.04 | 12411876.02 | 489954.2 | 2060303.55 | 81510.56 | 23412772.2 | 35288277.42 | 0 | 58493301.64 | 79779.17 | 135195134.63 | 101695134.63 | 80.5%
Cost Classification Total Spent to Date |  |  |  |  | 2322956.83 | 554403.04 | 12411876.02 | 489954.2 | 2060303.55 | 58782560.18 |  |  |  | 58493301.64 | 79779.17 | 135195134.63
Cost Classifcaton Funds REMAINING |  |  |  |  | 1507043.17 | -16203.04 | 858359.98 | 4917845.8 | -1360303.55 | 19940069.82 |  |  |  | -1756582.64 | 537931.83 | 24628161.37 | %Remaining | 19.5%
Revised 12-12-13
|  |  |  | DHHR/OEMS | 392632.05 | 554403.04 | 10208459.42 | 404793.8 | 0 | 0 | 0 | 2391658.32 | 0 | 21412270.16 | 36279.06 | 35400495.85 | DHHR/OEMS
|  |  |  | LCC | 0 | 0 | 0 | 0 | 2060303.55 | 0 | 0 | 5704619.1 | 0 | 0 | 0 | 7764922.65 | LCC
|  |  |  | MA | 654802.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24390.94 | 679192.96 | MA
|  |  |  | WVDE | 31521.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1933.43 | 33455.12 | WVDE
|  |  |  | GEO | 1378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1378 | GEO
|  |  |  | WVU | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4603.2 | 0 | 4603.2 | WVU
|  |  |  | WVNET | 45990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116.6 | 1990.06 | 48096.66 | WVNET
|  |  |  | WVOT/FTR | 267660.4 | 0 | 0 | 85160.4 | 0 | 70100.56 | 23412772.2 | 0 | 0 | 0 | 981.67 | 23836675.23 | WVOT/FTR
|  |  |  | WVOT | 823972.67 | 0 | 2203416.6 | 0 | 0 | 11410 | 0 | 0 | 0 | 30873311.68 | 14204.01 | 33926314.96 | WVOT
|  |  |  | SUM CHECK | 2217956.83 | 554403.04 | 12411876.02 | 489954.2 | 2060303.55 | 81510.56 | 23412772.2 | 8096277.42 | 0 | 52290301.64 | 79779.17 | 101695134.63 | SUM CHECK